## input
DEPT_NAME_MANAGING | PROJ_ID | PROJ_TITLE | PROJ_DESCRIPTION | EMP_ID_PMGR | EMP_NAME | EMP_ID_CMGR | EMP_CONS_MGR_NAME | EMP_SR_PROJ_MGR_NAME | DEPT_ID | DEPT_ID_MANAGING | PPHASE_ID | PPHASE_NAME | PTYPE_ID | PTYPE_NAME | PROJ_GRANT | TRACKER_ID | PROJ_FUND | PROJ_IS_FUNDED | PROJ_BILLABLE | PROJ_DISTRICT_1 | PROJ_DISTRICT_2 | PROJ_DISTRICT_3 | PROJ_DISTRICT_4 | PROJ_DAY_TO_DATE | PROJ_BID_AMT | PROJ_CO_COST | PROJ_DAYS_DUE_TO_CO | PROJ_COS_AFFECT_TIME | PROJ_ADJ_CONTRACT_COST | PROJ_CONTRACT_AMT | PROJ_HISTORICAL_CHARGEBACK | PROJ_CONST_EST | PROJ_ESTIMATE | FAMIS_BUDGET_BALANCE | FAMIS_ACTUAL_BALANCE | FAMIS_ENCUMBRANCES | FAMIS_COMMITMENTS | FAMIS_BALANCE | Expr2 | PLANNING_PS_BASELINE_START_DT | PLANNING_PS_BASELINE_END_DT | PLANNING_PS_ACTUAL_START_DT | PLANNING_PS_ACTUAL_END_DT | PLANNING_PS_ON_SCHEDULE_YN | Expr3 | DESIGN_PS_BASELINE_START_DT | DESIGN_PS_BASELINE_END_DT | DESIGN_PS_ACTUAL_START_DT | DESIGN_PS_ACTUAL_END_DT | DESIGN_PS_ON_SCHEDULE_YN | Expr5 | BIDDING_PS_BASELINE_START_DT | BIDDING_PS_BASELINE_END_DT | BIDDING_PS_ACTUAL_START_DT | BIDDING_PS_ACTUAL_END_DT | BIDDING_PS_ON_SCHEDULE_YN | Expr6 | CONST_PS_BASELINE_START_DT | CONST_PS_BASELINE_END_DT | CONST_PS_ACTUAL_START_DT | CONST_PS_ACTUAL_END_DT | CONST_PS_ON_SCHEDULE_YN | Expr7 | WARRANTY_PS_BASELINE_START_DT | WARRANTY_PS_BASELINE_END_DT | WARRANTY_PS_ACTUAL_START_DT | WARRANTY_PS_ACTUAL_END_DT | WARRANTY_PS_ON_SCHEDULE_YN | DESIGN_CONTRACT_AMT | ORIGINAL_CONTRACT_AMOUNT | APPROVED_CHANGE_ORDER_TOTAL | REVISED_CONTRACT_AMOUNT | ADDITIONAL_DAYS | ALL_YEARS_APPROP | EXPINDITURE_TO_DATE | SLOG_ID | SLOG_DATE | SLOG_DATE_END | STATUS_TASK | SLOG_ON_BUDGET | SLOG_ON_SCHEDULE | WBS_ID_LEVEL1 | WBS_ID_LEVEL2 | WBS_ID_LEVEL3 | WBS_NAME_1 | WBS_NAME_2 | WBS_NAME_3 | PROJ_CONCENT_DECREE | PROJ_CAAP | PROJ_ENTER_DT | PROJ_CAPACITY_WATER | PROJ_CAPACITY_SEWER | PROJ_BOND
Public Works | P00401 | REGIONAL RENEWAL/REPLACEMENT | This project supports specific Central Regional projects derived from the annual George T. Lohmeyer Wastewater Treatment Plant Renewal and Replacement Requirement Analysis (R&R). Available funding balances are identified then transferred to specific Central Region projects. | 967 | Miguel Arroyo |  |  | Miguel Arroyo | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 451 | Yes |  | -1 | -1 | -1 | -1 | [10 empty] | 7685937.34 | 4688033.96 | 0 | 0 | 2997903.38 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 7685937.34 | 4688091.453 | 70325 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 46 | Public Works | Water Sewer | Recap | No | No |  |  |  | No
Public Works | P10814 | CENTRAL NEW RIVER WATER MAIN RIVER CROSSINGS | The CITYs existing water transmission system includes a 16-inch pipe that crosses the New River at SE 1 Avenue and an existing 12-inch pipe that crosses the New River at SW 7Avenue. Both of these river crossings are sub-aqueous pipelines. Replacement pipelines are currently under design and will be replaced from new river all the way up to Broward boulevard. | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 495 | Yes | Yes | 0 | 0 | 0 | -1 | [6 empty] | 2188970 |  |  |  | 3765470.57 | 1171072.81 | 2287190.5 | 0 | 307207.26 | PLANNING | 4/4/2018 0:00 | 7/19/2018 0:00 | 4/4/2018 0:00 | 3/3/2022 0:00 |  | DESIGN | 7/20/2018 0:00 | 12/26/2018 0:00 | 3/4/2022 0:00 | 6/5/2022 0:00 |  | BIDDING | 12/27/2018 0:00 | 4/27/2019 0:00 | 6/6/2022 0:00 | 1/31/2023 0:00 |  | CONST | 4/28/2019 0:00 | 10/28/2019 0:00 | 2/1/2023 0:00 | 2/1/2024 0:00 |  | WARRANTY | 10/28/2019 0:00 | 10/27/2020 0:00 | 2/1/2024 0:00 | 2/1/2025 0:00 |  |  | 2188970 |  |  |  | 3765470.57 | 1404249.24 | 73728 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | No | [6 empty] | No | No |  |  |  | No
Public Works | P10850 | VICTORIA PARK A - NORTH SMALL WATERMAIN IMPROVEMENTS | Small Water Main replacement in the Victoria Park-North neighborhood. Replace approximately 26500 linear feet of existing undersized and deteriorated small water mains with new 6 and 8 polyvinyl chloride pipe water mains and improve fire hydrant coverage. | 1212 | Daniel Fisher |  |  | Scott Teschky | PBS | PBS | 8 | Warranty | 37 | Water Sewer | No | CM |  | Yes | Yes | 0 | -1 | 0 | 0 | 42 |  | 170356.2 |  |  | 4008101.2 | 3837745 | 139238 | 2906750.63 |  | 5268928.11 | 5266947.6 | 0 | 0 | 1980.51 | PLANNING | 7/16/2015 0:00 | 9/18/2015 0:00 | 7/16/2015 0:00 | 9/18/2015 0:00 |  | DESIGN | 9/20/2015 0:00 | 7/31/2018 0:00 | 9/20/2015 0:00 | 8/24/2018 0:00 |  | BIDDING | 8/1/2018 0:00 | 10/31/2018 0:00 | 8/24/2018 0:00 | 3/15/2019 0:00 |  | CONST | 11/1/2018 0:00 | 3/1/2020 0:00 | 3/11/2019 0:00 | 5/7/2020 0:00 |  | WARRANTY | 3/1/2020 0:00 | 3/1/2021 0:00 | 5/7/2020 0:00 | 5/7/2021 0:00 |  | 108560 | 3837745 | 170356.2 | 4008101.2 | 42 | 5268928.11 | 5684951.44 | 70326 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 61 | 34 | Public Works | WW2011 | New Construction | No | No
Public Works | P10909 | FIRE STATION #8 | This project consists of the design and construction a new facility at 1801 SW 1st Ave. pursuant to the 2004 Fire Rescue Facilities Bond as described in resolution No.04-124. CPZ Architects Inc. is the Design Consultant. The land for this project was acquired thru a land-swap agreement between the City and All Aboard Florida. Fire Station 8 will be next to the Wave Streetcar Vehicle Maintenance Facility. This project includes demolition and environmental remediation of the existing site. | 687 | Alex Rio | 687 | Alex Rio | Raymond Nazaire | FIR | PBS | 8 | Warranty | 22 | CityFacilities | No |  |  | Yes |  | 0 | 0 | 0 | -1 | 69 |  | 6930 |  | YES | 4172060 | 4165130 |  |  |  | 6141515.56 | 5943737.44 | 95096.2 | 0 | 102681.92 | PLANNING | 4/16/2015 0:00 | 8/15/2015 0:00 | 4/16/2015 0:00 | 8/15/2015 0:00 |  | DESIGN | 8/17/2015 0:00 | 5/4/2018 0:00 | 8/17/2015 0:00 | 5/4/2018 0:00 |  | BIDDING | 5/4/2018 0:00 | 7/10/2018 0:00 | 5/4/2018 0:00 | 10/15/2018 0:00 |  | CONST | 7/11/2018 0:00 | 8/11/2019 0:00 | 10/15/2018 0:00 | 11/1/2021 0:00 |  | WARRANTY | 8/11/2019 0:00 | 8/11/2020 0:00 | 1/20/2021 0:00 | 1/20/2022 0:00 |  | 578729 | 4165130 | 6930 | 4172060 | 69 | 6141515.56 | 6605070.135 | 72390 | 12/6/2023 0:00 |  | STATUS | Yes | Yes | 3 | 17 | 34 | Fire | Fire Bond | New Construction | No | Yes
Public Works | P10918 | NEW FIRE STATION 13 | This project consists of the design and construction a new fire station facility at Hugh Taylor Birch State Park pursuant to the 2004 Fire Rescue Facilities Bond as described in resolution No. 04-124. ACAI & Associates is the Architectural Design Consultant for this project. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | FIR | PBS | 2 | Design | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 12801603.55 | 763969.07 | 360746.87 | 0 | 11676887.61 | PLANNING | 4/16/2015 0:00 | 10/1/2018 0:00 | 4/16/2015 0:00 | 10/31/2019 0:00 |  | DESIGN | 10/1/2018 0:00 | 10/26/2019 0:00 | 6/15/2020 0:00 | 3/22/2024 0:00 |  | BIDDING | 10/28/2019 0:00 | 1/27/2020 0:00 | 3/23/2024 0:00 | 8/30/2024 0:00 |  | CONST | 1/28/2020 0:00 | 2/28/2021 0:00 | 9/2/2024 0:00 | 10/27/2025 0:00 |  | WARRANTY | 3/1/2021 0:00 | 3/1/2022 0:00 | 10/28/2025 0:00 | 10/28/2026 0:00 | [6 empty] | 12801603.55 | 986214.9925 | 73348 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | 3 | 17 | 34 | Fire | Fire Bond | New Construction | No | No
Public Works | P11065 | ELECTRICAL IMPROVEMENTS NEW RIVER | Upgrade of electrical service centers for 16 slips on the north side of the New River. Funding to be off-set through a grant from the Florida Inland Navigation District (FIND) with match from City. To be programmed in CIP. Topo survey has been done. | 1156 | Danica Grujicic | 883 | Irina Tokar | Raymond Nazaire | PKR | PBS | 2 | Design | 12 | Parks | No | CM |  | Yes | Yes | 0 | 0 | 0 | -1 |  |  | 0 |  |  | 0 |  |  | 1200000 |  | 712774.63 | 122907.63 | 0 | 0 | 589867 | PLANNING | 9/30/2016 0:00 | 11/30/2016 0:00 | 9/30/2016 0:00 | 2/4/2020 0:00 |  | DESIGN | 10/1/2017 0:00 | 7/15/2018 0:00 | 2/5/2020 0:00 | 5/14/2024 0:00 |  | BIDDING | 8/15/2018 0:00 | 11/15/2018 0:00 | 5/15/2024 0:00 | 9/2/2024 0:00 |  | CONST | 1/5/2019 0:00 | 7/5/2019 0:00 | 9/3/2024 0:00 | 6/3/2025 0:00 |  | WARRANTY | 7/6/2019 0:00 | 7/6/2020 0:00 | 6/4/2025 0:00 | 6/4/2026 0:00 |  |  |  | 0 | 0 |  | 712774.63 | 235711.915 | 73777 | 3/5/2024 0:00 |  | STATUS | Yes | Yes | 6 | 16 | 38 | Parks and Recreation | Marine Facilities | General Upgrades | No | No
Public Works | P11419 | RIVER OAKS STORMWATER PARK | This project is for the conceptual design (Phase 1) of a 9.1 acres of undeveloped land for use as a stormwater park. Conceptual design includes a new berm water control basins and an underground conveyance system that would lead to the creation of the stormwater park. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | Yes |  |  | Yes | No | 0 | 0 | 0 | -1 |  |  | 0 | [7 empty] | 4460015.4 | 4370154.8 | 72911.78 | 0 | 16948.82 | PLANNING | 10/3/2016 0:00 | 12/31/2016 0:00 | 10/3/2016 0:00 | 4/19/2017 0:00 |  | DESIGN | 1/1/2017 0:00 | 10/16/2017 0:00 | 8/17/2017 0:00 | 9/13/2018 0:00 |  | BIDDING | 10/17/2017 0:00 | 1/4/2018 0:00 | 9/14/2018 0:00 | 1/1/2020 0:00 |  | CONST | 1/5/2018 0:00 | 9/30/2018 0:00 | 1/30/2020 0:00 | 7/1/2021 0:00 |  | WARRANTY | 10/1/2018 0:00 | 9/30/2019 0:00 | 7/1/2021 0:00 | 7/1/2022 0:00 |  |  |  | 0 |  |  | 4460015.4 | 4736147.313 | 73748 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 69 | 68 | Public Works | Environmental Services | Study/Investigation | No | No |  |  |  | No
Public Works | P11465 | 17TH ST. CAUSEWAY- LARGE WATER MAIN REPLACEMENT | This project is for the replacement of existing 10-12 water mains on SE 17 St from SE 4 Ave to Eisenhower Blvd. with 24 water mains; replacement of existing 10 water mains on Cordova Rd from SE 17 St to Se 10 Ave with 12 water main; replacement of existing 8 water main on Se 10 Ave from Cordova Rd. to SE 20 St with 12 water main. | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 2 | Design | 23 | Utilities | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [8 empty] | 4000000 | 150000 | 5787092 | 257892.17 | 225528.15 | 0 | 5303671.68 | PLANNING |  |  | 1/1/2022 0:00 | 12/31/2022 0:00 |  | DESIGN |  |  | 1/1/2023 0:00 | 10/30/2023 0:00 |  | BIDDING |  |  | 10/31/2023 0:00 | 3/29/2024 0:00 |  | CONST |  |  | 3/29/2024 0:00 | 3/31/2025 0:00 |  | WARRANTY |  |  | 4/1/2025 0:00 | 4/1/2026 0:00 | [6 empty] | 5787092 | 328238.57 | 73730 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 61 | 36 | Public Works | WW2011 | Replacement | No | No |  |  |  | No
Public Works | P11563 | VICTORIA PARK SEWER BASIN A-19 REHAB | Project includes the rehabilitation of mainline sewers manholes and service laterals. Work includes pre and post television survey flow monitoring traffic control and site restoration. | 697 | Louis Lafaurie | 936 | Luis Oliveira | Brandy Leighton | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | -1 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 465956 | 7438772 | 7310993.66 | 6.11 | 125195 | 2577.23 | PLANNING |  |  | 1/3/2013 0:00 | 7/10/2014 0:00 |  | DESIGN |  | 10/23/2017 0:00 | 7/14/2014 0:00 | 10/23/2017 0:00 |  | BIDDING |  |  | 5/1/2015 0:00 | 7/31/2015 0:00 |  | CONST | 8/31/2015 0:00 | 12/30/2018 0:00 | 8/31/2015 0:00 | 7/29/2024 0:00 |  | WARRANTY | 12/31/2018 0:00 | 12/31/2019 0:00 | 7/29/2024 0:00 | 7/29/2025 0:00 |  |  |  | 0 | 0 |  | 7438772 | 7896517.86 | 73663 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 80 | 43 | Public Works | PostWW2011 | Rehabilitation | Yes | No |  |  |  | No
Public Works | P11566 | RIO VISTA SEWER BASIN REHAB PS D-43 | This project includes the rehabilitation of Mainline Sewers in the Rio Vista neighborhood associated with pump station D-43. Work includes pre and post television survey flow monitoring traffic control and site restoration. This is part of the Wastewater Conveyance System Long Term Remediation Program. There is no bidding phase for this project. | 697 | Louis Lafaurie | 1059 | Katherine Griffith | Brandy Leighton | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 454 | Yes | Yes | 0 | 0 | 0 | -1 |  |  | 0 |  |  | 0 |  |  | 1484209 |  | 7442367 | 6781125.32 | 142879.76 | 109820 | 408541.92 | PLANNING |  |  | 10/6/2013 0:00 | 1/6/2015 0:00 |  | DESIGN |  |  | 1/7/2015 0:00 | 5/1/2016 0:00 |  | BIDDING | [5 empty] | CONST | 5/31/2015 0:00 | 7/13/2018 0:00 | 5/31/2015 0:00 | 7/30/2024 0:00 |  | WARRANTY | 7/14/2018 0:00 | 7/16/2019 0:00 | 7/30/2024 0:00 | 7/30/2025 0:00 |  |  |  | 0 | 0 |  | 7442367 | 7532284.641 | 73666 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 80 | 43 | Public Works | PostWW2011 | Rehabilitation | Yes | No |  |  |  | No
Public Works | P11589 | FIVEASH WATER TREATMENT PLANT DISINFECTION IMPROVEMENTS | This project is for the construction of two separately designed projects under one construction contract. Combining the projects is necessary because both projects need to be completed at the same time. Having one construction contract will avoid disputes between two contractors working at the same time and competing for staging areas and storage space on the crowded water treatment plant site. Under this approach both projects can be constructed in three years.The first project Reliability Upgrades installs various repairs and replacements throughout the plant. Major items include replacement of the control system for the entire plant replacement of the obsolete emergency generatorsmodifications to the high service pumps and increasing the weather resistance of the plant buildings | 894 | Steve Hillberg | 911 | To Be Determined | Steve Hillberg | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 |  |  | 0 | [5 empty] | 1400000 | 1400000 | 16850247.57 | 3406558.92 | 4556329.4 | 605868.3 | 8281490.95 | PLANNING | 1/19/2012 0:00 | 10/12/2015 0:00 | 1/19/2012 0:00 | 10/12/2015 0:00 |  | DESIGN | 10/12/2015 0:00 | 1/9/2019 0:00 | 10/12/2015 0:00 | 1/9/2019 0:00 |  | BIDDING | 3/16/2017 0:00 | 4/25/2017 0:00 | 1/9/2019 0:00 | 6/15/2020 0:00 |  | CONST | 5/2/2017 0:00 | 5/1/2020 0:00 | 9/15/2020 0:00 | 9/1/2024 0:00 |  | WARRANTY | 5/4/2020 0:00 | 5/4/2021 0:00 | 9/1/2024 0:00 | 9/1/2025 0:00 |  | 708663 |  | 0 |  |  | 16850247.57 | 3947553.969 | 73575 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 61 | 36 | Public Works | WW2011 | Replacement | No | No
City Manager | P11608 | NCIP RIVER GARDEN NEIGHBORHOOD IMPROVEMENTS | This project is an NCIP (Neighborhood Capital Improvements Project) for the design and construction of the Entryway Monuments and landscaping installation at NW 6th Street and 24th Avenue and NW 23rd Avenue. | [5 empty] | CM | CM | 2 | Design | 1 | NCIP | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 |  |  | 0 |  |  | 0 |  |  | 70000 |  | 70000 | 8226.26 | 0 | 0 | 61773.74 | PLANNING |  |  | 10/1/2020 0:00 | 11/1/2020 0:00 |  | DESIGN | 11/20/2017 0:00 | 7/31/2018 0:00 | 11/1/2020 0:00 | 2/1/2021 0:00 |  | BIDDING | 8/1/2018 0:00 | 9/28/2018 0:00 | 3/1/2021 0:00 | 5/1/2021 0:00 |  | CONST | 10/1/2018 0:00 | 1/11/2019 0:00 | 5/1/2021 0:00 | 11/1/2021 0:00 |  | WARRANTY | 1/11/2019 0:00 | 1/11/2020 0:00 | 11/1/2021 0:00 | 11/1/2022 0:00 |  |  |  | 0 | 0 |  | 70000 | 59031.7895 | 73180 | 1/26/2024 0:00 |  | STATUS | Yes | Yes | 84 | 26 | 34 | City Manager's Office | NCIP | New Construction | No | No
Public Works | P11632 | RIVIERA ISLES UTILITIES UNDERGROUNDING | This project is for the undergrounding of overhead utility lines for Riviera Isles by special assessment. | 1025 | Ingrid Kindbom |  |  | Ingrid Kindbom | CM | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 253600 | 3585.07 | 0 | 0 | 250014.93 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 253600 | 16899.94 | 73320 | 2/5/2024 0:00 | 2/5/2024 0:00 | STATUS | Yes | Yes | 84 | 26 | 34 | City Manager's Office | NCIP | New Construction | No | No |  |  |  | No
Transportation and Mobility | P11660 | PARKING ADMINISTRATION BUILDING STRUCTURAL REPAIRS | Repair and/or rehab various structural elements of the Parking Services administration building after the 40-year inspection. Anticipate need to rehab or replace elevator reinforce/replace windows stairwells seal and paint concrete walls storm-harden | 1150 | Diana Carrillo |  |  |  | TAM | TAM | 6 | Construction | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 |  |  | 0 |  |  | 0 |  |  |  |  | 293985 | 293755.68 | 0 | 0 | 229.32 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [7 empty] | 0 | 0 |  | 293985 | 294621.93 | 73082 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 28 | 43 | Transportation and Mobility | Facilities | Rehabilitation | No | No
Public Works | P11664 | BASIN B-6 SANITARY SEWER SYSTEM REHAB | Sanitary Sewer Collection System Rehabilitation - Basin B-6 (Coral Ridge area) relining of sanitary sewer collection mains and laterals and rehabilitation of manholes. | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  |  | Yes |  | -1 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 7530933 | 8537342 | 2005747 | 127077.1 | 1081980 | 0 | 796689.9 | PLANNING |  |  | 3/1/2022 0:00 | 2/1/2024 0:00 |  | DESIGN |  |  | 2/1/2024 0:00 | 5/1/2024 0:00 |  | BIDDING |  |  | 5/1/2024 0:00 | 8/1/2024 0:00 |  | CONST |  |  | 8/1/2024 0:00 | 8/1/2026 0:00 |  | WARRANTY |  |  | 8/1/2026 0:00 | 8/1/2026 0:00 |  |  |  | 0 | 0 |  | 2005747 | 307952.469 | 73706 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation | No | No |  |  |  | No
Public Works | P11681 | SR A1A STREETSCAPE IMPROVEMENTS (WESTSIDE) | Project is located on the West side of A1A and includes providing a safe pedestrian walkway by relocating trees and street lights to within 2 feet of the curb replacing the existing concrete sidewalk with decorative pavers and installing lighted bollards and pedestrian-scale lights. | 1293 | Gary Foster | 883 | Irina Tokar | Gary Foster | PKR | PBS | 6 | Construction | 27 | Roadway Improvements | No | CM | 346 | Yes | Yes | 0 | -1 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 4300000 |  | 11316743.71 | 9305354.44 | 1631395.86 | 90000 | 289993.41 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING |  |  | 4/1/2022 0:00 | 4/24/2023 0:00 |  | CONST |  |  | 4/24/2023 0:00 | 12/31/2023 0:00 |  | WARRANTY |  |  | 12/31/2023 0:00 | 12/31/2024 0:00 |  |  |  | 0 | 0 |  | 11316743.71 | 9368055.596 | 73782 | 3/6/2024 0:00 | 3/6/2024 0:00 | STATUS | Yes | Yes | 2 | 72 | 34 | Dept. of Sustainable Development | CRA | New Construction | No | No |  |  |  | No
Public Works | P11714 | IDLEWYLD UNDERGROUNDING OF OVERHEAD UTILITIES | This project is for the study and undergrounding of overhead utilities in the Idlewyld neighborhood by special assessment. | 1220 | Ingrid Kindbom |  |  | Ingrid Kindbom | CM | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 397769 | -32894.29 | 0 | 235607 | 195056.29 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [7 empty] | 0 | 0 |  | 397769 | 70529.1825 | 73327 | 2/5/2024 0:00 | 2/5/2024 0:00 | STATUS | Yes | Yes | 84 | 26 | 34 | City Manager's Office | NCIP | New Construction | No | No |  |  |  | No
Public Works | P11715 | LAS OLAS ISLES UNDERGROUNDING OF OVERHEAD UTILITIES | This project is for the undergrounding of all overhead utility lines on Las Olas Isles by special assessment. | 1220 | Ingrid Kindbom |  |  | Gary Foster | CM | PBS | 6 | Construction | 23 | Utilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | 330 |  | 1819447.49 |  |  | 6552847.49 | 4733400 |  |  | 8500000 | 9023731 | 6891548.03 | 1954140.18 | 0 | 178042.79 | PLANNING |  |  | 1/7/2019 0:00 | 1/6/2020 0:00 |  | DESIGN |  |  | 1/7/2020 0:00 | 8/14/2020 0:00 |  | BIDDING |  |  | 8/17/2020 0:00 | 2/7/2022 0:00 |  | CONST |  |  | 3/17/2022 0:00 | 11/11/2023 0:00 |  | WARRANTY |  |  | 11/11/2023 0:00 | 11/11/2024 0:00 |  |  | 4733400 | 1819447.49 | 6552847.49 | 330 | 9023731 | 8450601.958 | 73781 | 3/6/2024 0:00 | 3/6/2024 0:00 | STATUS | Yes | No | 84 | 26 | 34 | City Manager's Office | NCIP | New Construction | No | No |  |  |  | Yes
Public Works | P11722 | RIVERWALK SEAWALL REPLACEMENT NORTHSIDE | Approximately 1700 linear feet of seawall is aging along the North New River/Riverwalk area. The seawall and land behind it will be inspected in 2015 and a repair/replacement plan developed. Florida Inland Navigation District (FIND) Florida Boating Infrastructure Grants (FBIG) and Broward Boating Improvement Program (BBIP) grants will be applied for to offset construction costs. Funding will be for design permitting repair and replacement of portions of the existing seawall. | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PKR | PBS | 2 | Design | 33 | Seawalls | Yes |  |  | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 4938735.08 | 165404.83 | 0 | 0 | 4773330.25 | PLANNING | 1/1/2015 0:00 | 2/28/2017 0:00 | 1/1/2015 0:00 | 2/28/2017 0:00 |  | DESIGN | 4/23/2018 0:00 | 6/22/2018 0:00 | 7/30/2021 0:00 | 6/30/2024 0:00 |  | BIDDING | 6/22/2018 0:00 | 7/9/2018 0:00 | 6/30/2024 0:00 | 12/31/2024 0:00 |  | CONST | 8/30/2018 0:00 | 8/12/2019 0:00 | 12/31/2024 0:00 | 12/31/2025 0:00 |  | WARRANTY | 8/13/2019 0:00 | 8/13/2020 0:00 | 12/31/2025 0:00 | 12/31/2026 0:00 | [6 empty] | 4938735.08 | 311297.735 | 73771 | 3/5/2024 0:00 |  | STATUS | Yes | No | 52 | 16 | 34 | Building Services | Marine Facilities | New Construction | No | No
Public Works | P11781 | GT LOHMEYER WWTP CRYOGENIC PLANT UPGRADES | This project is to upgrade all equipment instrumentation and controls to the latest technology in order to automate the Cryogenic Plant and increase reliability. Project will include any required control room upgrades for proper space conditioning. The work includes engineering evaluation and upgrades to several components of the Cryogenic plant including upgrade of the control systems to PLC valve replacements cold box rehabilitation replacement of the motor control counter upgrades to back-up systems and maintenance of the air compressors. | 1355 | Wilfredo Negron |  |  | William Power | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 451 | Yes | Yes | 0 | 0 | 0 | -1 | 311 |  | 254632.53 |  |  | 17649632.53 | 17395000 |  | 17000000 |  | 15942384 | 15537586.29 | 239561.28 | 0 | 165236.43 | PLANNING | 1/29/2018 0:00 | 6/4/2018 0:00 | 1/29/2018 0:00 | 6/4/2018 0:00 |  | DESIGN |  |  | 6/5/2018 0:00 | 8/8/2019 0:00 |  | BIDDING |  |  | 8/9/2018 0:00 | 7/7/2020 0:00 |  | CONST |  |  | 7/8/2020 0:00 | 12/20/2023 0:00 |  | WARRANTY |  |  | 12/21/2023 0:00 | 12/21/2024 0:00 |  |  | 17395000 | 254632.53 | 17649632.53 | 311 | 15942384 | 15952797.13 | 73403 | 2/8/2024 0:00 | 2/8/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation | No | No |  |  |  | No
Parks and Rec | P11811 | MILLS POND OBSERVATION DECK | Construct observation deck and trail at Mills Pond Park. |  |  | 885 | Connie Hayman |  | PKR | PKR | 8 | Warranty | 12 | Parks | Yes |  | 129 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 75000 | 67692.92 | 0 | 0 | 7307.08 | PLANNING | 1/1/2013 0:00 | 9/11/2016 0:00 | 1/1/2013 0:00 | 9/11/2016 0:00 |  | DESIGN | 4/16/2018 0:00 | 5/25/2018 0:00 | 4/16/2018 0:00 | 7/13/2018 0:00 |  | BIDDING | 5/27/2018 0:00 | 7/16/2018 0:00 | 5/27/2018 0:00 | 9/17/2018 0:00 |  | CONST | 7/18/2018 0:00 | 9/3/2018 0:00 | 9/18/2018 0:00 | 2/18/2019 0:00 |  | WARRANTY | 9/4/2018 0:00 | 9/4/2019 0:00 | 2/18/2019 0:00 | 2/18/2020 0:00 | [6 empty] | 75000 | 168093.945 | 71788 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No | No
Public Works | P11827 | SEAWALL REPLACEMENT ALONG NEW RIVER | Replacement/repair of seawalls along New River and all adjoining waterways. --part of the Annual Marine Facilities Improvement contract. | 1170 | Omar Castellon | 692 | Dane Esdelle | Omar Castellon | PBS | PBS | 15 | Complete | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 |  | 801801 | 16815 |  |  | 131826 | 115011 |  | 801801 | 705000 | 226529.58 | 225945.58 | 0 | 0 | 584 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [6 empty] | 115011 | 16815 | 131826 |  | 226529.58 | 263692.765 | 70328 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No | No |  |  |  | No
Public Works | P11842 | EDGEWOOD AREA STORMWATER IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The Edgewood neighborhood is currently under construction as part of the 1st tranche of neighborhoods to go into construction. Construction is expected to be completed by mid 2024.This project is part of the in-kind water quality consent order. | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 |  |  | 0 |  |  |  | 14471533 |  | 26000000 |  | 18775080 | 14569972 | 4205131.1 | 0 | -23.1 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/16/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/31/2017 0:00 | 5/16/2016 0:00 | 10/31/2020 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 6/4/2021 0:00 | 10/29/2021 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 10/30/2021 0:00 | 3/29/2024 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 3/30/2024 0:00 | 3/29/2025 0:00 |  |  | 14471533 | 0 |  |  | 18775080 | 14876095.56 | 73632 | 2/22/2024 0:00 | 2/22/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 68 | Public Works | Stormwater | Study/Investigation | Yes | No |  |  |  | Yes
Public Works | P11843 | PROGRESSO STORMWATER IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The Progresso neighborhood has been designed permitted and it is ready for bid once CEI services can be procured. Due to Procurement logistics and engineering staff resources we estimate the project will out to bid in late 2023/early 2024 as the 5th of the 7 neighborhood projects behind Edgewood and River Oaks (both in construction) Dorsey Riverbend and Durrs. | 1336 | Scarlet Del Valle |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 470 | Yes | No | 0 | 0 | -1 | 0 | [10 empty] | 14192943 | 649635.86 | 2999871 | 0 | 10543436.14 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/16/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/31/2017 0:00 | 1/1/2024 0:00 | 6/30/2024 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 7/1/2024 0:00 | 12/31/2024 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 4/30/2024 0:00 | 1/1/2027 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 1/1/2027 0:00 | 1/1/2028 0:00 | [6 empty] | 14192943 | 664981.7275 | 73727 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 82 | 68 | Public Works | Utilities Engineering | Study/Investigation | No | No |  |  |  | Yes
Public Works | P11844 | DURRS AREA STORMWATER IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The Durrs neighborhood has been designed permitted and it is ready for bid in early 2023 at the same time as Dorsey Riverbend neighborhood. Durrs and Dorsey Riverbend will be the second tranche of the 7 priority neighborhoods to go into construction behind Edgewood and River Oaks and are expected to take approximately 2 years to construct.This project will be partially funded $10.5 million by a Florida Department of Economic Opportunity grant. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 4 | Bidding | 36 | Stormwater | Yes |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 23736977 | 1047535.67 | 1528131.88 | 0 | 21161309.45 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/16/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/31/2017 0:00 | 5/16/2016 0:00 | 7/28/2023 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 7/31/2023 0:00 | 2/29/2024 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 3/4/2024 0:00 | 3/4/2026 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 3/5/2026 0:00 | 3/5/2027 0:00 | [6 empty] | 23736977 | 1185287.45 | 73752 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 |  |  | Public Works |  |  | No | No |  |  |  | Yes
Public Works | P11845 | DORSEY RIVERBEND STORMWATER IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The Dorsey Riverbend neighborhood has been designed permitted and it is ready for bid in early 2023 at the same time as Durrs neighborhood. Durrs and Dorsey Riverbend will be the second tranche of the 7 priority neighborhoods to go into construction behind Edgewood and River Oaks and are expected to take approximately 3 years to construct. | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 4 | Bidding | 36 | Stormwater | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 13533691 | 1018042.63 | 1809566.25 | 10584881 | 121201.12 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/15/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/31/2017 0:00 | 5/16/2016 0:00 | 11/1/2023 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 11/3/2023 0:00 | 4/2/2024 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 4/3/2024 0:00 | 4/3/2026 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 4/4/2026 0:00 | 4/3/2027 0:00 | [6 empty] | 13533691 | 1068400.21 | 73631 | 2/22/2024 0:00 | 2/22/2024 0:00 | STATUS | Yes | Yes | [6 empty] | No | No |  |  |  | Yes
Public Works | P11868 | RIVER OAKS STORMWATER IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The River Oaks neighborhood is currently under construction as part of the 1st tranche of neighborhoods to go into construction. Construction is expected to be completed by early 2024. This project is part of the in-kind water quality consent order. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [6 empty] | 25043981.79 |  |  |  | 29992578 | 22439258.82 | 7435241.33 | 0 | 118077.85 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/16/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/30/2017 0:00 | 5/16/2016 0:00 | 2/26/2021 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 3/1/2021 0:00 | 12/13/2021 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 12/14/2021 0:00 | 12/15/2024 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 12/16/2024 0:00 | 12/16/2025 0:00 |  |  | 25043981.79 |  |  |  | 29992578 | 22800447.91 | 73753 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 38 | Public Works | Stormwater | General Upgrades | Yes | No |  |  |  | Yes
Public Works | P11887 | NW SECOND AVENUE TANK RESTORATION | This project repaints the elevated tank inside and out adds a new logo around the entire tank adds a new LED lighting system for the logo replaces ladders up the tank and upgrades railings around the tank to meet safety codes makes structural repairs to the tank replaces the aircraft obstruction lights wth LED lights replaces the fencing around the site adds decorative fencing along the street site of the site and adds landscaping to the site. | 894 | Steve Hillberg |  |  | Steve Hillberg | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | -1 | 0 | 0 |  | 2801900 | 0 |  |  |  | 1901300 |  | 1700000 | 2500000 | 2743992.05 | 2613840.08 | 0 | 84100 | 46051.97 | PLANNING | 12/17/2014 0:00 |  | 12/17/2014 0:00 | 8/18/2015 0:00 |  | DESIGN | 2/2/2016 0:00 | 1/5/2017 0:00 | 2/9/2016 0:00 | 1/31/2017 0:00 |  | BIDDING | 1/17/2017 0:00 | 2/1/2017 0:00 | 6/19/2017 0:00 | 4/27/2018 0:00 |  | CONST | 2/15/2017 0:00 | 10/19/2017 0:00 | 4/30/2018 0:00 | 10/30/2019 0:00 |  | WARRANTY | 10/20/2017 0:00 | 11/20/2018 0:00 | 10/30/2019 0:00 | 10/30/2020 0:00 |  | 401640 | 1901300 | 0 |  |  | 2743992.05 | 3002565.598 | 73576 | 2/16/2024 0:00 |  | STATUS | Yes | No | 8 | 82 | 43 | Public Works | Utilities Engineering | Rehabilitation | No | No
Community Redevelopment | P11900 | LAS OLAS BLVD CORRIDOR IMPROVEMENTS | This project is part of implementing the overall Beach Master Plan. The project limits are from the intracoastal waterway to the Atlantic Ocean and may include re-development of the Las Olas Blvd including a wide promenade from the beach to the Intracoastal. Other improvements may include redevelopment of the Oceanside Parking Lot a new parking structure adjacent to the Las Olas Bridge and redevelopment of the canal adjacent to Las Olas Circle. | 1278 | Alex Torres |  |  | Thomas Green | CRA | CRA | 6 | Construction | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 46560825.42 | 46112509.6 | 0 | 0 | 448315.82 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [7 empty] | 0 | 0 |  | 46560825.42 | 46123636.4 | 73220 | 1/29/2024 0:00 |  | STATUS | Yes | Yes | 77 | 74 | 34 | Economic Development | Beach CRA | New Construction | No | No
Public Works | P11901 | VICTORIA PARK B - SOUTH SMALL WATERMAIN IMPROVEMENTS | Small Water Main replacement in the Victoria Park neighborhood - South. Replace approximately 29000 linear feet of existing undersized and deteriorated small water mains with new 6 and 8 polyvinyl chloride pipe water mains and improving fire hydrant coverage. | 1212 | Daniel Fisher |  |  | Scott Teschky | PBS | PBS | 8 | Warranty | 37 | Water Sewer | No | CM |  | Yes | Yes | 0 | -1 | 0 | 0 | 20 |  | 618758.26 |  |  | 6896433.26 | 6334875 |  | 4298945.72 |  | 7990255.51 | 7983369.31 | 0 | 0 | 6886.2 | PLANNING | 7/16/2015 0:00 | 9/18/2015 0:00 | 7/16/2015 0:00 | 9/18/2015 0:00 |  | DESIGN | 9/20/2015 0:00 | 7/31/2018 0:00 | 9/20/2015 0:00 | 7/31/2018 0:00 |  | BIDDING | 8/1/2018 0:00 | 10/31/2018 0:00 | 8/1/2018 0:00 | 10/31/2018 0:00 |  | CONST | 11/1/2018 0:00 | 3/1/2020 0:00 | 3/11/2019 0:00 | 9/19/2021 0:00 |  | WARRANTY | 3/1/2020 0:00 | 3/1/2021 0:00 | 9/19/2021 0:00 | 9/19/2022 0:00 |  | 165560 | 6334875 | 618758.26 | 6896433.26 | 20 | 7990255.51 | 8371706.438 | 70330 | 1/22/2024 0:00 |  | STATUS | Yes | Yes |  | 61 | 36 |  | WW2011 | Replacement | No | No
Information Technology | P11937 | ENTERPRISE RESOURCE PLANNING (ERP) PROJECT | Hire a consultant to develop specifications to purchase a Financial Systems Modernization - ERP (Enterprise Resource Planning System) Information Technology Services is assisting the Finance Department in seeking an ERP to provide integration of business management practices and modern technology. In simpler words an ERP is a massive software architecture that supports the streaming and distribution of geographically scattered enterprise information across all the departments of the city. An ERP systemâ€™s key objective is to integrate information and processes from all functional divisions of an organization and merge it for effortless access and structure. | 1312 | Angela Marinas |  |  |  | ITS | ITS | 25 | Implementation | 22 | CityFacilities | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 10358117.13 | 9574264.85 | 650626.32 | 0 | 133225.96 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 10358117.13 | 9574283.835 | 73047 | 1/19/2024 0:00 | 1/19/2024 0:00 | STATUS | Yes | Yes | 4 |  | 39 | Information Technology |  | Technology | No | No | 7/26/2013 14:36
Public Works | P11991 | DOWNTOWN SEWER BASIN PS A-7 REHABILITATION | The project includes the rehabilitation of manholes lateral service connections main lines point repairs minor road restoration and landscaping the use of trenchless technologies to repair sewer system components such as lining of gravity sewers manholes and sewer laterals. Work also includes pre and post rehabilitation close circuit television survey flow monitoring traffic control and site restoration. | 697 | Louis Lafaurie | 936 | Luis Oliveira | Brandy Leighton | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 454 | Yes | Yes | 0 | -1 | 0 | -1 | [10 empty] | 11664894 | 5793199.38 | 2737240.28 | 127565 | 3006889.34 | PLANNING |  |  | 10/4/2013 0:00 | 4/15/2014 0:00 |  | DESIGN |  |  | 4/1/2014 0:00 | 9/29/2017 0:00 |  | BIDDING |  |  | 1/21/2015 0:00 | 3/9/2015 0:00 |  | CONST | 4/21/2015 0:00 | 12/28/2018 0:00 | 4/21/2015 0:00 | 7/30/2024 0:00 |  | WARRANTY | 12/29/2018 0:00 | 12/29/2019 0:00 | 7/30/2024 0:00 | 7/30/2025 0:00 | [6 empty] | 11664894 | 6652307.916 | 73662 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 34 | Public Works | Utilities Engineering | New Construction | Yes | No | 9/19/2013 15:52 |  |  | No
Public Works | P12010 | 2013-14 ANNUAL BRIDGE RESTORATION CONTRACT | This project is for the restoration of bridges with epoxy coating including but not limited to: concrete spalls cracks expansion joints bulkheads and concrete piles replacement of extremely corroded rebars painting and other maintenance. | 1195 | Ana Ziegler | 692 | Dane Esdelle | Raymond Nazaire | PBS | PBS | 10 | Annual | 2 | Annual | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 |  |  | 0 |  |  |  | 266973.26 |  |  |  | 4797191 | 2211311.29 | 2100608 | 0 | 485271.71 | PLANNING |  |  | 2/20/2023 0:00 |  |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  |  | 2/20/2025 0:00 |  | WARRANTY | [6 empty] | 266973.26 | 0 |  |  | 4797191 | 3289794.425 | 73770 | 3/5/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No | No | 10/23/2013 15:40 |  |  | No
Public Works | P12020 | HECTOR PARK STORMWATER IMPROVEMENTS | The Project includes the installation of new stormwater infrastructure including a well to address documented flooding issues at the site. This Project is included in Phase 1 of the Stormwater Master Plan for FY19. | 1206 | Francisco Rios |  |  | Rares Petrica | PBS | PBS | 15 | Complete | 36 | Stormwater | No |  | 470 | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 811445.24 | 811445 | 0 | 0 | 0.24 | PLANNING |  |  | 8/24/2014 0:00 | 9/30/2018 0:00 |  | DESIGN |  |  | 10/1/2018 0:00 | 10/31/2019 0:00 |  | BIDDING |  |  | 8/1/2019 0:00 | 11/15/2019 0:00 |  | CONST |  |  | 9/14/2020 0:00 | 4/17/2021 0:00 |  | WARRANTY |  |  | 4/18/2021 0:00 | 4/17/2022 0:00 | [6 empty] | 811445.24 | 968763.79 | 70331 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction | No | No | 2/21/2014 11:33
Public Works | P12034 | 1416 SE 11 COURT STORMWATER IMPROVEMENTS | The project includes the installation of new stormwater infrastructure to address documented flooding issues at the site. This Project is included in Phase 1 of the Stormwater Master Plan | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 15 | Complete | 36 | Stormwater | No |  | 470 | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 1028068 | 871974.52 | 0 | 0 | 156093.48 | PLANNING |  |  | 2/24/2014 0:00 | 9/4/2018 0:00 |  | DESIGN |  |  | 9/5/2018 0:00 | 12/14/2018 0:00 |  | BIDDING |  |  | 12/17/2018 0:00 | 9/30/2019 0:00 |  | CONST |  |  | 9/30/2019 0:00 | 8/31/2021 0:00 |  | WARRANTY |  |  | 9/1/2021 0:00 | 9/1/2022 0:00 | [6 empty] | 1028068 | 872197.44 | 73754 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction | No | No | 2/27/2014 8:22
Public Works | P12045 | CITYWIDE WATERWAY SURVEYS | In February 18 2014 City Commission Conference meeting CC approved the survey of the City Canals that have not been surveyed in order to get estimates for City-wide canal dredging needs estimated costs and schedules. There are approximately 300 canals in need of surveying located throughout the City. All these waterways are the priority for this survey project. | 1100 | Rares Petrica |  |  | Rares Petrica | PBS | PBS | 15 | Complete | 31 | Canals | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 750241 | 730088 | 0 | 0 | 20153 | PLANNING |  |  | 4/8/2014 0:00 | 2/28/2018 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 750241 | 1401630.823 | 70332 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 |  | 68 | Public Works |  | Study/Investigation | No | No | 3/19/2014 17:01
Public Works | P12049 | FLAGLER HEIGHTS SEWER BASIN A-21 LATERALS | The rehabilitation of sewer laterals identified in Sewer Basin A-21 by using the cured-in-place pipe method for lateral pipes. The work will include pre and post TV survey flow monitoring flow bypass satisfactory rehabilitation of the sewer laterals in Sewer Basin A-21. There is no bidding phase for this project. | 697 | Louis Lafaurie | 1059 | Katherine Griffith | Brandy Leighton | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 482 | Yes | Yes | 0 | -1 | 0 | 0 | [6 empty] | 400529.8 |  |  |  | 4126452 | 2109804.41 | 1718977.41 | 0 | 297670.18 | PLANNING | 7/1/2014 0:00 | 10/1/2014 0:00 | 7/1/2014 0:00 | 10/1/2014 0:00 |  | DESIGN | 10/2/2014 0:00 | 6/4/2015 0:00 | 10/2/2014 0:00 | 6/29/2016 0:00 |  | BIDDING | [5 empty] | CONST | 2/4/2015 0:00 | 5/30/2015 0:00 | 6/30/2016 0:00 | 6/29/2024 0:00 |  | WARRANTY |  |  | 6/30/2024 0:00 | 7/30/2025 0:00 |  |  | 400529.8 |  |  |  | 4126452 | 2576955.99 | 73667 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 34 | Public Works | Utilities Engineering | New Construction | Yes | No | 4/23/2014 10:21 |  |  | No
Public Works | P12055 | BASIN A-18 SANITARY SEWER COLLECTION SYSTEM REHABILIATION | This project is for the sanitary sewer collection system rehabilitation located at Basin A -18 (Dorsey-Riverbend area). The project will include relining of sanitary sewer collection mains and laterals. | 697 | Louis Lafaurie | 1059 | Katherine Griffith | Brandy Leighton | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | 0 | -1 | 0 | [9 empty] | 580858 | 7160276 | 6795540.77 | 12.57 | 171205 | 193517.66 | PLANNING | 7/21/2014 0:00 | 1/30/2015 0:00 | 7/21/2014 0:00 | 1/30/2015 0:00 |  | DESIGN | 2/1/2015 0:00 | 9/30/2015 0:00 | 2/1/2015 0:00 | 12/15/2016 0:00 |  | BIDDING |  |  | 9/15/2016 0:00 | 12/1/2016 0:00 |  | CONST | 5/30/2015 0:00 | 9/30/2015 0:00 | 12/16/2016 0:00 | 7/30/2024 0:00 |  | WARRANTY |  |  | 7/30/2024 0:00 | 7/29/2025 0:00 | [6 empty] | 7160276 | 7541263.835 | 73664 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 43 | Public Works | Utilities Engineering | Rehabilitation | Yes |  | 5/19/2014 10:40 |  |  | No
Public Works | P12058 | LAS OLAS TUNNEL TOP PARK | The City proposes to build a pedestrian friendly plaza on the top of an extended tunnel roof at the Federal Highway entrance to Las Olas Blvd. with park benches and areas designed for a shade and a tourist kiosk. This project is required to be led by Florida Department of Transportation (FDOT) to include Bridge Design Report Final Design and Construction. This project is the District 4 Park within the 2019 Parks Bond. | 1278 | Alex Torres |  |  | Alex Torres | PKR | PBS | 6 | Construction | 12 | Parks | No |  | 350 | Yes | No | 0 | 0 | 0 | -1 | [10 empty] | 12672748 | 2061779.43 | 0 | 0 | 10610968.57 | PLANNING |  |  | 6/1/2017 0:00 |  |  | DESIGN |  |  | 6/1/2019 0:00 |  |  | BIDDING |  |  | 1/2/2021 0:00 |  |  | CONST |  |  | 9/1/2021 0:00 |  |  | WARRANTY |  |  | 1/1/2024 0:00 | 12/31/2024 0:00 | [6 empty] | 12672748 | 2090732.93 | 73483 | 2/10/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No | Yes | 5/21/2014 10:54 |  |  | No
Public Works | P12070 | FXE MASTER PLAN UPDATE | Update of the Airport's existing Master Plan to provide future airfield and non-airfield development options for 5 10 and 20 years. The current Master Plan was completed in 2007 and approved by the Federal Aviation Administration in 2010. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 8 | Warranty | 3 | Airport | Yes | CM | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 193133 | 191444.56 | 95.8 | 0 | 1592.64 | PLANNING |  |  | 5/7/2015 0:00 | 7/26/2016 0:00 |  | DESIGN |  |  | 11/3/2016 0:00 | 12/31/2018 0:00 |  | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 193133 | 249621.94 | 70353 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 68 | Transportation and Mobility | Airport | Study/Investigation | No | No | 7/9/2014 15:55 |  |  | No
Public Works | P12074 | SOUTHEAST ISLES TIDAL AND STORMWATER IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The SE Isles area has been designed permitted and it is ready for bid in late 2024. SE Isles area will be the last neighborhood to be constructed out of the original 7 and construction is expected to take approximately 3 years. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | Yes |  | 470 | Yes | Yes | 0 | -1 | 0 | -1 | [10 empty] | 5688770 | 1619854.98 | 3431.2 | 0 | 4065483.82 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/16/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/31/2017 0:00 | 5/16/2016 0:00 | 12/31/2024 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 1/1/2025 0:00 | 4/1/2025 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 5/30/2025 0:00 | 12/30/2027 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 1/1/2028 0:00 | 1/1/2029 0:00 | [6 empty] | 5688770 | 1724824.563 | 73643 | 2/23/2024 0:00 | 2/23/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No | No | 7/29/2014 13:08 |  |  | Yes
Public Works | P12082 | VICTORIA PARK STORM NEIGHBORHOOD IMPROVEMENTS | This project is one of the 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program. The Victoria Park neighborhood has been designed permitted and it is ready for bid once CEI services can be procured. Due to Procurement logistics and engineering staff resources we estimate the project will out to bid in early 2024 as the 6th of the 7 neighborhood projects behind Edgewood and River Oaks (both in construction) Dorsey Riverbend Durrs and Progresso. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 5280000 | 2910684.73 | 2361031.44 | 0 | 8283.83 | PLANNING | 10/1/2014 0:00 | 5/16/2016 0:00 | 10/1/2014 0:00 | 5/16/2016 0:00 |  | DESIGN | 5/16/2016 0:00 | 12/31/2017 0:00 | 5/16/2016 0:00 | 9/30/2024 0:00 |  | BIDDING | 1/1/2018 0:00 | 8/30/2018 0:00 | 10/1/2024 0:00 | 3/31/2025 0:00 |  | CONST | 9/1/2018 0:00 | 12/31/2022 0:00 | 4/1/2025 0:00 | 2/28/2027 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 3/1/2027 0:00 | 3/1/2028 0:00 | [6 empty] | 5280000 | 2914580.11 | 73742 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No | No | 9/8/2014 14:00 |  |  | Yes
Parks and Rec | P12085 | FACILITY MAINTENANCE PRIORITIES (PLACEHOLDER) | This project is for large equipment repairs and for all other unknown capital repairs to existing facilities. The City has 130 buildings that are in continuous need of major equipment replacement and/or renovation. | 1143 | Enrique Sanchez |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 22 | CityFacilities | No | PBS |  | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 159239 | 118692.56 | 0 | 0 | 40546.44 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 159239 | 127525.56 | 73182 | 1/26/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 9/17/2014 15:41
Public Works | P12087 | BRIDGE REPLACEMENT AT SOUTH OCEAN DRIVE | This project is for the replacement of an existing bridge at South Ocean Drive. It is 80 feet long by 36 feet wide. City Bridge No. 865775 was built in 1952. The project will be designed with FY15 funding then accumulate funding for replacement cost. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 6 | Construction | 19 | Bridge | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 5236143 | 102508.78 | 4359970.2 | 0 | 773664.02 | PLANNING | 5/1/2016 0:00 | 3/5/2018 0:00 | 5/1/2016 0:00 | 3/5/2018 0:00 |  | DESIGN | 3/7/2018 0:00 | 3/25/2019 0:00 | 3/27/2018 0:00 | 2/28/2020 0:00 |  | BIDDING | 3/25/2019 0:00 | 4/30/2019 0:00 | 2/28/2023 0:00 | 11/7/2023 0:00 |  | CONST | 5/30/2019 0:00 | 9/30/2019 0:00 | 11/8/2023 0:00 | 4/5/2025 0:00 |  | WARRANTY | 9/30/2019 0:00 | 9/30/2020 0:00 | 4/6/2025 0:00 | 4/6/2026 0:00 | [6 empty] | 5236143 | 333091.75 | 73486 | 2/12/2024 0:00 |  | STATUS | Yes | No | [6 empty] | No | No | 9/17/2014 15:49 |  |  | No
Public Works | P12089 | BRIDGE REPLACEMENT AT COCONUT ISLE | Demolition of the existing Coconut Isle bridge and construction of a new bridge. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 15 | Complete | 19 | Bridge | No |  | 345 | Yes | Yes | 0 | -1 | 0 | 0 |  | 1096655.64 |  |  |  |  | 1418351 |  |  | 1096655.64 | 2028920 | 2025155.12 | 0 | 0 | 3764.88 | PLANNING | 10/29/2014 0:00 | 7/10/2016 0:00 | 10/29/2014 0:00 | 7/10/2016 0:00 |  | DESIGN | 7/13/2016 0:00 | 4/24/2018 0:00 | 7/13/2016 0:00 | 4/24/2018 0:00 |  | BIDDING | 8/14/2018 0:00 | 10/29/2018 0:00 | 9/27/2018 0:00 | 4/24/2019 0:00 |  | CONST | 10/29/2018 0:00 | 5/30/2019 0:00 | 1/6/2020 0:00 | 3/31/2021 0:00 |  | WARRANTY | 5/30/2019 0:00 | 5/30/2020 0:00 | 3/31/2021 0:00 | 3/30/2022 0:00 |  | 213247 | 1418351 |  |  |  | 2028920 | 2632535.04 | 70334 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 36 | Public Works | Bridges | Replacement | No | No | 9/18/2014 8:09
Parks and Rec | P12097 | NEW CARTER PARK SENIOR CENTER | Construction of a senior center at Carter Park a 5900 square foot facility with capacity of 250 participants. The center will include classrooms a fitness area technology and social areas. | 1320 | Marc Isaac |  |  | Thomas Green | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 2100000 | 34495 | 0 | 0 | 2065505 | PLANNING | 2/25/2015 0:00 | 3/31/2017 0:00 | 2/25/2015 0:00 | 3/31/2019 0:00 |  | DESIGN | 2/1/2019 0:00 | 2/1/2020 0:00 | 6/1/2019 0:00 | 2/1/2020 0:00 |  | BIDDING | 4/1/2020 0:00 | 7/1/2020 0:00 | 4/1/2020 0:00 | 7/1/2020 0:00 |  | CONST | 8/1/2020 0:00 | 8/1/2021 0:00 | 8/1/2020 0:00 | 8/1/2021 0:00 |  | WARRANTY | 8/2/2021 0:00 | 8/2/2022 0:00 | 8/2/2021 0:00 | 8/2/2022 0:00 | [6 empty] | 2100000 | 81543.5 | 73022 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 9/18/2014 12:04
Public Works | P12114 | ELECTRICAL/SCADA EVALUATION | This project holistically evaluates the overall plant and addresses the global needs with regards to the current condition of the various plant electrical and control systems. The output of the consultant would be a schedule that clearly identifies and prioritizes the work to be done to improve the electrical and control elements at the GTL WWTP. Furthermore it would evaluate the current SCADA and incorporates it into the same schedule. | 967 | Miguel Arroyo |  |  |  | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 451 | Yes | Yes | 0 | 0 | 0 | 0 | [10 empty] | 380000 | 23383 | 0 | 0 | 356617 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 380000 | 23446.52 | 67631 | 2/23/2023 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 38 | Public Works | Utilities Engineering | General Upgrades | No | No | 9/23/2014 9:34
Information Technology | P12123 | EOC DATA CENTER INFRASTRUCTURE UPGRADE | Aligning with the Cityâ€™s initiative to become a resilient and safe community the Information Technology Services (ITS) Department has begun implementing a disaster recovery data center at the EOC to provide direct access by emergency staff to critical computer and communications systems during an EOC activation and to house the Cityâ€™s critical computer and communications systems including the Public Works call center and public safety electronic data in a category 5 facility.Â The current air conditioning (AC) and electrical system does not provide adequate capacity and resiliency to support the computer and communications systems that will be relocated to the EOC.Â The current uninterruptible power supply (UPS) at the EOC is over 8 years old and nearing its end of life. Reliable AC | 1350 | Aarmondas Walker | 687 | Alex Rio |  | ITS | ITS | 15 | Complete | 22 | CityFacilities | Yes |  |  | Yes | No | -1 | 0 | 0 | 0 | [10 empty] | 476063.63 | 459702.16 | 0 | 0 | 16361.47 | PLANNING |  |  | 12/15/2014 0:00 | 12/30/2014 0:00 |  | DESIGN |  |  | 1/1/2015 0:00 | 1/15/2015 0:00 |  | BIDDING | [5 empty] | CONST |  |  | 1/22/2015 0:00 |  |  | WARRANTY | [10 empty] | 476063.63 | 486420.16 | 71816 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 4 | 65 | 35 | Information Technology | Engineering | Renovation | No | No | 12/12/2014 10:29 |  |  | No
Transportation and Mobility | P12126 | DOWNTOWN FORT LAUDERDALE MOBILITY HUB PROJECT | To provide management of the design and construction of streetscape improvements in the Downtown Fort Lauderdale Mobility Hub. The Downtown Fort Lauderdale Mobility Hub Project includes design and construction of physical improvements to achieve a high-quality user experience seamless mobility and mode transfer walkability and bike ability and to catalyze transit oriented development.The City is a sub-recipient of a grant from the Broward Metropolitan Planning Organization (BMPO) which expires end of 2020. |  |  |  |  | Kristin Thompson | TAM | TAM | 6 | Construction | 27 | Roadway Improvements | Yes |  |  | Yes | No | 0 | -1 | 0 | 0 | [10 empty] | 50000 | 28963.5 | 3437.5 | 0 | 17599 | PLANNING |  |  | 3/1/2017 0:00 | 12/11/2017 0:00 |  | DESIGN |  |  | 1/18/2018 0:00 | 6/5/2019 0:00 |  | BIDDING |  |  | 6/10/2019 0:00 | 9/12/2019 0:00 |  | CONST |  |  | 11/25/2019 0:00 | 9/30/2020 0:00 |  | WARRANTY |  |  | 10/1/2020 0:00 | 10/1/2021 0:00 | [6 empty] | 50000 | 35451.16 | 73083 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 8 | 24 | 34 | Public Works | Transportation | New Construction | No | No | 1/26/2015 15:15 |  |  | No
Public Works | P12144 | NCIP SUNRISE KEY NEIGHBORHOOD IMPROVEMENTS | This is a Neighborhood Community Investment Plan (NCIP) award to the Sunrise Key Neighborhood for installation of decorative street name sign posts | 687 | Alex Rio | 687 | Alex Rio | Irina Tokar | CM | PBS | 8 | Warranty | 1 | NCIP | No | CM | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [8 empty] | 47000 | 60000 | 60700 | 18069 | 3000 | 0 | 39631 | PLANNING | 9/18/2017 0:00 | 12/29/2017 0:00 | 9/18/2017 0:00 | 12/29/2017 0:00 |  | DESIGN | 2/20/2018 0:00 | 9/28/2018 0:00 | 8/19/2019 0:00 | 11/29/2019 0:00 |  | BIDDING | 10/1/2018 0:00 | 1/18/2019 0:00 | 9/15/2020 0:00 | 11/1/2021 0:00 |  | CONST | 1/21/2019 0:00 | 4/21/2019 0:00 | 11/1/2021 0:00 | 3/30/2023 0:00 |  | WARRANTY | 4/21/2019 0:00 | 4/21/2020 0:00 | 3/30/2023 0:00 | 3/30/2024 0:00 | [6 empty] | 60700 | 84607.25 | 70354 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 26 | 34 | City Manager's Office | NCIP | New Construction | No | No | 5/22/2015 8:18
City Manager | P12153 | BCIP NORTH BEACH VILLAGE BUSINESS ASSOCIATION AREA IMPROVEMENTS | Business Community Investment Plan (BCIP) North Beach Village Business Association. The project is for construction of two mid-century modern entranceway monuments in the North Beach Village area. The association is using volunteer points as their match and 22500 points have been deducted from their CVC/Volunteer Points account for this project. Total construction cost of project is not to exceed $22500 with the matching points of 22500. | [5 empty] | CM | CM | 2 | Design | 20 | BCIP | No | CM |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 22500 | 8650 | 0 | 0 | 13850 | PLANNING |  |  | 11/5/2018 0:00 | 4/5/2019 0:00 |  | DESIGN | 8/6/2018 0:00 | 9/28/2018 0:00 | 10/1/2020 0:00 | 6/1/2022 0:00 |  | BIDDING | 10/8/2018 0:00 | 12/17/2018 0:00 |  |  |  | CONST | 1/7/2019 0:00 | 4/17/2019 0:00 | 6/1/2022 0:00 | 12/30/2022 0:00 |  | WARRANTY | 4/17/2019 0:00 | 4/17/2020 0:00 | 9/1/2021 0:00 | 9/1/2022 0:00 | [6 empty] | 22500 | 36338.565 | 73181 | 1/26/2024 0:00 |  | STATUS | Yes | Yes | 84 | 27 | 34 | City Manager's Office | BCIP | New Construction | No | No | 5/22/2015 10:01
Public Works | P12169 | GEORGE T. LOHMEYER (GTL) ODOR CONTROL SYSTEM | This project is for the George T. Lohmeyer Wastewater Treatment Plant odor control system dewatering building study and upgrade. | 894 | Steve Hillberg |  |  | Steve Hillberg | PBS | PBS | 2 | Design | 23 | Utilities | No |  |  | Yes | No | 0 | 0 | 0 | -1 | [10 empty] | 5401626 | 183024.91 | 0 | 5218601.09 | 0 | PLANNING |  |  | 2/21/2017 0:00 | 8/31/2020 0:00 |  | DESIGN |  |  | 9/1/2020 0:00 | 3/30/2023 0:00 |  | BIDDING |  |  | 3/30/2023 0:00 | 8/1/2023 0:00 |  | CONST |  |  | 8/1/2023 0:00 | 2/1/2024 0:00 |  | WARRANTY |  |  | 2/1/2024 0:00 | 2/1/2025 0:00 | [6 empty] | 5401626 | 229296.41 | 73588 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 68 | Public Works | Utilities Engineering | Study/Investigation | No | No | 8/12/2015 13:47
Public Works | P12170 | GEORGE T. LOHMEYER CONCRETE RESTORATION | This project is to assess the concrete surfaces and structures at the GT Lohmeyer Waste Water Treatment Plant for failures. The work will create the bid specs for concrete repairs oversee the bid process and the construction inspection services. | 884 | Raymond Nazaire |  |  | Raymond Nazaire | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 451 | Yes | Yes | 0 | 0 | 0 | 0 | [9 empty] | 500000 | 596975 | 434578.92 | 94124.52 | 0 | 68271.56 | PLANNING | 12/17/2015 0:00 | 7/8/2016 0:00 | 10/1/2016 0:00 | 10/31/2016 0:00 |  | DESIGN | 7/8/2016 0:00 | 11/1/2016 0:00 | 11/1/2016 0:00 | 4/13/2017 0:00 |  | BIDDING | 3/2/2017 0:00 | 3/13/2017 0:00 | 1/6/2020 0:00 | 11/30/2021 0:00 |  | CONST | 3/13/2017 0:00 | 6/14/2017 0:00 | 2/1/2022 0:00 | 6/30/2023 0:00 |  | WARRANTY | 6/14/2017 0:00 | 6/14/2018 0:00 | 7/30/2023 0:00 | 7/30/2024 0:00 | [6 empty] | 596975 | 635236.42 | 71221 | 9/22/2023 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 8/12/2015 14:40 |  |  | No
Public Works | P12171 | BUTLER BUILDING UPGRADE AT GTL WELLFIELD | The Butler building is used for the Beach crew office staging area and storage of George T. Lohmeyer Water Treatment Plant equipment and maintenance items. The building is deteriorated and is exposed to the environment in places. The building needs to be assessed for upgrades or replacement to bring into compliance with the Miami/Dade specifications. | 885 | Connie Hayman | 687 | Alex Rio | Raymond Nazaire | PBS | PBS | 4 | Bidding | 37 | Water Sewer | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 3112526 | 367986.99 | 1196182.01 | 0 | 1548357 | PLANNING | 8/1/2018 0:00 | 11/1/2018 0:00 | 8/1/2018 0:00 | 11/1/2018 0:00 |  | DESIGN | 11/2/2018 0:00 | 5/2/2019 0:00 | 11/2/2018 0:00 | 5/10/2019 0:00 |  | BIDDING | 5/3/2019 0:00 | 10/3/2019 0:00 | 7/10/2023 0:00 | 5/20/2024 0:00 |  | CONST | 10/4/2019 0:00 | 4/5/2021 0:00 | 12/4/2023 0:00 | 5/21/2025 0:00 |  | WARRANTY | 4/6/2021 0:00 | 4/6/2022 0:00 | 5/22/2025 0:00 | 5/22/2026 0:00 | [6 empty] | 3112526 | 520793.31 | 73487 | 2/12/2024 0:00 |  | STATUS | No | No | 8 | 28 |  | Public Works | Facilities |  | No | No | 8/12/2015 15:04 |  |  | Yes
Public Works | P12176 | GTL MOTOR CONTROL CENTERS REHABILITATION | This project is for upgrades of various Motor Control Centers based on the Electrical Reliability Study. The study resulted in recommendations for the George T. Lohmeyer Wastewater Treatment Plant. The project is included in Water and Wastewater RFQ currently advertising a task order for design will be negotiated for design in FY 2024. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [6 empty] | 4951000 |  | 5000000 |  | 12659285 | 5757313.24 | 0 | 0 | 6901971.76 | PLANNING | 5/5/2016 0:00 | 2/28/2018 0:00 | 10/2/2023 0:00 | 12/31/2023 0:00 |  | DESIGN | 3/1/2018 0:00 | 11/16/2018 0:00 | 1/1/2024 0:00 | 4/1/2025 0:00 |  | BIDDING | 11/17/2018 0:00 | 3/30/2019 0:00 | 4/2/2025 0:00 | 9/2/2025 0:00 |  | CONST | 3/31/2019 0:00 | 3/30/2020 0:00 | 9/3/2025 0:00 | 9/3/2026 0:00 |  | WARRANTY | 3/31/2020 0:00 | 3/31/2021 0:00 | 9/4/2026 0:00 | 9/4/2027 0:00 |  |  | 4951000 |  |  |  | 12659285 | 6049608.58 | 73718 | 3/1/2024 0:00 |  | STATUS | Yes | Yes | 8 |  |  | Public Works |  |  | No | No | 8/13/2015 8:40 |  |  | No
Transportation and Mobility | P12183 | PARKING ADMINISTRATION AND CITY PARK GARAGE REPAIRS | The consulting firm DeRose Design Consultants Inc. was hired by the City in 2013 to perform a structural mechanical and electrical inspection of City properties. As a result of this study repairs at various properties under the Parking fund were identified. The funds requested for this project will be used for the structural mechanical and electrical improvements at the City Park Garage and the Parking Administration Building. | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 6 | Construction | 22 | CityFacilities | No |  | 461 | Yes | Yes | 0 | 0 | 0 | 0 | [10 empty] | 5169946 | 2407640.71 | 1777586.56 | 37500 | 947218.73 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 5169946 | 2407988.71 | 73508 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 8/13/2015 12:04 |  |  | Yes
Public Works | P12190 | UTILITIES ASSET MANAGEMENT SYSTEM | This project is for the purchase and implementation of a utilities asset management software with geographic information system (GIS) capabilities. | 942 | Craig Barrett |  |  | Christopher Bennett | PBS | PBS | 6 | Construction | 23 | Utilities | No |  | 470 | Yes | Yes | 0 | 0 | 0 | 0 | [10 empty] | 4617350 | 2259444.11 | 627425.06 | 0 | 1730480.83 | PLANNING |  |  | 10/1/2015 0:00 | 2/7/2017 0:00 |  | DESIGN | [5 empty] | BIDDING |  |  | 2/8/2017 0:00 | 2/28/2018 0:00 |  | CONST |  |  | 3/1/2018 0:00 | 1/20/2023 0:00 |  | WARRANTY | [10 empty] | 4617350 | 2272627.61 | 62739 | 7/25/2022 0:00 | 7/25/2022 0:00 | STATUS | Yes | Yes | 8 |  |  | Public Works |  |  | No | No | 8/14/2015 14:59 |  |  | No
Public Works | P12198 | CITY HALL FIRST FLOOR SECURITY | Renovation of City Hall's first floor lobby to enhance security flow of foot-traffic and interior aesthetics. The existing security desk will be demolished and relocated to improve security sight distances and to allow for proper cuing of visitors as they sign in and out per the new/updated security procedures. Additional updates to the lobby will include improved waiting area seating electronic message signs (TVs) and other miscellaneous aesthetic updates. | 865 | Khant Myat |  |  | Brandy Leighton | CM | PBS | 8 | Warranty | 22 | CityFacilities | No |  | 331 | Yes | Yes | 0 | 0 | 0 | 0 | [6 empty] | 133639 |  |  |  | 185000 | 183053.23 | 0 | 0 | 1946.77 | PLANNING |  |  | 4/7/2015 0:00 | 8/15/2015 0:00 |  | DESIGN |  |  | 8/16/2015 0:00 | 7/14/2016 0:00 |  | BIDDING |  |  | 8/5/2016 0:00 | 12/1/2016 0:00 |  | CONST |  |  | 12/2/2016 0:00 | 1/31/2017 0:00 |  | WARRANTY |  |  | 2/1/2017 0:00 | 2/1/2018 0:00 |  | 24963.98 | 133639 |  |  |  | 185000 | 220038.13 | 70355 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 28 | 37 | City Manager's Office | Facilities | Security Upgrades | No | No | 9/24/2015 14:31 |  |  | No
Public Works | P12243 | TAXIWAY FOXTROT RELOCATION | Demolition of the existing 3200 linear feet of taxiway pavement lights and guidance signs. Construction of new taxiway including grading subgrade limerock base course asphalt paving pavement striping new taxiway edgelights and guidance signs. The project will provide for the civil and electrical design for the relocation as well as survey and soils testing services. DBE compliance will also be required to comply with federal grant requirements during the design and construction phases. Design is anticipated to begin in mid-2017 with construction in the following year. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 8 | Warranty | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 3360474 | 2839370.39 | 0 | 0 | 521103.61 | PLANNING | 11/1/2016 0:00 | 5/22/2017 0:00 | 11/1/2016 0:00 | 5/22/2017 0:00 |  | DESIGN | 10/18/2018 0:00 | 3/26/2019 0:00 | 10/18/2018 0:00 | 3/26/2019 0:00 |  | BIDDING | 5/22/2019 0:00 | 11/5/2019 0:00 | 5/22/2019 0:00 | 11/5/2019 0:00 |  | CONST | 1/29/2020 0:00 | 7/14/2020 0:00 | 2/28/2020 0:00 | 10/8/2021 0:00 |  | WARRANTY | 8/7/2021 0:00 | 8/7/2021 0:00 | 10/8/2021 0:00 | 10/7/2022 0:00 | [6 empty] | 3360474 | 3016668.64 | 70356 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 36 | Transportation and Mobility | Airport | Replacement | No | No | 8/11/2016 12:50 |  |  | No
Public Works | P12259 | PUBLIC WORKS ADMINISTRATION BUILDING AIR CONDITION | There are five air conditioning units on the rooftop and two inside units at the Public Works Administration Building that need to be replaced. The five units are 100% fresh air which cause more extensive wear and tear as they are exposed to the elements and the two additional units are older and need replacement. The seven units have received extensive repairs with sheet metal and replacement of blower wheels and drain pans. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | PBS | PBS | 6 | Construction | 22 | CityFacilities | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [8 empty] | 1900000 | 1900000 | 2573250 | 2230292.13 | 163995.77 | 0 | 178962.1 | PLANNING |  |  | 12/1/2019 0:00 | 2/19/2020 0:00 |  | DESIGN |  |  | 2/24/2020 0:00 | 1/1/2021 0:00 |  | BIDDING |  |  | 1/2/2021 0:00 | 10/18/2021 0:00 |  | CONST |  |  | 5/1/2022 0:00 | 1/31/2024 0:00 |  | WARRANTY |  |  | 2/1/2024 0:00 | 2/1/2025 0:00 | [6 empty] | 2573250 | 2779785.36 | 73351 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | 8 | 28 | 36 | Public Works | Facilities | Replacement | No | No | 8/16/2016 11:42 |  |  | No
Public Works | P12261 | FXE DOWNTOWN HELISTOP ELEVATOR IMPROVEMENTS | This project is for repairs and improvements of the existing elevator that services the downtown Helistop to extend its useful operations life and correct any issues associated with the operation of the elevator. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 8 | Warranty | 3 | Airport | No |  | 468 | Yes | Yes | 0 | -1 | 0 | -1 | [10 empty] | 237912 | 222510.42 | 0 | 0 | 15401.58 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | 3/14/2017 0:00 | 8/22/2017 0:00 | 3/14/2017 0:00 | 8/22/2017 0:00 |  | CONST | 1/5/2018 0:00 | 5/30/2018 0:00 | 2/24/2020 0:00 | 5/31/2022 0:00 |  | WARRANTY | 5/30/2018 0:00 | 5/29/2019 0:00 | 6/1/2022 0:00 | 6/1/2023 0:00 | [6 empty] | 237912 | 272709.92 | 69914 | 6/30/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 36 | Transportation and Mobility | Airport | Replacement | No | No | 8/16/2016 13:26 |  |  | No
Public Works | P12264 | CITYWIDE CANAL DREDGING PLAN - CYCLE 1 | This project includes the dredging of various canals throughout the City in order to provide proper flow of stormwater from drainage canals and channels. The work also includes the navigation of vessels and conveyance of stormwater in navigable canals. The scope of the project requires dredging the bottom canal channel to a maximum of five feet below average low water elevation. This will be done in order to comply with the Cityâ€™s canal dredging criteria and ensure all stormwater outfalls are clear. The funds in this project will be used to make up the shortfall in the Osceola Creek Restoration Project (P12743) if needed after the construction bids are received in May 2023. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 11 | Hold | 31 | Canals | No |  | 470 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 1530239 | 279555.12 | 6197.38 | 0 | 1244486.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1530239 | 418241.4025 | 72015 | 11/3/2023 0:00 | 11/3/2023 0:00 | STATUS | Yes | Yes | 8 | 65 | 35 | Public Works | Engineering | Renovation | Yes | No | 8/16/2016 13:37 |  |  | No
Public Works | P12267 | DSD BUILDING - COOLING SYSTEM REPLACEMENT | Replace the heating ventilations and air conditioning (HVAC) system at the Department of Sustainable Development as follows; Replace four (4) cooling units on roof. Replace indoor air-handling unit. The project shall include modifications and cleaning of existing duct system and replacement of some ductsenergy efficiency improvements test and balance; and temporary replacement of 2 outdoor units. | 1156 | Danica Grujicic |  |  | Irina Tokar | DSD | PBS | 8 | Warranty | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 1081510 | 1079441.11 | 0 | 0 | 2068.89 | PLANNING | 12/1/2016 0:00 | 2/28/2017 0:00 | 12/1/2016 0:00 | 2/28/2017 0:00 |  | DESIGN | 9/16/2017 0:00 | 7/24/2017 0:00 | 3/1/2017 0:00 | 7/24/2017 0:00 |  | BIDDING | 8/11/2017 0:00 | 1/15/2017 0:00 | 8/11/2017 0:00 | 1/1/2018 0:00 |  | CONST | 1/8/2018 0:00 | 10/1/2018 0:00 | 1/8/2018 0:00 | 4/29/2019 0:00 |  | WARRANTY | 10/2/2018 0:00 | 10/2/2019 0:00 | 4/30/2019 0:00 | 4/30/2023 0:00 | [6 empty] | 1081510 | 1319745.01 | 70357 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 2 | 92 | 36 | Dept. of Sustainable Development | Building Services | Replacement | No | No | 9/9/2016 14:50
Public Works | P12285 | TWIN LAKES NORTH ANNEXATION IMPROVEMENTS | This project consists of the design and construction of traffic calming measures and other elements to improve the safety of pedestrians in the Twin Lakes North Neighborhood. The proposed improvements are the following: four (4) access treatments to indicate to drivers that they are entering a neighborhood one (1) traffic circle located at the intersection between 10th Avenue and 47th Street to force vehicular traffic to slow down and seven (7) pinch points within the neighborhood to require the drivers to slow down through the area. | 757 | Jean Examond |  |  | Raymond Nazaire | TAM | PBS | 8 | Warranty | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 383710 | 368869.11 | 0 | 0 | 14840.89 | PLANNING | 10/31/2016 0:00 | 4/20/2017 0:00 | 10/31/2016 0:00 | 4/20/2017 0:00 |  | DESIGN | 4/21/2017 0:00 | 9/30/2018 0:00 | 3/26/2019 0:00 | 6/21/2019 0:00 |  | BIDDING | 1/15/2018 0:00 | 11/30/2018 0:00 | 10/1/2019 0:00 | 1/31/2020 0:00 |  | CONST | 3/19/2018 0:00 | 5/30/2019 0:00 | 5/18/2020 0:00 | 11/30/2020 0:00 |  | WARRANTY | 8/2/2018 0:00 | 5/29/2020 0:00 | 12/1/2020 0:00 | 12/1/2021 0:00 |  | 57620 |  |  |  |  | 383710 | 568829.765 | 70358 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 34 | Transportation and Mobility | Transportation | New Construction | No | No | 12/16/2016 12:24
Public Works | P12289 | EXECUTIVE AIRPORT PARKING LOT | Planning design and construction of an approximately 300 space parking lot at Fort Lauderdale Executive Airport. The construction will take place on a 6 acre vacant property located north of Commercial Blvd and NW 21st Avenue. The project will include site clearing earthwork paving landscaping concrete perimeter wall and security cameras. | 689 | Fernando Blanco |  |  | Jill Prizlee | CM | PBS | 15 | Complete | 3 | Airport | No | CM | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 265980.26 | 265725 | 0 | 0 | 255.26 | PLANNING | 1/23/2017 0:00 | 4/19/2017 0:00 | 1/23/2017 0:00 | 4/19/2017 0:00 |  | DESIGN | 6/19/2017 0:00 | 8/23/2018 0:00 | 6/19/2017 0:00 | 8/23/2018 0:00 |  | BIDDING | 9/17/2018 0:00 | 1/10/2019 0:00 | 9/17/2018 0:00 | 1/10/2019 0:00 |  | CONST | 2/8/2019 0:00 | 6/13/2019 0:00 | 2/8/2019 0:00 | 6/13/2019 0:00 |  | WARRANTY | 6/14/2019 0:00 | 6/14/2020 0:00 | 6/14/2019 0:00 | 6/14/2020 0:00 | [6 empty] | 265980.26 | 332973.805 | 68333 | 1/22/2024 0:00 | 1/22/2024 0:00 | STATUS | Yes | Yes | 10 | 9 | 34 | Transportation and Mobility | Airport | New Construction | No | No | 1/27/2017 11:10 |  |  | No
Public Works | P12299 | WEST LAKE DRIVE BRIDGE RESTORATION | Bridge Rehabilitation - This 28.9 ft. long single span prestressed concrete slab bridge was constructed in 1964. The bridge has a roadway width of 27.9 ft. and carries two lanes of traffic on an urban collector roadway in a residential neighborhood. There are 4.5 ft. wide sidewalks on each side. The bridge has significant deterioration to the beams bents caps and abutments which has signficant reduce the bearing capacity of the bridge. The Cityâ€™s contracted structural engineering consultant will develop a task order to design permit and provide construction management services for the repairs of structural and aesthetic elements of the bridge. | 885 | Connie Hayman | 885 | Connie Hayman | Raymond Nazaire | PBS | PBS | 8 | Warranty | 19 | Bridge | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 1218444 | 1190875.9 | 22908.6 | 0 | 4659.5 | PLANNING | 8/1/2017 0:00 | 12/31/2017 0:00 | 8/1/2017 0:00 | 2/7/2020 0:00 |  | DESIGN | 4/10/2018 0:00 | 8/8/2018 0:00 | 2/9/2020 0:00 | 3/21/2022 0:00 |  | BIDDING |  |  | 3/21/2022 0:00 | 3/21/2022 0:00 |  | CONST |  |  | 4/4/2022 0:00 | 11/18/2022 0:00 |  | WARRANTY |  |  | 11/19/2022 0:00 | 11/19/2023 0:00 | [6 empty] | 1218444 | 1322262.72 | 70335 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 43 | Public Works | Bridges | Rehabilitation | No | No | 4/4/2017 10:12 |  |  | No
Parks and Rec | P12308 | PILE REPLACEMENT WITHIN THE NEW RIVER | The task order is for the replacement of timber piling at various marina location throughout the New River and includes timber pile replacement installation of pile wraps and caps. This task order is for work at the following locations along the New River; 4TH Ave East to Railroad Bridge Railroad Bridge East to Andrews Ave Andrews Ave East to 3rd Ave 3rd Ave Easst to U.S.I Andrews Ave East to 3rd Ave 3rd Ave East to U.S. 1. The work shall be completed within 45 days after the Notice to Proceed. | 1231 | Jonathan Luscomb |  |  | Enrique Sanchez | PKR | PKR | 2 | Design | 37 | Water Sewer | No | PBS |  | No | No | 0 | -1 | 0 | -1 | [10 empty] | 63513 | 1566 | 0 | 0 | 61947 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  | 7/10/2021 0:00 | 7/31/2022 0:00 |  | WARRANTY |  |  | 7/31/2022 0:00 | 7/31/2023 0:00 | [6 empty] | 63513 | 3132 | 73134 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 38 | Public Works | Utilities Engineering | General Upgrades | No | No | 5/17/2017 11:26
Transportation and Mobility | P12318 | NE 4TH STREET IMPROVEMENTS | This project includes improvements to pedestrian bicycle users and parking areas on NE 4th Street from US 1 to NE 3rd Avenue. Redesign of the street will include improvements aimed at making it safer for pedestrians and bicyclists to traverse the corridor. Improvements may include lighting landscaping signage Americans with Disabilities (ADA) upgrades parking and other pedestrian and bicycle amenities. | 1210 | Karen Warfel |  |  | Karen Warfel | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 249300 | 215810.13 | 30091.93 | 0 | 3397.94 | PLANNING |  |  | 1/1/2018 0:00 | 10/1/2018 0:00 |  | DESIGN |  |  | 11/1/2019 0:00 | 12/31/2020 0:00 |  | BIDDING |  |  | 1/4/2021 0:00 | 3/31/2021 0:00 |  | CONST |  |  | 4/1/2021 0:00 | 2/28/2022 0:00 |  | WARRANTY |  |  | 2/28/2022 0:00 | 2/28/2023 0:00 | [6 empty] | 249300 | 246878.91 | 73010 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | [6 empty] | No | No | 6/16/2017 9:45
Transportation and Mobility | P12326 | SHADY BANKS ENTRYWAY | Project funding will be used to implement the vision of the Shady Banks Neighborhood through their Neighborhood Mobility Master Plan. The priority item for the neighborhood was to address the speed of vehicles entering their neighborhood as well as the volume of cut through traffic. The scope includes narrowing the entryway at Davie Boulevard and SW 17th Avenue including reducing the high speed right turn lane installing a neckdown on SW 17th Avenue at the approach to SW 12th Court install a raised intersection at SW 12th Ct and SW 17th Avenue and using patterned asphalt to demarcate the entryway into the neighborhood. | 884 | Raymond Nazaire |  |  | Raymond Nazaire | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 100000 | 19057 | 0 | 0 | 80943 | PLANNING |  |  | 4/19/2021 0:00 | 8/2/2021 0:00 |  | DESIGN |  |  | 8/2/2021 0:00 | 4/29/2022 0:00 |  | BIDDING |  |  | 5/2/2022 0:00 | 6/30/2022 0:00 |  | CONST |  |  | 7/1/2022 0:00 | 9/30/2022 0:00 |  | WARRANTY |  |  | 9/30/2022 0:00 | 9/30/2023 0:00 | [6 empty] | 100000 | 35785.78 | 73084 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 8/23/2017 13:24 |  |  | No
Public Works | P12328 | EMERGENCY MEDICAL SUB-STATION #88 | To construct an Emergency Medical Sub-Station located on/about Federal Highway south of Broward Boulevard to address the need for additional Emergency Medical Services to the downtown district and the areas along south Federal Highway. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | FIR | PBS | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 6157763 | 1178105.09 | 0 | 3800000 | 1179657.91 | PLANNING | 2/1/2021 0:00 | 8/1/2021 0:00 | 2/1/2021 0:00 | 3/1/2024 0:00 |  | DESIGN | 8/2/2021 0:00 | 12/4/2022 0:00 | 3/4/2024 0:00 | 9/4/2024 0:00 |  | BIDDING | 12/5/2022 0:00 | 3/5/2023 0:00 | 9/5/2024 0:00 | 1/6/2025 0:00 |  | CONST | 12/5/2022 0:00 | 5/5/2024 0:00 | 1/7/2025 0:00 | 12/31/2025 0:00 |  | WARRANTY |  |  | 1/1/2026 0:00 | 1/1/2027 0:00 | [6 empty] | 6157763 | 1202894.99 | 73349 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | 8 | 28 | 34 | Public Works | Facilities | New Construction | No | No | 9/19/2017 7:36 |  |  | No
Public Works | P12337 | CORDOVA ROAD SEAWALL REPAIR / REPLACEMENT | This project will repair/replace a 2200 linear feet portion of a seawall along Cordova Road between SE 7th Street and SE 12th Street. The wall cap has areas of spalls coral rock seals have failed creating voids there are spalls with exposed rebar and cracks with staining. There is visible distress to the soil behind the wall. The wall is currently over topping. This project will fund the design permitting and construction to repair/replace a portion of the existing seawall. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 33 | Seawalls | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 6018841 | 5887268.07 | 21814.3 | 0 | 109758.63 | PLANNING |  |  | 2/24/2014 0:00 | 9/4/2018 0:00 |  | DESIGN |  |  | 9/5/2018 0:00 | 5/30/2019 0:00 |  | BIDDING |  |  | 5/30/2019 0:00 | 9/30/2019 0:00 |  | CONST |  |  | 9/30/2019 0:00 | 8/31/2021 0:00 |  | WARRANTY |  |  | 9/1/2021 0:00 | 9/1/2022 0:00 | [6 empty] | 6018841 | 6086355.705 | 73755 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 16 | 36 | Public Works | Marine Facilities | Replacement | No | No | 9/19/2017 9:16
Public Works | P12355 | AIRPORT DRAINAGE IMPROVEMENTS PHASE-I | This project is to construct drainage improvements adjacent to airport parcels 9 32 and 33 and will serve as Phase-I of a multiphase master drainage program. The improvement includes earthwork piping swale and basing installation. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 2205690 | 954386.3 | 0 | 0 | 1251303.7 | PLANNING |  |  | 3/10/2021 0:00 | 4/1/2021 0:00 |  | DESIGN |  |  | 4/2/2021 0:00 | 1/21/2022 0:00 |  | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2205690 | 1007769.42 | 71236 | 9/22/2023 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 9/19/2017 15:09 |  |  | No
City Manager | P12356 | AVIATION EQUIPMENT & SERVICE FACILITY EXPANSION | This project is for the expansion of the Fort Lauderdale Executive Airport Aviation Equipment and Service (AES)facility. This expansion will include additional ramp space the construction of two additional bays and theconstruction of a covered walk-way between the AES and the airport's Administration Building. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 2 | Design | 3 | Airport | No | CM | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 3930500 | 542844.32 | 99864.5 | 0 | 3287791.18 | PLANNING | 10/2/2017 0:00 | 1/12/2018 0:00 | 10/2/2017 0:00 | 1/12/2018 0:00 |  | DESIGN | 1/17/2018 0:00 | 2/15/2019 0:00 | 1/17/2018 0:00 | 5/26/2023 0:00 |  | BIDDING | 3/18/2019 0:00 | 7/5/2019 0:00 | 6/1/2023 0:00 | 9/1/2023 0:00 |  | CONST | 8/5/2019 0:00 | 1/3/2020 0:00 | 9/4/2023 0:00 | 3/1/2024 0:00 |  | WARRANTY | 1/4/2020 0:00 | 1/4/2021 0:00 | 3/2/2024 0:00 | 3/2/2025 0:00 | [6 empty] | 3930500 | 765031.015 | 71263 | 9/25/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 35 | City Manager's Office | Airport | Renovation | No | No | 9/20/2017 7:33 |  |  | No
Public Works | P12358 | FXE AIRFIELD SIGNAGE REPLACEMENT | This project is for the design and construction for the replacement of the airports existing quartz lit airfield guidance signs with new light emitting diode (LED) guidance signs. The new LED signs will be more efficient longer lasting and help reduce maintenance costs. The project is partially funded by a grant from the Florida Department of Transportation for 80% reimbursement of eligible project costs. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 8 | Warranty | 3 | Airport | No |  | 468 | Yes | Yes | 0 | 0 | 0 | 0 |  | 901087 | [8 empty] | 404750 | 377725.38 | 0 | 0 | 27024.62 | PLANNING | 8/20/2018 0:00 | 9/17/2018 0:00 | 8/20/2018 0:00 | 9/17/2018 0:00 |  | DESIGN | 10/2/2018 0:00 | 12/28/2018 0:00 | 10/2/2018 0:00 | 2/5/2020 0:00 |  | BIDDING | 1/14/2019 0:00 | 5/3/2019 0:00 | 2/6/2020 0:00 | 6/3/2020 0:00 |  | CONST | 6/3/2019 0:00 | 7/26/2019 0:00 | 6/4/2020 0:00 | 1/28/2022 0:00 |  | WARRANTY | 7/27/2019 0:00 | 7/27/2020 0:00 | 1/29/2022 0:00 | 1/29/2023 0:00 | [6 empty] | 404750 | 529232.88 | 69793 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 9/20/2017 7:39 |  |  | No
Public Works | P12369 | RIVERWALK FLOATING DOCK DESIGN & PERMITTING PHASE 1 & 2 | This project is for the design and permitting phase to place an additional floating dock along the New River near Esplanade Park. The Florida Inland Navigation District awarded a grant to the City for this project in October 2017 of $65000. The City Match will be provided by the Grants Genera Fund FD001-9129.Phase II involves the manufacturing and installation of the dock with access gangways as designed on Phase I | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PKR | PBS | 6 | Construction | 12 | Parks | Yes |  | 129 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 65000 | 63488.27 | 0 | 0 | 1511.73 | PLANNING | 9/15/2018 0:00 | 10/15/2018 0:00 | 9/15/2018 0:00 | 10/15/2018 0:00 |  | DESIGN | 10/15/2018 0:00 | 5/15/2019 0:00 | 10/15/2018 0:00 | 4/1/2022 0:00 |  | BIDDING | 5/15/2019 0:00 | 9/15/2019 0:00 | 4/1/2022 0:00 | 4/6/2023 0:00 |  | CONST | 9/15/2019 0:00 | 2/15/2020 0:00 | 4/7/2023 0:00 | 3/29/2024 0:00 |  | WARRANTY | 2/15/2020 0:00 | 3/15/2021 0:00 | 3/29/2024 0:00 | 3/28/2025 0:00 | [6 empty] | 65000 | 137770.065 | 73772 | 3/5/2024 0:00 |  | STATUS | Yes | Yes | 6 | 16 | 34 | Parks and Recreation | Marine Facilities | New Construction | No | No | 11/1/2017 15:37 |  |  | Yes
Public Works | P12370 | BILL KEITH PRESERVE SHORELINE STABILIZATION DESIGN AND PERMITTING | This project is for the design and permitting phase to create shoreline stabilization for the Bill Keith Preserve. The Florida Inland Navigation District awarded a grant to the City for this project in October 2017 of $60000. The City Match will be provided by the Grants Genera Fund FD001-9129. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | PKR | PBS | 6 | Construction | 12 | Parks | Yes |  | 129 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 60000 | 58488.89 | 0 | 0 | 1511.11 | PLANNING | 9/15/2018 0:00 | 10/15/2018 0:00 | 9/15/2018 0:00 | 10/15/2018 0:00 |  | DESIGN | 10/15/2018 0:00 | 5/15/2019 0:00 | 7/17/2019 0:00 | 7/31/2022 0:00 |  | BIDDING | 5/15/2019 0:00 | 9/15/2019 0:00 | 7/1/2022 0:00 | 9/1/2023 0:00 |  | CONST | 9/15/2019 0:00 | 2/15/2020 0:00 | 11/28/2023 0:00 | 7/25/2024 0:00 |  | WARRANTY | 2/15/2020 0:00 | 2/15/2021 0:00 | 7/26/2024 0:00 | 7/26/2025 0:00 | [6 empty] | 60000 | 126982.24 | 73778 | 3/5/2024 0:00 |  | STATUS | Yes | Yes | 6 | 16 | 34 | Parks and Recreation | Marine Facilities | New Construction | No | No | 11/1/2017 15:40 |  |  | No
Transportation and Mobility | P12377 | TARPON RIVER TRAFFIC CALMING IMPROVEMENTS | Project funding will implement the highest priorities out of the Tarpon River Mobility Masterplan. The neighborhoodâ€™s priority was to address pedestrian connectivity and safety. Primary improvements include the installation of new sidewalks and any leftover funds will go towards mobility masterplan improvements prioritized by the neighborhood. The priority is to begin with SW 9th Avenue and SW 7th Street. | 1318 | Mackendy Philippi |  |  |  | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 106000 | 104609.68 | 0 | 0 | 1390.32 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 106000 | 108678.72 | 73062 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 34 | Transportation and Mobility | Transportation | New Construction | No | No | 12/4/2017 13:04 |  |  | No
Public Works | P12383 | NE 25TH AVE 24 FORCE MAIN REPLACEMENT | This project is for the construction costs of the replacement of a deteriorated 24-inch diameter ductile iron pipe sewer force main measuring approximately 5500 linear feet. The force main is located along NE 25th Avenue from Commercial Boulevard to Oakland Park Boulevard. | 1183 | Cyrill Garcia |  |  | William Power | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 496 | Yes | Yes | -1 | 0 | 0 | 0 | [6 empty] | 10688500 |  |  |  | 19832533 | 560215.24 | 11642160.99 | 0 | 7630156.77 | PLANNING | 5/1/2019 0:00 | 9/1/2020 0:00 | 5/1/2019 0:00 | 1/13/2023 0:00 |  | DESIGN | 9/1/2019 0:00 | 3/1/2021 0:00 | 10/18/2023 0:00 | 7/11/2025 0:00 |  | BIDDING | 11/1/2019 0:00 | 7/1/2021 0:00 | 1/16/2023 0:00 | 10/17/2023 0:00 |  | CONST | 7/1/2020 0:00 | 9/30/2026 0:00 | 12/11/2023 0:00 | 3/23/2025 0:00 |  | WARRANTY | 10/1/2026 0:00 | 9/30/2027 0:00 | 3/24/2025 0:00 | 3/24/2026 0:00 |  |  | 10688500 |  |  |  | 19832533 | 787980.61 | 73766 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | Yes |  | 1/22/2018 16:09 |  |  | No
Public Works | P12384 | NE 38TH ST 42 INCH FM AND NE 19TH AVE 24 INCH FM REPLACEMENTS | The first part of this project will consist of replacing approximately 8000 linear feet of deteriorated 42-inch diameter sewer force main along NE 38th Street between N Dixie Highway and Coral Ridge Club. In addition approximately 3000 linear feet of 24-inch new sewer force main will be installed along NE 19th Avenue between NE 38th Street and NE 32nd Street. On October 24 2019 FDEP approved the request to modify this project by installing 2500 linear feet of 24-inch new sewer force main along NE 50th Court in lieu of the 3000 feet of 24-inch new sewer force main along NE 19th Avenue. | 1183 | Cyrill Garcia |  |  | William Power | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 496 | Yes | Yes | -1 | 0 | 0 | 0 | [6 empty] | 27909300 |  |  |  | 31189144 | 694875.01 | 29803525.23 | 0 | 690743.76 | PLANNING | 5/1/2019 0:00 | 9/1/2020 0:00 | 10/16/2018 0:00 | 1/15/2023 0:00 |  | DESIGN | 9/1/2019 0:00 | 3/1/2021 0:00 | 10/19/2023 0:00 | 10/31/2025 0:00 |  | BIDDING | 11/1/2019 0:00 | 7/1/2021 0:00 | 1/16/2023 0:00 | 10/18/2023 0:00 |  | CONST | 7/1/2020 0:00 | 9/30/2026 0:00 | 12/11/2023 0:00 | 10/1/2025 0:00 |  | WARRANTY | 10/1/2026 0:00 | 9/30/2027 0:00 | 10/2/2025 0:00 | 10/2/2026 0:00 |  |  | 27909300 |  |  |  | 31189144 | 923559.525 | 73767 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | Yes |  | 1/23/2018 13:13 |  |  | No
Public Works | P12387 | EFFLUENT PIPE 54 FORCE MAIN REPLACEMENT | This project is for the rehabilitation or replacement of a 54-inch pipe leading from George T. Lohmeyer Wastewater Treatment Plant (GTL) to the injection wells. The effluent pipeline is a single point of failure within the wastewater system. While it has roughly 18 years of useful life remaining it is Pre-stressed Concrete Cylinder Pipe (PCCP) that has been known to cause issues. This project also includes inspection survey or testing of the existing pipe development of redundancy options and related work. | 1380 | Gabrielle Bork |  |  | William Power | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 496 | Yes | Yes | 0 | 0 | 0 | -1 | [6 empty] | 45967219 |  |  |  | 53347080 | 679358.64 | 47970458.47 | 0 | 4697262.89 | PLANNING | 5/1/2019 0:00 | 9/1/2020 0:00 | 2/1/2019 0:00 | 9/1/2022 0:00 |  | DESIGN | 9/1/2019 0:00 | 3/1/2021 0:00 | 9/2/2022 0:00 | 3/14/2023 0:00 |  | BIDDING | 11/1/2019 0:00 | 7/1/2021 0:00 | 3/15/2023 0:00 | 11/12/2023 0:00 |  | CONST | 7/21/2020 0:00 | 9/30/2026 0:00 | 11/13/2023 0:00 | 6/5/2026 0:00 |  | WARRANTY | 10/1/2026 0:00 | 9/30/2027 0:00 | 6/5/2026 0:00 | 6/5/2027 0:00 |  |  | 45967219 |  |  |  | 53347080 | 862409.12 | 73625 | 2/23/2024 0:00 | 2/23/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | Yes |  | 1/23/2018 13:32 |  |  | No
Public Works | P12388 | NE 13TH ST 24 FORCE MAIN REPLACEMENT | This project is for the replacement of a deteriorated 24-inch diameter sewer force main measuring approximately 3300 linear feet. The force main is located along NE 13th Street from State Road 845 to State Road 811. | 697 | Louis Lafaurie |  |  | Brandy Leighton | PBS | PBS | 8 | Warranty | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 3569607 | 3220531.71 | 0 | 0 | 349075.29 | PLANNING | 6/1/2018 0:00 | 9/28/2018 0:00 | 6/1/2018 0:00 | 7/27/2020 0:00 |  | DESIGN | 10/1/2018 0:00 | 4/30/2019 0:00 | 7/28/2020 0:00 | 1/12/2021 0:00 |  | BIDDING | 12/1/2018 0:00 | 8/30/2019 0:00 |  |  |  | CONST | 9/1/2019 0:00 | 3/1/2021 0:00 | 1/13/2021 0:00 | 10/22/2021 0:00 |  | WARRANTY | 3/2/2021 0:00 | 3/1/2022 0:00 | 8/24/2021 0:00 | 8/23/2022 0:00 | [6 empty] | 3569607 | 3579789.62 | 70337 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | Yes |  | 1/23/2018 13:40 |  |  | Yes
Public Works | P12389 | 18 INCH FM REPLACEMENT ACROSS THE N. RIVER FROM NE 9TH ST TO N. BIRCH ROAD | This project is for the replacement of a deteriorated 18-inch diameter sewer force main measuring approximately 1000 linear feet. The force main crosses the North New River from NE 9th Street to N Birch Road. | 1212 | Daniel Fisher |  |  | Scott Teschky | PBS | PBS | 15 | Complete | 37 | Water Sewer | No | CO | 495 | Yes | Yes | -1 | -1 | 0 | 0 | [10 empty] | 2238875.1 | 2232074.44 | 0 | 0 | 6800.66 | PLANNING | 6/15/2018 0:00 | 10/15/2018 0:00 | 6/15/2018 0:00 | 10/15/2018 0:00 |  | DESIGN | 10/16/2018 0:00 | 5/30/2019 0:00 | 10/16/2018 0:00 | 11/26/2019 0:00 |  | BIDDING | 12/16/2018 0:00 | 9/30/2019 0:00 | 11/27/2019 0:00 | 11/2/2020 0:00 |  | CONST | 10/1/2019 0:00 | 4/1/2021 0:00 | 11/2/2020 0:00 | 6/10/2021 0:00 |  | WARRANTY | 4/2/2021 0:00 | 4/1/2022 0:00 | 6/11/2021 0:00 | 6/11/2022 0:00 | [6 empty] | 2238875.1 | 2357528.44 | 70338 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | Yes |  | 1/23/2018 13:42
Public Works | P12393 | FIVEASH ELECTRICAL SYSTEM REPLACEMENTS (2015-2020) | Replace medium voltage fused service disconnect switches; Replace medium voltage MCC_5201 and MCC_5202; Replace PNL_5602 (LPHS-3); Replace XFMR5501 and XFMR 5502; Replace MCC_5504 and MCC_5503; Replace MCC_5311; add second feed; incorporate/eliminate MCC_5313; Replace/Convert MCC_5614 to 480V and dedicated to HYD_2103; Replace/Convert MCC_5615 to 480V and dedicate to HYD_2104; Replace SWBD5616; Replace XFMR 5612; Replace PNL 5630; Replace General Circuit Breaker Panel boards transformers and branch circuits; Replace Surface Wash Pump 1 starter; Replace 2 HSP starters with VFDs; Convert 240V motors to 480V and re-feed; Replace MSTR3202 (Backwash Pump 2) at the Fiveash Regional Water Treatment Plant. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 495 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 2991001.5 | 198643 | 99980 | 0 | 2692378.5 | PLANNING |  |  | 1/1/2021 0:00 | 3/31/2021 0:00 |  | DESIGN |  |  | 4/1/2021 0:00 | 12/31/2023 0:00 |  | BIDDING |  |  | 1/1/2024 0:00 | 10/31/2024 0:00 |  | CONST |  |  | 11/1/2024 0:00 | 11/1/2025 0:00 |  | WARRANTY |  |  | 11/3/2025 0:00 | 11/3/2026 0:00 | [6 empty] | 2991001.5 | 263086 | 73118 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No |  | 1/24/2018 9:30 |  |  | No
Public Works | P12396 | PEELE DIXIE SURGE PROTECTION UPGRADES | Replace/Retrofit existing panel boards with integral surge protective devices to external mounted units connected through a branch circuit breaker at the Peele Dixie Water Treatment Plant. | 894 | Steve Hillberg | 894 | Steve Hillberg | Steve Hillberg | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 495 | Yes | Yes | -1 | -1 | -1 | -1 | [8 empty] | 60000 | 100000 | 100000 | 33991.82 | 0 | 0 | 66008.18 | PLANNING |  |  | 10/1/2019 0:00 | 10/1/2020 0:00 |  | DESIGN |  |  | 10/1/2020 0:00 | 3/31/2021 0:00 |  | BIDDING |  |  | 4/1/2021 0:00 | 9/6/2021 0:00 |  | CONST |  |  | 9/6/2021 0:00 | 2/28/2023 0:00 |  | WARRANTY |  |  | 2/28/2023 0:00 | 2/28/2024 0:00 | [6 empty] | 100000 | 45065.32 | 73577 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No |  | 1/24/2018 10:11
Public Works | P12399 | FIVEASH WTP PCCP REPLACEMENT | Replace prestressed concrete cylinder pipe (PCCP) feeding the high service pumps at the Fiveash Regional Water Treatment Plant. | 1198 | Axel Rivera Martinez |  |  | Scott Teschky | PBS | PBS | 15 | Complete | 37 | Water Sewer | No | CO | 495 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 33511 | 30379 | 0 | 0 | 3132 | PLANNING |  | 9/30/2018 0:00 | 7/9/2019 0:00 | 6/30/2021 0:00 |  | DESIGN | 10/1/2018 0:00 | 5/9/2019 0:00 | 7/1/2021 0:00 | 4/27/2022 0:00 |  | BIDDING | 5/10/2019 0:00 | 11/5/2019 0:00 | 4/28/2022 0:00 | 10/25/2022 0:00 |  | CONST | 11/6/2019 0:00 | 1/28/2021 0:00 | 10/26/2022 0:00 | 10/26/2023 0:00 |  | WARRANTY | 1/29/2021 0:00 | 1/29/2022 0:00 | 10/27/2023 0:00 | 10/27/2024 0:00 | [6 empty] | 33511 | 70166.23 | 70339 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | No |  | 1/24/2018 10:23 |  |  | No
Public Works | P12400 | PROSPECT WELLFIELD ELECTRICAL STUDIES AND TESTING | Perform Short Circuit Device Coordination and Arc Flash Study Electrical Maintenance Testing and Generate Accurate As-Built One Line Drawings and plans of the entire wellfield. | 894 | Steve Hillberg | 934 | Herbert Stanley | Steve Roberts Jr. | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No | CO | 495 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 185000 | 1168 | 0 | 0 | 183832 | PLANNING |  |  | 10/26/2021 0:00 | 3/31/2023 0:00 |  | DESIGN |  |  | 3/31/2023 0:00 | 12/30/2023 0:00 |  | BIDDING |  |  | 12/30/2023 0:00 | 12/30/2023 0:00 |  | CONST |  |  | 12/30/2023 0:00 | 12/30/2023 0:00 |  | WARRANTY |  |  | 12/30/2023 0:00 | 12/30/2024 0:00 | [6 empty] | 185000 | 2336 | 73578 | 2/16/2024 0:00 |  | STATUS | Yes | No | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No |  | 1/24/2018 10:27
Public Works | P12401 | PROSPECT WELLFIELD BONDING & GROUNDING TESTING & LIGHTING PROTECTION | Perform Bonding and Grounding survey and testing and add lightning protection to generator buildings to the Prospect Wellfield. | 894 | Steve Hillberg |  |  | Steve Hillberg | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No | CO | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 99000 | 1784 | 0 | 0 | 97216 | PLANNING |  |  | 11/15/2019 0:00 | 3/31/2023 0:00 |  | DESIGN |  |  | 3/31/2023 0:00 | 12/30/2023 0:00 |  | BIDDING |  |  | 12/30/2023 0:00 | 12/30/2023 0:00 |  | CONST |  |  | 12/30/2023 0:00 | 12/30/2023 0:00 |  | WARRANTY |  |  | 12/30/2023 0:00 | 12/30/2024 0:00 | [6 empty] | 99000 | 3567.5 | 73579 | 2/16/2024 0:00 |  | STATUS | Yes | No | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No |  | 1/24/2018 10:32
Public Works | P12403 | PEELE-DIXIE WTP CHEMICAL STORAGE IMPROVEMENTS | At the Peele Dixie Water Treatment Plant the anti-scalant and corrosion inhibitor bulk chemical tanks do not allow for a full load delivery of chemicals. This project is to investigate the addition of another tank and /or the replacement with multiple smaller tanks. Additionally the day tanks for the sodium hydroxide and sulfuric acid do not hold enough chemical to last a whole day and additional storage is required. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 750000 | 25400 | 429870 | 0 | 294730 | PLANNING |  |  | 4/3/2023 0:00 | 6/30/2023 0:00 |  | DESIGN |  |  | 7/3/2023 0:00 | 12/29/2023 0:00 |  | BIDDING |  |  | 1/1/2024 0:00 | 6/28/2024 0:00 |  | CONST |  |  | 7/1/2024 0:00 | 12/27/2024 0:00 |  | WARRANTY |  |  | 12/27/2024 0:00 | 12/27/2025 0:00 | [6 empty] | 750000 | 46491.14 | 73719 | 3/1/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No |  | 1/24/2018 10:41 |  | No | No
Public Works | P12408 | FORCE MAIN (FROM PUMP STATION A-54 TO A-10) UPSIZE -REDUNDANCY | Install approximately 1900 linear feet of 30-inch force main parallel to the existing 30-inch force main running from Pump Station A-54 to Pump Station A-10 starting at SW 4th Avenue running east along SW 19th Street to S Andrews Avenue. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 2 | Design | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 430254 | 56093 | 371206.03 | 0 | 2954.97 | PLANNING |  |  | 1/1/2023 0:00 | 8/31/2023 0:00 |  | DESIGN |  |  | 8/9/2023 0:00 | 5/24/2024 0:00 |  | BIDDING |  |  | 5/24/2024 0:00 | 9/30/2024 0:00 |  | CONST |  |  | 9/30/2024 0:00 | 5/30/2025 0:00 |  | WARRANTY |  |  | 5/31/2025 0:00 | 5/31/2026 0:00 | [6 empty] | 430254 | 134327.72 | 73691 | 2/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 34 | Public Works | Water Sewer | New Construction | No |  | 1/24/2018 10:49 |  |  | No
Public Works | P12410 | PUMP STATIONS C-1 AND C-2 REPLACEMENT | Replacement of Pump Stations C-1 and C-2. Upgrade the pumps at Pump Station C-1 with higher capacity models. Replace station piping valves and appurtenances and wet well as necessary. | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | 0 | -1 | 0 | [8 empty] | 660000 |  | 3373470 | 229729.9 | 40090 | 0 | 3103650.1 | PLANNING |  |  | 10/1/2023 0:00 | 12/15/2023 0:00 |  | DESIGN |  |  | 12/18/2023 0:00 | 4/13/2024 0:00 |  | BIDDING |  |  | 4/15/2024 0:00 | 8/30/2024 0:00 |  | CONST |  |  | 9/2/2024 0:00 | 2/28/2025 0:00 |  | WARRANTY |  |  | 3/1/2025 0:00 | 3/1/2026 0:00 | [6 empty] | 3373470 | 316968.9 | 73731 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | No |  | 1/24/2018 10:52 |  |  | No
Public Works | P12412 | PUMP STATION A-16 RELOCATION | This projects consists on the construction of a new Underground wastewater pump station (Relocation of (PS) A-16) to approximately 120 feet east on SE 11th Street. The new Pump Station location is based on meeting federal setbacks for the construction of the new Court House. The project will include the construction of an 18â€ PVC gravity sewer extension from the existing sanitary sewer manhole to the new Pump Station A- 16 location. Also a new 10â€ HDPE force main from the new PS A-16 to a connection point with the Cityâ€™s existing 36â€ force main. Additionally This project includes the construction of a 30â€ HDPE water main on SE 3rd Avenue and SE 9th Street to vacate the area near the proposed Federal Court House site. And finally the abandonment and decommissioning of the existing PS. | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | 0 | 0 | -1 |  | 2725570 |  |  |  |  | 2725570 |  |  |  | 5350000 | 4682818.43 | 525877.75 | 0 | 141303.82 | PLANNING |  |  | 10/29/2018 0:00 | 2/19/2019 0:00 |  | DESIGN |  |  | 2/20/2019 0:00 | 1/3/2022 0:00 |  | BIDDING |  |  | 1/3/2022 0:00 | 7/5/2022 0:00 |  | CONST |  |  | 4/17/2023 0:00 | 3/19/2024 0:00 |  | WARRANTY |  |  | 3/20/2024 0:00 | 3/19/2025 0:00 |  |  | 2725570 |  |  |  | 5350000 | 4873166.17 | 73735 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | No | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | No |  | 1/24/2018 11:03 |  |  | No
Public Works | P12414 | GRAVITY PIPE IMPROVEMENTS TO THE DOWNTOWN COLLECTION SYSTEM | Project includes the following: Upsize 920 feet of the existing 12-inch gravity pipe to a 15-inch gravity pipe along E Las Olas Boulevard from SE 1st Avenue to SE 4th Avenue; Upsize 750 feet of the existing 14-inch gravity pipe to 21-inch gravity pipe right by the pump station and along SE 2nd Street from SW 1st Avenue to SE 1st Avenue; Upsize 84 feet of the existing 14-inch gravity pipe to 24-inch gravity pipe right by the Pump Station A-7 along SW 2nd Street; Upsize 560 feet of the existing 15-inch gravity pipe to 18-inch gravity pipe right along SE 1st Avenue from East Las Olas Boulevard to SE 2nd Street. | 894 | Steve Hillberg |  |  | Steve Hillberg | PBS | PBS | 11 | Hold | 37 | Water Sewer | No | CO | 495 | Yes | Yes | 0 | 0 | 0 | -1 |  | 3100150 | [6 empty] | 2000000 | 2300000 | 3435370 | 193226.9 | 0 | 0 | 3242143.1 | PLANNING | 3/1/2018 0:00 | 6/22/2018 0:00 | 3/1/2018 0:00 | 6/22/2018 0:00 |  | DESIGN | 6/22/2018 0:00 | 10/5/2018 0:00 | 6/22/2018 0:00 | 1/10/2020 0:00 |  | BIDDING | 10/5/2018 0:00 | 11/30/2018 0:00 | 1/10/2020 0:00 | 6/28/2023 0:00 |  | CONST | 12/1/2018 0:00 | 4/30/2019 0:00 | 6/28/2023 0:00 | 3/28/2024 0:00 |  | WARRANTY | 5/1/2019 0:00 | 4/30/2020 0:00 | 3/28/2024 0:00 | 3/28/2025 0:00 | [6 empty] | 3435370 | 242557.9 | 73582 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No |  | 1/24/2018 11:06
Public Works | P12427 | NEW MID-BLOCK RAPID FLASHING BEACON NW 9TH AVE AND NW 2ND STREET | New Mid-Block Rapid Flashing Beacon at NW 9th Avenue and NW 2nd Street in Dorsey-Riverbend neighborhood.Â This crosswalk will connect students from Walker Elementary and the neighborhood on the west side of NW 9th Avenue to the Boys and Girls Club onÂ the east side of NW 9th Avenue at NW 2nd Street.Â The scope of the project includes the design survey of the intersection final design and construction of the crosswalk.Â The design includes the traffic signing and marking needed ADA ramps any drainage relocations due to conflicts sidewalk reconstruction at intersection to connect to crosswalk and new rapid-flashing beacon crosswalk signage with push buttons.Â | 1176 | _PROJECT MANAGER |  |  | Lisa Marie Glover | CRA | PBS | 2 | Design | 27 | Roadway Improvements | No |  | 347 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 140685 | 44309.69 | 0 | 0 | 96375.31 | PLANNING |  |  | 7/1/2020 0:00 | 1/2/2021 0:00 |  | DESIGN |  |  | 7/5/2021 0:00 | 3/31/2022 0:00 |  | BIDDING |  |  | 4/1/2022 0:00 | 5/31/2022 0:00 |  | CONST |  |  | 6/1/2022 0:00 | 8/31/2022 0:00 |  | WARRANTY |  |  | 8/31/2022 0:00 | 8/31/2023 0:00 | [6 empty] | 140685 | 85597.185 | 67622 | 2/23/2023 0:00 |  | STATUS | Yes | Yes | 8 | 72 | 34 | Public Works | CRA | New Construction | No |  | 4/6/2018 13:23 |  |  | No
Transportation and Mobility | P12434 | SW 2ND AVENUE MEDIAN PARKING | Construct angle pave parking in the street median to provide more public parking for the commercial area. | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 8 | Warranty | 17 | Parking | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | 20 |  | 0 |  |  | 0 |  |  |  |  | 434109.82 | 394703.57 | 0 | 0 | 39406.25 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [7 empty] | 0 | 0 | 20 | 434109.82 | 442756.355 | 72970 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 10 | 83 | 34 | Transportation and Mobility | Parking Systems | New Construction |  |  | 5/23/2018 14:57 |  |  | No
Transportation and Mobility | P12435 | BREAKERS AVENUE AND BIRCH ROAD IMPROVEMENTS | The Breakers Avenue project includes wider sidewalks street trees and landscape milling and paving street lighting and traffic calming between Riomar Street (north to the entrance of the Bonnet House Museum and Gardens) to Vistamar Street. The design will prioritize Breakers Avenue for the safe movement of the pedestrians supporting the character and destinations along the Avenue. | 1359 | Ben Rogers |  |  | Karen Warfel | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [9 empty] | 5000000 | 4132799 | 1101323.91 | 103412.83 | 0 | 2928062.26 | PLANNING |  |  | 6/28/2019 0:00 | 7/31/2020 0:00 |  | DESIGN |  |  | 8/3/2020 0:00 | 4/29/2022 0:00 |  | BIDDING |  |  | 5/2/2022 0:00 | 7/29/2022 0:00 |  | CONST |  |  | 8/1/2022 0:00 | 8/1/2023 0:00 |  | WARRANTY |  |  | 8/1/2023 0:00 | 8/1/2024 0:00 |  | 893589 |  |  |  |  | 4132799 | 1258806.685 | 73085 | 1/19/2024 0:00 |  | STATUS | No | Yes | 8 | 24 | 34 | Public Works | Transportation | New Construction |  | Yes | 5/30/2018 11:52 |  |  | No
Public Works | P12443 | SISTRUNK CROSSWALKS | Design and construct approximately 6 new crosswalks along Sistrunk Blvd between NW 24th Ave and Andrews Avenue including ADA ramps and striping of crosswalks. This project supports the safe mobility of all ages and abilities of pedestrian bicyclists and transit users within the heart of the NW neighborhood. This project is funded by the NW CRA. | 1151 | Brandy Leighton |  |  | Brandy Leighton | TAM | PBS | 2 | Design | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 525000 | 105338.47 | 0 | 0 | 419661.53 | PLANNING |  |  | 2/1/2024 0:00 | 6/28/2024 0:00 |  | DESIGN |  |  | 7/1/2024 0:00 | 3/31/2025 0:00 |  | BIDDING |  |  | 3/31/2025 0:00 | 5/31/2025 0:00 |  | CONST |  |  | 5/31/2025 0:00 | 11/30/2025 0:00 |  | WARRANTY |  |  | 11/30/2025 0:00 | 11/30/2026 0:00 | [6 empty] | 525000 | 139659.97 | 71867 | 10/25/2023 0:00 | 10/25/2023 0:00 | STATUS | Yes | Yes | 8 | 24 | 34 | Public Works | Transportation | New Construction | No | No | 7/24/2018 15:00 |  |  | No
Public Works | P12446 | PUBLIC WORKS JOINT FACILITY | This project consists of the design and construction of a new facility and parking lot at Plant A (1901 NW 6th Street/Sistrunk) to house the Meter Shop and Stormwater Operations Staff and vehicles. Work will include necessary site improvements to the existing roadway and fence-line. | 1220 | Ingrid Kindbom |  |  | Ingrid Kindbom | PBS | PBS | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  |  | Yes |  | 0 | 0 | -1 | 0 | [9 empty] | 5000000 | 1854216 | 156206.6 | 88029.24 | 0 | 1609980.16 | PLANNING |  |  | 9/26/2018 0:00 | 6/30/2024 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1854216 | 165035.78 | 73326 | 2/5/2024 0:00 | 2/5/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No | No | 7/27/2018 12:30 |  |  | No
Public Works | P12447 | ROADWAY REPAIR FACILITY | This project consists of the design and construction of a new facility for the new Roadway Repairs Crew and their vehicles. Work will include necessary site improvements including the construction of a fence line around the property. | 1293 | Gary Foster |  |  | Gary Foster | PBS | PBS | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  |  | Yes |  | -1 | 0 | 0 | 0 | [10 empty] | 35000 | 33892.5 | 0 | 0 | 1107.5 | PLANNING |  |  | 9/26/2018 0:00 | 2/29/2024 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 35000 | 34695.5 | 71235 | 9/22/2023 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No | No | 7/27/2018 12:31 |  |  | No
Parks and Rec | P12452 | FLORENCE C. HARDY PARK IMPROVEMENTS | This project will provide installation of new artificial turf on the multipurpose field at Florence C. Hardy Park and retrofitting the existing field lighting to new Light Emitting Diode (LED) technology. The city's Bermuda fields are not being sufficiently rested to maintain an adequate playing surface. The installation of an artificial turf will enhance the City's ability to meet the demands for the playing areas and allow for proper maintenance of the bermuda fields. With the high demand for field space and high cost of purchasing and developing land for athletic fields converting natural grass fields to artificial turf fields is an alternative that will increase the supply of fields space at a marginal cost. | 1320 | Marc Isaac |  |  | Thomas Green | PKR | PKR | 15 | Complete | 12 | Parks | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [8 empty] | 800000 | 800000 | 13918 | 13747 | 0 | 0 | 171 | PLANNING |  |  | 3/5/2020 0:00 | 11/27/2020 0:00 |  | DESIGN |  |  | 11/27/2020 0:00 | 5/31/2021 0:00 |  | BIDDING |  |  | 5/31/2021 0:00 | 7/30/2021 0:00 |  | CONST |  |  | 7/30/2021 0:00 | 4/25/2022 0:00 |  | WARRANTY |  |  | 4/25/2022 0:00 | 4/25/2023 0:00 | [6 empty] | 13918 | 27841 | 71822 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 19 | 43 | Parks and Recreation | Parks (Detailed) or (Generic) | Rehabilitation | No | No | 8/9/2018 13:26
City Manager | P12455 | TAXIWAY INTERSECTION IMPROVEMENTS | This project is to design and construct a new taxiway intersection in order to improve airfield operations. The project will involve demolition of the existing taxiways construction of new taxiways including paving new Light Emitting Mode (LED) lights and guidance signs pavement striping and sodding. The project is partially funded by a grant from the Florida Department of Transportation (FDOT) for approximately 80% reimbursement of eligible project costs and an airport match of 20%. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 6 | Construction | 3 | Airport | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [9 empty] | 1300000 | 960500 | 909247.7 | 0 | 0 | 51252.3 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING |  |  | 4/2/2021 0:00 | 7/30/2021 0:00 |  | CONST |  |  | 9/9/2021 0:00 | 12/30/2022 0:00 |  | WARRANTY |  |  | 12/31/2022 0:00 | 12/31/2023 0:00 | [6 empty] | 960500 | 980278.7 | 71856 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No | No | 8/9/2018 13:40 |  |  | No
Public Works | P12456 | SEWER BASIN D-40 REHAB | Hazen & Sawyer (Consultant) is the Consent Order Program Manager and is responsible for overall program management. This Project will require the Consultant to provide engineering services needed to deliver I/I Reduction in a portion of Sanitary Sewer basin D-40. The Consultant shall provide professional services including engineering analysis field investigation rehabilitation scope preparation and construction management in portions of these pump station areas. The Consultant will be an extension of the City Staff to oversee and report on the rehabilitation of their limits of construction. | 697 | Louis Lafaurie |  |  | Brandy Leighton | PBS | PBS | 2 | Design | 23 | Utilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 169237 | 65030.51 | 28.75 | 103775 | 402.74 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  | 11/1/2022 0:00 | 6/29/2024 0:00 |  | WARRANTY |  |  | 6/30/2024 0:00 | 7/29/2025 0:00 | [6 empty] | 169237 | 110356.16 | 73665 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No | No | 8/9/2018 13:44 |  |  | No
City Manager | P12459 | EXECUTIVE AIRPORT PARCEL 21B NRA MITIGATION & MAINTENANCE | This project is for the mitigation and enhancement of a portion Parcel 21B Natural Resource Area (NRA) as established by the conservation easement approved by Broward County Environmental Protection and Growth Management Department (BCEPGMD). The project includes removal of non-native and/or exotic nuisance species/vegetation new native planting and providing maintenance services for a three (3) year period following acceptance of project by BCEPGMD. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 8 | Warranty | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [9 empty] | 1200000 | 514652 | 480481.54 | 34170 | 0 | 0.46 | PLANNING | [5 empty] | DESIGN |  |  | 1/8/2018 0:00 | 9/14/2018 0:00 |  | BIDDING |  |  | 9/17/2018 0:00 | 5/26/2020 0:00 |  | CONST |  |  | 5/27/2020 0:00 | 6/27/2021 0:00 |  | WARRANTY |  |  | 6/28/2021 0:00 | 6/29/2021 0:00 | [6 empty] | 514652 | 519947.24 | 71857 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 43 | Transportation and Mobility | Airport | Rehabilitation | No | No | 8/22/2018 15:29 |  |  | No
Public Works | P12461 | MILLS POND PARK ARTIFICIAL TURF | This project will provide installation of new artificial turf on the three multi -purpose fields at Mills Pond Park as well as retrofitting the existing field lighting to new Light-Emitting Diode (LED) technology. The city's Bermuda fields are not being sufficiently rested to maintain an adequate playing surface. The installation of an artificial turf will enhance the City's ability to meet the demands for the playing areas and allow for proper maintenance of the Bermuda fields. With the high demand for field space and high cost of purchasing and developing land for athletic fields converting natural grass fields to artificial turf fields is an alternative that will increase the supply of fields space at a marginal cost. | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PKR | PBS | 8 | Warranty | 12 | Parks | No |  | 331 | Yes | Yes | 0 | 0 | -1 | 0 | [8 empty] | 2500000 | 2900000 | 3171264.26 | 3015671.69 | 0 | 0 | 155592.57 | PLANNING |  |  | 11/1/2019 0:00 | 1/15/2020 0:00 |  | DESIGN |  |  | 2/1/2020 0:00 | 12/1/2020 0:00 |  | BIDDING |  |  | 1/15/2021 0:00 | 1/15/2022 0:00 |  | CONST |  |  | 4/1/2022 0:00 | 11/1/2022 0:00 |  | WARRANTY |  |  | 11/1/2022 0:00 | 11/1/2030 0:00 | [6 empty] | 3171264.26 | 3115974.045 | 73518 | 2/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 43 | Parks and Recreation | General Parks | Rehabilitation | No | No | 8/27/2018 14:19 |  |  | No
Public Works | P12462 | CORAL RIDGE SMALL WATERMAIN IMPROVEMENTS | This project is for small water main improvements in the Coral Ridge neighborhood. This project will replace existing water mains which are undersized and deteriorated with approximately 16000 linear feet of 6-inch water mains. | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 11 | Hold | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 4979064.5 | 42152.5 | 0 | 0 | 4936912 | PLANNING |  |  | 4/3/2023 0:00 | 10/31/2023 0:00 |  | DESIGN |  |  | 11/1/2023 0:00 | 1/31/2024 0:00 |  | BIDDING |  |  | 2/1/2024 0:00 | 7/31/2024 0:00 |  | CONST |  |  | 8/1/2024 0:00 | 2/28/2025 0:00 |  | WARRANTY |  |  | 3/3/2025 0:00 | 3/3/2026 0:00 | [6 empty] | 4979064.5 | 86509.43 | 73736 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No | No | 8/27/2018 14:33 |  |  | No
Public Works | P12464 | TARPON RIVER A-11 SEWER BASIN REHAB | The project includes point repairs minor road restoration and landscaping and the rehabilitation of mainline sewers. It will employ the use of trenchless technologies to repair sewer system components such as lining of gravity sewers manholes and sewer laterals for Basin A-11. Work also includes pre and post TV survey flow monitoring traffic control and site restoration. This is part of the Wastewater Conveyance System Long Term Remediation Program. | 697 | Louis Lafaurie |  |  | Brandy Leighton | PBS | PBS | 2 | Design | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 7310014 | 425492.81 | 2592581.25 | 1471273 | 2820666.94 | PLANNING |  |  | 12/3/2018 0:00 | 2/15/2019 0:00 |  | DESIGN |  |  | 11/1/2022 0:00 | 8/11/2023 0:00 |  | BIDDING |  |  | 8/23/2023 0:00 | 1/15/2024 0:00 |  | CONST |  |  | 1/16/2024 0:00 | 1/31/2025 0:00 |  | WARRANTY |  |  | 2/3/2025 0:00 | 2/3/2026 0:00 | [6 empty] | 7310014 | 694546.54 | 73580 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 8/27/2018 14:45 |  |  | No
Public Works | P12465 | HARBOR BEACH SEWER BASIN D-34 REHAB | The project includes point repairs minor road restoration and landscaping and the rehabilitation of mainline sewers in Basin D-34. It will employ the use of trenchless technologies to repair sewer system components such as lining of gravity sewers manholes and sewer laterals. Work also includes pre and post TV survey flow monitoring traffic control and site restoration. This is part of the Wastewater Conveyance System Long Term Remediation Program. | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [8 empty] | 1281610 | 1798102 | 1672083 | 126945.46 | 393653.44 | 0 | 1151484.1 | PLANNING |  |  | 3/1/2022 0:00 | 2/1/2024 0:00 |  | DESIGN |  |  | 2/1/2024 0:00 | 5/1/2024 0:00 |  | BIDDING |  |  | 5/1/2024 0:00 | 8/1/2024 0:00 |  | CONST |  |  | 8/1/2024 0:00 | 8/1/2025 0:00 |  | WARRANTY |  |  | 8/1/2025 0:00 | 8/1/2026 0:00 | [6 empty] | 1672083 | 303967.028 | 73707 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No | No | 8/27/2018 14:54 |  |  | No
Transportation and Mobility | P12470 | NW 15TH AVENUE COMPLETE STREETS PROJECT | One mile of NW 15th Avenue connecting Carter Park on Sunrise Blvd. and Mills Pond Park on NW 19th St. and serves vehicle cut through. The scope includes improving bicycle and pedestrian accommodations to increase safety along the corridor for work and school including adding crosswalks. Traffic calming improvements to reduce speeds and discourage cut through traffic along this major collector road bisecting the Lauderdale Manors neighborhood. This project is part of Phase I within the LauderTrail (Comm. Priority) masterplan. | 1360 | Andre Eugent |  |  | Karen Warfel | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 215000 | 190173.09 | 11989.06 | 0 | 12837.85 | PLANNING |  |  | 3/1/2018 0:00 | 3/1/2019 0:00 |  | DESIGN |  |  | 10/1/2019 0:00 | 7/31/2020 0:00 |  | BIDDING |  |  | 8/15/2020 0:00 | 12/31/2020 0:00 |  | CONST |  |  | 1/30/2021 0:00 | 1/30/2022 0:00 |  | WARRANTY |  |  | 2/1/2022 0:00 | 2/1/2023 0:00 | [6 empty] | 215000 | 208506.03 | 73075 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 8 | 24 | 38 | Public Works | Transportation | General Upgrades | No | Yes | 8/28/2018 9:40 |  |  | No
Public Works | P12474 | MID-FIELD TAXIWAY EXTENSION AND RUN-UP AREA | This project is for the design and construction of a Taxiway extension reconstruction and expansion for the run-up area and installation of a blast deflection fence. This project is partially funded by a grant from the Florida Department of Transportation (FDOT) for approximately 80% reimbursement of the eligible project costs. The airport match is 20%. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 6 | Construction | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 1932038 | 241057.55 | 421539.26 | 0 | 1269441.19 | PLANNING |  |  | 7/8/2019 0:00 | 9/30/2019 0:00 |  | DESIGN |  |  | 6/9/2021 0:00 | 12/31/2021 0:00 |  | BIDDING |  |  | 6/6/2022 0:00 | 4/3/2023 0:00 |  | CONST |  |  | 4/4/2023 0:00 | 4/4/2024 0:00 |  | WARRANTY |  |  | 4/5/2024 0:00 | 4/4/2025 0:00 | [6 empty] | 1932038 | 330975.05 | 70016 | 7/7/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 34 | Transportation and Mobility | Airport | New Construction | No | No | 8/30/2018 14:45 |  |  | No
Public Works | P12478 | STORMSTATION 1 FIXED EMERGENCY GENERATORS | Install permanent generator to run the stormstation pumps in the event of a electrical power outage. This project is currently awaiting the execution of the General Civil Services contract by the Procurement Department. Once the contract is executed the current design approximately 80% complete will be finalized and the project can be bid out. There is a projected lead time of 60 weeks on generators therefore the estimated completion for this project will be FY 2024/25. |  |  | 793 | Sayd Hussain | Rares Petrica | PBS | PBS | 2 | Design | 22 | CityFacilities | No |  |  | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 520250 | 67944 | 42981.22 | 325000 | 84324.78 | PLANNING |  |  | 1/3/2021 0:00 | 1/31/2023 0:00 |  | DESIGN |  |  | 2/1/2023 0:00 | 10/30/2023 0:00 |  | BIDDING |  |  | 11/1/2023 0:00 | 4/30/2024 0:00 |  | CONST |  |  | 5/1/2024 0:00 | 5/1/2025 0:00 |  | WARRANTY |  |  | 5/2/2025 0:00 | 5/2/2026 0:00 | [6 empty] | 520250 | 87051.37 | 73379 | 2/6/2024 0:00 | 2/6/2024 0:00 | STATUS | Yes | Yes | [8 empty] | 8/30/2018 14:47 |  |  | Yes
Public Works | P12479 | STORMSTATION 2 FIXED EMERGENCY GENERATORS | Install permanent generator to run the stormstation pumps in the event of a electrical power outage. This project is currently awaiting the execution of the General Civil Services contract by the Procurement Department. Once the contract is executed the current design approximately 80% complete will be finalized and the project can be bid out. There is a projected lead time of 60 weeks on generators therefore the estimated completion for this project will be FY 2024/25. | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 2 | Design | 22 | CityFacilities | No |  |  | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 436000 | 60545.25 | 4762 | 325000 | 45692.75 | PLANNING |  |  | 1/3/2021 0:00 | 1/31/2023 0:00 |  | DESIGN |  |  | 2/1/2021 0:00 | 10/30/2023 0:00 |  | BIDDING |  |  | 11/1/2023 0:00 | 4/30/2024 0:00 |  | CONST |  |  | 5/1/2024 0:00 | 5/1/2025 0:00 |  | WARRANTY |  |  | 5/2/2025 0:00 | 5/2/2026 0:00 | [6 empty] | 436000 | 75734.26 | 73380 | 2/6/2024 0:00 | 2/6/2024 0:00 | STATUS | Yes | Yes | [8 empty] | 8/30/2018 14:47 |  |  | No
Public Works | P12484 | REFURBISHMENT OF THE FIVEASH WTP 5 MG STEEL TANK (NORTH) | The 5 MG Fiveash steel tank interior needs to be sandblasted perform welding repairs on the failing components apply NSF protective coating and perform disinfection using NSF chemicals. The exterior of the tank will need to sandblasted and a protective coating applied. | 1352 | Lamar Case |  |  | Daniel Fisher | PBS | PBS | 8 | Warranty | 23 | Utilities | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | 56 |  | 386423.92 |  |  | 1116211.96 | 923000 |  | 1350000 |  | 736100.98 | 744250.98 | 0 | 1000 | -9150 | PLANNING |  |  | 5/15/2019 0:00 | 2/9/2020 0:00 |  | DESIGN |  |  | 2/10/2020 0:00 | 6/18/2020 0:00 |  | BIDDING |  |  | 6/19/2020 0:00 | 11/30/2022 0:00 |  | CONST |  |  | 12/1/2022 0:00 | 3/25/2023 0:00 |  | WARRANTY |  |  | 2/1/2023 0:00 | 2/1/2024 0:00 |  |  | 923000 | 386423.92 | 1116211.96 | 56 | 736100.98 | 864608.98 | 69274 | 5/19/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 35 | Public Works | Water Sewer | Renovation | No | No | 10/26/2018 13:12 |  |  | No
Public Works | P12485 | FIVEASH WATER TREATMENT PLANT FILTERS REHABILITATION | Rehabilitate all 14 media filters for Phase 02 of this project at the Fiveash Regional Water Treatment Plant (WTP). | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 6 | Construction | 23 | Utilities | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [6 empty] | 3354380 |  | 2900000 | 2900000 | 5720000 | 5402327.29 | 30700.91 | 0 | 286971.8 | PLANNING |  |  | 8/5/2019 0:00 | 10/11/2019 0:00 |  | DESIGN |  |  | 10/14/2019 0:00 | 1/13/2020 0:00 |  | BIDDING |  |  | 1/14/2020 0:00 | 6/1/2022 0:00 |  | CONST |  |  | 6/2/2022 0:00 | 10/18/2024 0:00 |  | WARRANTY |  |  | 10/18/2024 0:00 | 10/18/2025 0:00 |  |  | 3354380 |  |  |  | 5720000 | 5889255.53 | 73737 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation | No | No | 10/29/2018 14:30 |  |  | No
Transportation and Mobility | P12509 | TEMPORARY FIRE STATION 13 | This project is for the relocation of the temporary Fire Station 54 trailers to house temporary Fire Station 13 while the new station is rebuilt substantially where it exists today. | 1367 | Caroline Yeakel |  |  | Kristin Thompson | FIR | TAM | 6 | Construction | 14 | Fire | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 960932 | 308941.53 | 376949.68 | 0 | 275040.79 | PLANNING |  |  | 12/1/2016 0:00 | 1/6/2020 0:00 |  | DESIGN |  |  | 1/7/2020 0:00 | 4/1/2021 0:00 |  | BIDDING |  |  | 4/2/2021 0:00 | 2/1/2022 0:00 |  | CONST |  |  | 2/1/2022 0:00 | 8/1/2023 0:00 |  | WARRANTY |  |  | 8/2/2023 0:00 | 8/1/2024 0:00 |  | 161403.96 |  |  |  |  | 960932 | 450023.28 | 73775 | 3/5/2024 0:00 |  | STATUS | Yes | No | 3 | 17 | 34 | Fire | Fire Bond | New Construction | No | No | 6/18/2019 7:43 |  |  | No
Transportation and Mobility | P12513 | FORT LAUDERDALE BEACH PARK PARKING LOT IMPROVEMENTS (BID) | Improvements to the parking lot and beach area to help in the execution of beach events in this area. These improvements include; a new curb cut on Seabreeze Blvd. for semi-trucks to enter median cuts in the parking lot for tractor trailers to make turns and enter the beach entrance from the lower level of parking lot a cut-through in the center landscape island to decrease event staging area which also maximizes public parking space and water/sewer/powerline extension to the eventsâ€™ beach area.The proposed funding source for the parking lot improvements is money coming from the The Beach Business Improvement District (BID) | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 15 | Complete | 17 | Parking | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 1550000 | 110652.76 | 591152 | 0 | 848195.24 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [5 empty] | 64570 |  |  |  |  | 1550000 | 115742.26 | 73509 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 52 | 74 | 35 | Building Services | Beach CRA | Renovation | No | No | 7/1/2019 13:15 |  | No | Yes
Public Works | P12515 | NORTH FORK RIVERFRONT PARK | The North Fork Riverfront Park is a City owned parcel with possible wetlands located on the south bank of the North Fork of the New River. | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PKR | PBS | 11 | Hold | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 0 | 1991.9 | 0 | 0 | -1991.9 | PLANNING | [5 empty] | DESIGN | 2/16/2021 0:00 | 8/10/2022 0:00 | 2/16/2021 0:00 | 7/7/2025 0:00 |  | BIDDING | 8/11/2022 0:00 | 2/13/2023 0:00 |  |  |  | CONST | 2/14/2023 0:00 | 2/14/2025 0:00 |  |  |  | WARRANTY | 2/15/2025 0:00 | 2/15/2026 0:00 | [8 empty] | 0 | 77786.9 | 73397 | 2/15/2024 0:00 |  | STATUS | No | No | 8 | 11 | 68 | Public Works | Stormwater | Study/Investigation | No |  | 8/2/2019 13:58 |  |  | No
Public Works | P12517 | ANNUAL CONCRETE AND PAVER STONES CONTRACT | Repair of damaged sidewalks and paver bricks City-wide based on results of the Sidewalk Inspection and Management System. | 757 | Jean Examond |  |  | Jill Prizlee | PBS | PBS | 10 | Annual | 27 | Roadway Improvements | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | [6 empty] | 971000 |  |  | 2000000 | 3693164 | 2505667.02 | 239745.58 | 5 | 947746.4 | PLANNING |  |  | 7/15/2019 0:00 | 8/31/2019 0:00 |  | DESIGN |  |  | 9/1/2019 0:00 | 11/6/2019 0:00 |  | BIDDING |  |  | 11/6/2019 0:00 | 4/7/2020 0:00 |  | CONST |  |  | 4/8/2020 0:00 | 4/7/2022 0:00 |  | WARRANTY |  |  | 4/8/2022 0:00 | 4/7/2023 0:00 |  | 1800000 | 971000 |  |  |  | 3693164 | 3846116.19 | 73786 | 3/6/2024 0:00 | 3/6/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 35 | Public Works | Engineering | Renovation | No | No | 8/7/2019 9:24 |  |  | No
Public Works | P12518 | ANNUAL ASPHALT MILL AND RESURFACING | Citywide resurfacing of streets based on assessed conditions. Streets identified for resurfacing will be scheduled based on the Pavement Condition Index (PCI) from the 2013 Pavement Management Inspection. | 757 | Jean Examond |  |  | Jill Prizlee | PBS | PBS | 10 | Annual | 27 | Roadway Improvements | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | [6 empty] | 619972.4 |  |  | 2000000 | 4000000 | 2208334.79 | 102868.79 | 1624365.43 | 64430.99 | PLANNING |  |  | 7/15/2019 0:00 | 11/1/2019 0:00 |  | DESIGN |  |  | 12/2/2019 0:00 | 12/11/2019 0:00 |  | BIDDING |  |  | 12/12/2019 0:00 | 5/29/2020 0:00 |  | CONST |  |  | 6/1/2020 0:00 | 3/2/2023 0:00 |  | WARRANTY | [5 empty] | 2000000 | 619972.4 |  |  |  | 4000000 | 2618254.905 | 73784 | 3/6/2024 0:00 | 3/6/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 35 | Public Works | Engineering | Renovation | No | No | 8/7/2019 9:27 | No | No | No
Transportation and Mobility | P12519 | FLAGLER GREENWAY TRANSPORTATION EQUITY IMPROVEMENT PROJECT | This project will enhance accessibility and connections to the Flagler Greenway which in a designated Transportation Equity Zone. The project will implement safe connections to Flagler Greenway to promote active transport initiatives to help the City become more walk-able and bike-able. The project includes construction of ADA ramps RFB beacons raised crosswalks and high intensity signing/striping Project within Phase I of LauderTrail priority section. | 1210 | Karen Warfel |  |  |  | TAM | TAM | 15 | Complete | 27 | Roadway Improvements | Yes |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 71205 | -736.16 | 0 | 0 | 71941.16 | PLANNING |  |  | 9/1/2019 0:00 | 3/31/2020 0:00 |  | DESIGN |  |  | 4/1/2020 0:00 | 8/5/2021 0:00 |  | BIDDING |  |  | 8/6/2021 0:00 | 2/21/2022 0:00 |  | CONST |  |  | 2/28/2022 0:00 | 5/26/2022 0:00 |  | WARRANTY |  |  | 5/26/2022 0:00 | 5/25/2023 0:00 | [6 empty] | 71205 | 22492.84 | 73086 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 8 | 24 | 34 | Public Works | Transportation | New Construction | No | Yes | 8/8/2019 8:55 |  |  | No
Public Works | P12520 | EXECUTIVE AIRPORT RUNWAY INCURSION MITIGATION | The Federal Aviation Administrations's (FAA) Office of Airports (ARP) has developed a comprehensive and multi-year program to identify prioritize and implement solutions to address locations to mitigate runway incursions caused by an aircraft. FXE identified nine (9) areas on their airfield as areas of concern that could potentially lead to unauthorized runway incursions. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 6 | Construction | 3 | Airport | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [8 empty] | 85000 | 85000 | 1320042 | 210281.8 | 0 | 0 | 1109760.2 | PLANNING |  |  | 6/2/2020 0:00 | 7/2/2020 0:00 |  | DESIGN |  |  | 7/3/2020 0:00 | 9/16/2020 0:00 |  | BIDDING |  |  | 9/17/2020 0:00 | 4/7/2021 0:00 |  | CONST |  |  | 4/8/2021 0:00 | 3/25/2022 0:00 |  | WARRANTY |  |  | 3/26/2022 0:00 | 3/26/2023 0:00 | [6 empty] | 1320042 | 326631.55 | 70017 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 34 | Transportation and Mobility | Airport | New Construction | No | No | 8/28/2019 13:40 |  |  | No
Public Works | P12521 | RUNWAY 31 BYPASS TAXIWAYS | This project is for design and construction of by-pass taxiways at Runway 31 as called for in the current AirportLayout Plan (ALP). The project is partially funded by a grant from the Florida Department of Transportation (FDOT)for approximately 80% reimbursement of eligible project costs and an airport match of 20%. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 2 | Design | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 674536 | 61138.12 | 434187.25 | 0 | 179210.63 | PLANNING |  |  | 2/15/2021 0:00 | 5/27/2021 0:00 |  | DESIGN |  |  | 8/18/2021 0:00 | 4/1/2022 0:00 |  | BIDDING |  |  | 4/2/2022 0:00 | 4/5/2023 0:00 |  | CONST |  |  | 6/1/2023 0:00 | 2/29/2024 0:00 |  | WARRANTY |  |  | 3/2/2024 0:00 | 3/2/2025 0:00 | [6 empty] | 674536 | 91574.22 | 69919 | 6/30/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 38 | Transportation and Mobility | Airport | General Upgrades | No | No | 9/10/2019 9:09 |  |  | No
Public Works | P12522 | RUNWAY 9 RUN-UP AREA (SOUTH) | This project is for the design and construction of the run-up area and the installation of a blast fence at the westernend of Runway 9. This project is partially funded by a grant from the Federal Aviation Administration (FAA) forapproximately 90% reimbursement of the eligible project costs and by a grant from the Florida Department ofTransportation (FDOT) for approximately 5% reimbursement of the eligible project costs. The Airport match is 5%. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 4 | Bidding | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 110678 | 69133 | 0 | 0 | 41545 | PLANNING |  |  | 6/2/2021 0:00 | 3/1/2022 0:00 |  | DESIGN |  |  | 3/2/2022 0:00 | 8/1/2022 0:00 |  | BIDDING |  |  | 8/2/2022 0:00 | 1/6/2023 0:00 |  | CONST |  |  | 1/9/2023 0:00 | 3/8/2024 0:00 |  | WARRANTY |  |  | 3/9/2024 0:00 | 3/10/2025 0:00 | [6 empty] | 110678 | 142969 | 70018 | 7/7/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 38 | Transportation and Mobility | Airport | General Upgrades | No | No | 9/10/2019 9:14 |  |  | No
Public Works | P12528 | GTL CHLORINE FLASH MIX REMODEL | The George T. Lohmeyer Wastewater Treatment Plant (GTL) has one chlorine flash mix basin where chlorine isinjected to effluent before discharge. This project will require bypass pumping of the basin to enable concreteinspection and repairs and to replace all slide gates. Chlorine injection will also be moved upstream. | 1176 | _PROJECT MANAGER |  |  | Daniel Fisher | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | PBS | 458 | Yes | Yes | -1 | -1 | -1 | -1 | 150 |  | 0 |  |  | 11516111.88 | 11516111.88 |  |  |  | 12867577.88 | 413373.5 | 11729698.88 | 0 | 724505.5 | PLANNING |  |  | 1/1/2020 0:00 | 7/16/2020 0:00 |  | DESIGN |  |  | 7/17/2020 0:00 | 3/1/2022 0:00 |  | BIDDING |  |  | 3/2/2022 0:00 | 7/23/2023 0:00 |  | CONST |  |  | 7/24/2023 0:00 | 9/6/2024 0:00 |  | WARRANTY |  |  | 9/7/2024 0:00 | 9/7/2025 0:00 |  |  | 11516111.88 | 0 | 11516111.88 | 150 | 12867577.88 | 601943.96 | 73699 | 2/27/2024 0:00 | 2/27/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No | No | 9/10/2019 9:47 |  |  | No
Public Works | P12529 | EFFLUENT PUMPS STANDBY GENERATOR & ADMIN BLDG IMPROVEMENTS | The George T. Lohmeyer Wastewater Treatment Plant (GTL) has no standby electrical power for the effluent pumps.When Florida Power and Light (FPL) power is lost the effluent discharges to the Intracoastal requiring FloridaDepartment of Environmental Protection notification. This project will require significant upgrades to theAdministration Building to add a 10 megawatt gas-turbine emergency generator on a new second floor. | 1212 | Daniel Fisher |  |  | Daniel Fisher | PBS | PBS | 2 | Design | 37 | Water Sewer | No |  | 458 | Yes | Yes | -1 | -1 | -1 | -1 | [8 empty] | 27000000 | 28200000 | 28295566 | 467217.51 | 8447049.31 | 2324861.2 | 17056437.98 | PLANNING |  |  | 3/9/2020 0:00 | 10/10/2022 0:00 |  | DESIGN |  |  | 10/10/2022 0:00 | 3/26/2024 0:00 |  | BIDDING |  |  | 3/27/2024 0:00 | 9/23/2024 0:00 |  | CONST |  |  | 9/24/2024 0:00 | 9/19/2025 0:00 |  | WARRANTY |  |  | 9/20/2026 0:00 | 9/19/2027 0:00 | [6 empty] | 28295566 | 613130.43 | 73375 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | Yes | No | 9/10/2019 10:04 |  |  | No
Public Works | P12530 | DEEPWELL ELECTRIC POWER INSTRUMENTATION & CONTROL | The Deepwell Underground Injection site is the location of final disposal of treated effluent from the George T .Lohmeyer Wastewater Treatment Plant. This site consists of 5 wells with associated instrumentation andelectrically actuated control valves that inject the treated water. This project will replace the underground electricalconduit and electrical feeders to the equipment for the 5 wells. The site is over 1200 feet in length and the newconduit will extend across nearly the entire length. This project will require excavation of the existing conduit andthe transition of electrical feeders one (1) well at a time. | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 458 | Yes | Yes | -1 | -1 | -1 | -1 | [8 empty] | 2950000 | 3200000 | 4111687 | 2820488.36 | 590045.09 | 240789.23 | 460364.32 | PLANNING |  |  | 10/28/2019 0:00 | 2/28/2020 0:00 |  | DESIGN |  |  | 2/28/2020 0:00 | 10/16/2020 0:00 |  | BIDDING |  |  | 10/16/2020 0:00 | 2/1/2022 0:00 |  | CONST |  |  | 2/1/2022 0:00 | 4/30/2024 0:00 |  | WARRANTY |  |  | 4/30/2024 0:00 | 4/30/2025 0:00 | [6 empty] | 4111687 | 3101865.26 | 73773 | 3/5/2024 0:00 |  | STATUS | No | No | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No | No | 9/10/2019 10:07 |  |  | No
Public Works | P12531 | NORTH NEW RIVER DRIVE EAST WM REPLACEMENT | This project is to replace approximately 1285 linear feet of 6 ductile iron water main that has had numerous failureswith 8 polyvinyl chloride (PVC) water main between East Las Olas and SE 3rd Avenue along North New River DriveEast. | 1370 | William Power |  |  | William Power | PBS | PBS | 2 | Design | 23 | Utilities | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 1474309.08 | 630414.91 | 496868.83 | 0 | 347025.34 | PLANNING |  |  | 4/3/2023 0:00 | 6/30/2023 0:00 |  | DESIGN |  |  | 7/3/2023 0:00 | 9/29/2023 0:00 |  | BIDDING |  |  | 10/2/2023 0:00 | 4/30/2024 0:00 |  | CONST |  |  | 5/1/2024 0:00 | 12/31/2024 0:00 |  | WARRANTY |  |  | 12/31/2024 0:00 | 12/31/2025 0:00 | [6 empty] | 1474309.08 | 722737.0175 | 71539 | 10/16/2023 0:00 | 10/16/2023 0:00 | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No | No | 9/10/2019 10:11 |  |  | No
Public Works | P12539 | TAXIWAY GOLF PAVEMENT REHAB | Design for the milling and re-surfacing of the asphalt pavement along taxiway Golf between taxiways Charlie andNovember based on the current pavement condition index (PCI) of 69. New pavement striping will also be applied.The project will also involve the re-design of taxiway Mike to conform to current Federal Aviation Administration (FAA)design standards including new light-emitting-diode (LED) taxiway edge lights and guidance signs. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 4 | Bidding | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 586988 | 31377.84 | 523936.6 | 0 | 31673.56 | PLANNING |  |  | 4/1/2020 0:00 | 3/1/2021 0:00 |  | DESIGN |  |  | 8/18/2021 0:00 | 4/1/2022 0:00 |  | BIDDING |  |  | 4/2/2022 0:00 | 11/23/2022 0:00 |  | CONST |  |  | 2/13/2023 0:00 | 12/29/2023 0:00 |  | WARRANTY |  |  | 12/30/2023 0:00 | 12/31/2024 0:00 | [6 empty] | 586988 | 53225.33 | 69921 | 6/30/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 43 | Transportation and Mobility | Airport | Rehabilitation | No | No | 9/10/2019 14:58 |  |  | No
Public Works | P12540 | RUNWAY 27 BY-PASS TAXIWAYS | Design for the construction of two by-pass taxiways south of the east end of runway 27 to provide for a more efficientflow of traffic between the north and south sides of the airfield. Additionally taxiway Echo will be re-aligned toprovide a 90-degree entrance and the run-up area will be reconfigured to meet current Federal Aviation Administration(FAA) design standards. The project will include pavement demolition asphalt electrical sodding and striping. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 11 | Hold | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 150150 | 9881 | 0 | 0 | 140269 | PLANNING |  |  | 7/1/2026 0:00 | 1/1/2027 0:00 |  | DESIGN |  |  | 1/4/2027 0:00 | 8/31/2027 0:00 |  | BIDDING |  |  | 9/1/2027 0:00 | 12/31/2027 0:00 |  | CONST |  |  | 1/3/2028 0:00 | 9/1/2028 0:00 |  | WARRANTY |  |  | 9/2/2028 0:00 | 9/3/2029 0:00 | [6 empty] | 150150 | 20110.25 | 69185 | 5/12/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 38 | Transportation and Mobility | Airport | General Upgrades | No | No | 9/10/2019 15:03 |  |  | No
Public Works | P12549 | SEAWALL MAINTENANCE | This project is for replacement of two city owned seawalls: Sebastian and Seville. The replacement efforts will include potential structural modifications to address the challenges associated with sea level rise in addition to the standard capital repairs rehabilitation or replacement.This project is currently awaiting the execution of the General Civil Services contract by the Procurement Department. Once the contract is executed the current design approximately 90% complete will be finalized and the project can be bid out. There is a projected construction period of 12 months for the two combined seawalls. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 2 | Design | 33 | Seawalls | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 940000 | 288924.5 | 0 | 0 | 651075.5 | PLANNING |  |  | 1/1/2020 0:00 | 11/1/2020 0:00 |  | DESIGN |  |  | 11/2/2020 0:00 | 12/31/2023 0:00 |  | BIDDING |  |  | 1/1/2024 0:00 | 8/1/2024 0:00 |  | CONST |  |  | 8/2/2024 0:00 | 8/2/2025 0:00 |  | WARRANTY |  |  | 8/3/2025 0:00 | 8/3/2026 0:00 | [6 empty] | 940000 | 351331.98 | 73756 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 16 | 43 | Public Works | Marine Facilities | Rehabilitation | No | No | 9/10/2019 16:21 |  |  | No
Public Works | P12553 | HORTT PARK PLAYGROUND REPLACEMENT | New playground replacement at Hortt Park in Shady Banks neighborhood. All existing playground equipment is outdated and will be replaced. The existing playground surfacing is mulch proposed surfacing is rubber poured in place. Existing Shade sail posts are in good condition but the shade sails will also have to be replaced. | 883 | Irina Tokar |  |  | Irina Tokar | PKR | PBS | 15 | Complete | 12 | Parks | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 414750 | 365229 | 0 | 0 | 49521 | PLANNING |  |  | 9/1/2019 0:00 | 10/1/2019 0:00 |  | DESIGN |  |  | 10/8/2019 0:00 | 11/30/2019 0:00 |  | BIDDING |  |  | 12/15/2019 0:00 | 8/1/2020 0:00 |  | CONST |  |  | 12/1/2020 0:00 | 4/7/2021 0:00 |  | WARRANTY |  |  | 4/7/2021 0:00 | 4/7/2022 0:00 | [6 empty] | 414750 | 450619.5 | 70360 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 35 | Parks and Recreation | General Parks | Renovation | No | No | 10/4/2019 15:42 |  |  | No
Public Works | P12554 | PEELE DIXIE OLD PLANT ELECTRICAL CONNECTION | The old plant is located in the same lot of the new plant but these the had separated transformers with FPL electrical meters. The transformer for the old plant blew out and since then it has been using a city power generator. The project is to provide the old plant with a permanent electrical connection. | 1278 | Alex Torres |  |  | Jorge Holguin | PBS | PBS | 15 | Complete | 23 | Utilities | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 10745 | 10876 | 0 | 0 | -131 | PLANNING |  |  | 10/7/2019 0:00 | 12/10/2019 0:00 |  | DESIGN |  |  | 12/11/2019 0:00 | 1/17/2020 0:00 |  | BIDDING |  |  | 1/21/2020 0:00 | 11/13/2020 0:00 |  | CONST |  |  | 12/22/2020 0:00 | 4/9/2021 0:00 |  | WARRANTY |  |  | 4/10/2021 0:00 | 4/9/2022 0:00 | [6 empty] | 10745 | 33626.5 | 70343 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades | No | No | 10/17/2019 16:07 |  |  | No
Public Works | P12555 | COONTIE HATCHEE PARK - PLAYGROUND REPLACEMENT | Installation of the of the new playground surfacing and exercise equipment. The playground will be for two age groups 2-5 and 5-12. The new playground should be similar in footprint to the one we are replacing. The playground should use natural looking materials but durable and long-lasting. The playground should have wood mulch surface as existing. | 1156 | Danica Grujicic |  |  | Irina Tokar | PKR | PBS | 8 | Warranty | 12 | Parks | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 350000 | 347145.19 | 0 | 0 | 2854.81 | PLANNING |  |  | 9/1/2019 0:00 | 11/1/2019 0:00 |  | DESIGN |  |  | 11/2/2019 0:00 | 5/1/2020 0:00 |  | BIDDING |  |  | 6/1/2020 0:00 | 9/1/2020 0:00 |  | CONST |  |  | 11/1/2020 0:00 | 4/1/2021 0:00 |  | WARRANTY |  |  | 4/2/2021 0:00 | 4/2/2022 0:00 | [6 empty] | 350000 | 412005.28 | 70361 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 28 | 38 | Parks and Recreation | Facilities | General Upgrades | No | No | 10/24/2019 16:04
Transportation and Mobility | P12557A | NE 4TH AVENUE STREETSCAPE PROJECT - SUNRISE BLVD TO NE 13TH ST | Transportation improvements and streetscape enhancements to include new wide sidewalks including American Disability Act (ADA) ramps pedestrian street lighting shade trees and potential entryway signs features. Scope includes the engineering design design survey construction and construction inspection services. Funded with BC Grant for economic investment through implementation of complete streets. | 1318 | Mackendy Philippi |  |  |  | CRA | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | Yes |  |  |  | Yes | 0 | -1 | 0 | 0 | [10 empty] | 0 | 381719.96 | 613535.05 | 0 | -995255.01 | PLANNING |  |  | 1/2/2020 0:00 | 7/31/2020 0:00 |  | DESIGN |  |  | 8/3/2020 0:00 | 8/31/2021 0:00 |  | BIDDING |  |  | 9/1/2021 0:00 | 12/31/2021 0:00 |  | CONST |  |  | 1/4/2022 0:00 | 1/4/2023 0:00 |  | WARRANTY |  |  | 1/4/2023 0:00 | 1/4/2024 0:00 | [6 empty] | 0 | 396683.96 | 73063 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 8 | 24 | 34 | Public Works | Transportation | New Construction | No | No | 10/30/2019 10:11 |  |  | No
Public Works | P12566 | NORTH REDUNDANT SEWER FORCE MAIN | Following the numerous force main breaks from December 2019 the City declared this as an emergency project. Two contractors were awarded to install the pipe which will take flows from Coral Ridge Golf Course to GTL wastewater treatment plant. This limits for this project is from Coral Ridge Golf Course up to approximately 900 feet south from the intersection of E Sunrise Blvd and NE 15th Ave. Murphy Pipeline Contractors Inc. was awarded the contract to install this portion. | 1031 | Scott Teschky |  |  | Scott Teschky | PBS | PBS | 15 | Complete | 37 | Water Sewer | No |  |  | Yes | Yes | -1 | -1 | 0 | 0 | 150 |  | 3993049.27 |  |  | 28413765.27 | 24420716 |  |  |  | 29687890.79 | 29665370.93 | 0 | 0 | 22519.86 | PLANNING |  |  | 12/23/2019 0:00 | 1/12/2020 0:00 |  | DESIGN |  |  | 1/24/2020 0:00 |  |  | BIDDING | [5 empty] | CONST |  |  | 1/24/2020 0:00 | 10/31/2022 0:00 |  | WARRANTY |  |  | 8/16/2021 0:00 | 8/16/2022 0:00 |  |  | 24420716 | 3993049.27 | 28413765.27 | 150 | 29687890.79 | 30753430.64 | 70344 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | Yes |  | 1/2/2020 11:51 |  |  | No
Police | P12573 | NEW POLICE HEADQUARTERS | The new Police Headquarters is anticipated to be approximately 200000 SF in total size with a multi-level parking garage for approximately 400 vehicles. The city leadership team selected the West Broward Boulevard site located at 1300 West Broward Boulevard for this project. On this site the current police headquarters shall remain in use during construction and then be demolished as part of this project at the completion of the new facility. It is the desire of the city to utilize the design and placement of this building to be a gateway into the downtown area. The amount of site area that this project would utilize will be determined during the planning and design process. It is anticipated that the Headquarters will be 3-4 stories. | 1358 | Robert Buscemi |  |  |  | POL | POL | 6 | Construction | 16 | Police | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 144875000 | 48777725.7 | 83942547.92 | 4039688 | 8115038.38 | PLANNING | 8/1/2019 0:00 | 2/15/2021 0:00 | 1/1/2020 0:00 |  |  | DESIGN | 9/18/2020 0:00 | 6/1/2021 0:00 | 9/18/2020 0:00 |  |  | BIDDING | 2/15/2021 0:00 | 6/1/2021 0:00 |  |  |  | CONST | 6/16/2021 0:00 | 1/23/2023 0:00 |  |  |  | WARRANTY | 1/23/2023 0:00 | 1/23/2024 0:00 | [8 empty] | 144875000 | 48963209.7 | 73215 | 1/29/2024 0:00 |  | STATUS | Yes | Yes | 7 | 21 | 34 | Police | Police Facilities | New Construction | No | No | 2/11/2020 14:16 |  |  | Yes
Parks and Rec | P12578 | POOL RESURFACING â€“ CARTER POOL CROISSANT POOL RIVERLAND POOL | The project is to resurface two pools and one water playground. The pools and water playground are showing spots where the diamond brite has come up over the years even with patching. One of the pools has not been resurfaced since it was opened in 2005. |  |  |  |  | Enrique Sanchez | PKR | PKR | 11 | Hold | 12 | Parks | No |  |  | Yes | Yes | 0 | 0 | -1 | -1 | [8 empty] | 170000 | 195000 | 124450 | 124449.63 | 0 | 0 | 0.37 | PLANNING |  |  | 4/1/2020 0:00 | 4/20/2020 0:00 |  | DESIGN |  |  | 5/1/2020 0:00 | 6/1/2020 0:00 |  | BIDDING |  |  | 8/1/2020 0:00 | 1/15/2021 0:00 |  | CONST |  |  | 4/1/2021 0:00 | 7/1/2021 0:00 |  | WARRANTY |  |  | 7/1/2021 0:00 | 7/1/2022 0:00 | [6 empty] | 124450 | 144633.63 | 71797 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 23 | 43 | Parks and Recreation | General Services | Rehabilitation | No | No | 4/3/2020 9:05
Public Works | P12585 | GALT OCEAN MILE BEAUTIFICATION | This project will be for the Galt Ocean Mile corridor improvements. The existing sidewalk has multiple patches due to utility repairs and difficulty of matching the existing construction material originally installed light poles and fixtures are faded and in poor physical appearance existing street surface is worn and existing striping is faded. The project scope will include milling and resurfacing existing road wider sidewalks with decorative paver inserts royal palms paver raised intersections pedestrian lighting pavement markings and regulatory signs. | 1293 | Gary Foster |  |  | Gary Foster | PBS | PBS | 2 | Design | 27 | Roadway Improvements | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [9 empty] | 4000000 | 3055000 | 191876.6 | 265655.03 | 0 | 2597468.37 | PLANNING |  |  | 9/6/2021 0:00 | 7/5/2023 0:00 |  | DESIGN |  |  | 7/5/2023 0:00 | 6/24/2024 0:00 |  | BIDDING |  |  | 6/24/2024 0:00 | 12/31/2024 0:00 |  | CONST |  |  | 12/31/2024 0:00 | 12/31/2025 0:00 |  | WARRANTY |  |  | 12/31/2025 0:00 | 12/31/2026 0:00 | [6 empty] | 3055000 | 287314.26 | 73383 | 2/6/2024 0:00 | 2/6/2024 0:00 | STATUS | Yes | Yes | 8 | 23 | 43 | Public Works | General Services | Rehabilitation | No | No | 7/16/2020 8:27 |  |  | No
Public Works | P12597 | NE 1ST STREET BRIDGE | This project is for a full bridge replacement at NE 1st Street over the Stranahan Lake (Bridge #865727) due to existing City damaged infrastructure. The bridge is a 44-feet long two-span steel multi-girder beam bridge that was constructed in 1940. The bridge has a roadway width of 24.1 feet and carries two lanes of traffic in a residential neighborhood. The work will include removing and replacing the vehicular and pedestrian structure and installing a new bridge with an upgraded structure to meet Florida Department of Transportation (FDOT) compliance standards. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 2716084 | 40278 | 0 | 0 | 2675806 | PLANNING |  |  | 4/4/2022 0:00 | 1/18/2023 0:00 |  | DESIGN |  |  | 1/19/2023 0:00 | 1/19/2024 0:00 |  | BIDDING |  |  | 1/22/2024 0:00 | 6/21/2024 0:00 |  | CONST |  |  | 6/24/2024 0:00 | 6/27/2025 0:00 |  | WARRANTY |  |  | 6/28/2025 0:00 | 6/28/2026 0:00 | [6 empty] | 2716084 | 80922 | 73488 | 2/12/2024 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 38 | Public Works | Bridges | General Upgrades |  |  | 9/22/2020 16:46
Transportation and Mobility | P12599 | ADA-COMPLIANT BUS STOPS | This project concerns the installation of 15 ADA-Compliant Bus Stops along the Community Bus (Sun Trolley) Service Routes. As of 2019 15 bus stops have been identified as â€˜non-compliantâ€™ within the City. An additional attachment has been provided to detail the locations of the non-compliant stops. Broward County Transit (BCT) has provided a cost estimate for work needed to obtain compliance which is estimated at $25000 per bus stop for a total of $375000 to update all 15 bus stop locations to ADA compliance standards. The work would include: â€¢ Purchase of Right of Wayâ€¢ Relocation of utilities/cables/drainageâ€¢ Installation of concrete padâ€¢ Redesign curbing around locationâ€¢ Shelter/bus equipment | 1292 | Lisa Marie Glover |  |  |  | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 300000 | 70353.27 | 0 | 0 | 229646.73 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 300000 | 71433.27 | 73070 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 42 | Transportation and Mobility | Transportation | ADA Compliance |  |  | 9/22/2020 16:46
Public Works | P12604 | SMALL WATER MAIN REPLACEMENT - HENDRICKS ISLE | This project will replace approximately 3500 linear feet of old 6-inch water main preferably by pipe bursting methods to minimize impact to neighbors. Milling and re-pavement of the entire street will be done to allow for better driving conditions. | 1380 | Gabrielle Bork |  |  | William Power | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 454 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 1640637 | 124581.25 | 0 | 0 | 1516055.75 | PLANNING |  |  | 1/1/2024 0:00 | 12/31/2024 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1640637 | 176540.56 | 73724 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation |  |  | 9/22/2020 16:48 |  |  | No
Public Works | P12605 | NEW PUMPING STATION FLAGLER VILLAGE A-24 | This project is for the design and construction of a new wastewater pump station between NE 3rd Avenue and NE 4th Avenue on NE 6th Street. The project will split the existing gravity system in the same location and redirect the southern section to the new pump station construct a new 12-inch force main from the new pump station to the existing 18-inch force main on NE 5th Street. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | -1 | 0 | 0 | 282 |  | 0 |  |  | 3615000 | 3615000 |  |  | 1700000 | 4604871 | 3778437.84 | 345557.83 | 0 | 480875.33 | PLANNING |  |  | 7/1/2021 0:00 | 6/30/2022 0:00 |  | DESIGN |  |  | 7/1/2022 0:00 | 2/28/2023 0:00 |  | BIDDING |  |  | 3/1/2022 0:00 | 6/9/2023 0:00 |  | CONST |  |  | 6/12/2023 0:00 | 5/31/2024 0:00 |  | WARRANTY |  |  | 6/1/2024 0:00 | 6/1/2025 0:00 |  |  | 3615000 | 0 | 3615000 | 282 | 4604871 | 3946966.32 | 73765 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/22/2020 16:48 |  |  | No
Public Works | P12606 | CORAL RIDGE COUNTRY CLUB ESTATES B11 BASIN REHAB | The project includes point repairs minor road restoration and landscaping and the rehabilitation of mainline sewers in Basin B-11. It will employ the use of trenchless technologies to repair sewer system components such as the lining of gravity sewers manholes and sewer laterals. Work also includes pre and post Closed Circuit Television (CCTV) survey flow monitoring traffic control and site restoration. This is part of the Wastewater Conveyance System Long Term Remediation Program. | 697 | Louis Lafaurie |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 454 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 5741374 | 82329 | 0 | 0 | 5659045 | PLANNING |  |  | 12/1/2020 0:00 | 8/31/2022 0:00 |  | DESIGN |  |  | 9/1/2022 0:00 | 11/1/2023 0:00 |  | BIDDING |  |  | 11/2/2023 0:00 | 1/31/2024 0:00 |  | CONST |  |  | 2/1/2024 0:00 | 2/3/2025 0:00 |  | WARRANTY |  |  | 2/4/2025 0:00 | 2/4/2026 0:00 | [6 empty] | 5741374 | 178095.735 | 73669 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 43 | Public Works | Utilities Engineering | Rehabilitation |  |  | 9/22/2020 16:48 |  |  | No
Public Works | P12608 | TRIPLEX PUMPING STATION REHABILITATION | This project is for the complete rehabilitation of wastewater Pump Stations A-7 A-8 A-20 A-22 A-23 A-27 A-28 A-29 A-31 B-4 and B-11. The work shall include the removal and replacement of all mechanical electrical and ventilation equipment replacement of all pumps pipes valves suction and discharge piping re-routing of discharge piping repairs and protective coating of the wet well relocation of all controls to outside of the station and any structural repairs needed. All pumps and equipment shall meet current conditions and take into account any future development. | 1176 | _PROJECT MANAGER |  |  | Daniel Fisher | PBS | PBS | 2 | Design | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 14853955.05 | 1200012.1 | 158943.5 | 0 | 13494999.45 | PLANNING |  |  | 1/1/2021 0:00 | 3/1/2022 0:00 |  | DESIGN |  |  | 3/1/2022 0:00 | 4/1/2024 0:00 |  | BIDDING |  |  | 4/2/2024 0:00 | 9/29/2024 0:00 |  | CONST |  |  | 9/30/2024 0:00 | 10/1/2026 0:00 |  | WARRANTY |  |  | 10/2/2026 0:00 | 10/2/2027 0:00 | [6 empty] | 14853955.05 | 1321195.42 | 73700 | 2/27/2024 0:00 | 2/27/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation |  |  | 9/22/2020 16:49 |  |  | No
City Manager | P12612 | RUNWAY 9 TAXIWAY INTERSECTION IMPROVEMENTS | Design for the re-alignment of taxiways Echo and Juliet on the southern end of runway 9. The taxiways will be extended into perpendicular taxiways. The project will also include the milling and resurfacing of taxiway Echo. New asphalt striping sodding and light-emitting-diode (LED) edge-lights and guidance signs will be installed. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 22000 | 10397 | 0 | 0 | 11603 | PLANNING |  |  | 6/2/2021 0:00 | 9/30/2022 0:00 |  | DESIGN |  |  | 4/1/2022 0:00 | 8/1/2022 0:00 |  | BIDDING |  |  | 8/2/2022 0:00 | 1/6/2023 0:00 |  | CONST |  |  | 1/9/2023 0:00 | 3/8/2024 0:00 |  | WARRANTY |  |  | 3/9/2024 0:00 | 3/10/2025 0:00 | [6 empty] | 22000 | 21315.5 | 71858 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 38 | City Manager's Office | Airport | General Upgrades |  |  | 9/22/2020 16:50 |  |  | No
Public Works | P12615 | 1544 ARGYLE DRIVE STORMWATER IMPROVEMENTS | This project includes replacement and installation of new stormwater infrastructures at 1544 Argyle Drive. | 1336 | Scarlet Del Valle |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 295885 | 52036.5 | 231103.15 | 0 | 12745.35 | PLANNING | 10/1/2021 0:00 | 5/31/2022 0:00 | 10/1/2021 0:00 | 12/31/2022 0:00 |  | DESIGN |  |  | 1/1/2023 0:00 | 3/31/2023 0:00 |  | BIDDING |  |  | 4/1/2023 0:00 | 5/31/2023 0:00 |  | CONST | 6/1/2022 0:00 | 12/31/2022 0:00 | 6/1/2023 0:00 | 9/30/2023 0:00 |  | WARRANTY | 1/1/2023 0:00 | 1/1/2024 0:00 | 10/1/2023 0:00 | 9/30/2024 0:00 | [6 empty] | 295885 | 97477.125 | 73732 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 38 | Public Works | Stormwater | General Upgrades |  |  | 9/22/2020 16:51 |  |  | No
Public Works | P12616 | NE 16TH STREET STORMWATER IMPROVEMENTS | This project is for the installation of stormwater infrastructure to alleviate stormwater flooding on NE 16th Street between NE 4th & 5th Avenues adjacent to Fort Lauderdale High School. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 8 | Warranty | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 300000 | 215390.4 | 0 | 0 | 84609.6 | PLANNING |  |  | 10/12/2020 0:00 | 11/30/2020 0:00 |  | DESIGN |  |  | 12/1/2020 0:00 | 5/31/2021 0:00 |  | BIDDING |  |  | 6/1/2021 0:00 | 8/20/2021 0:00 |  | CONST |  |  | 8/23/2021 0:00 | 10/23/2021 0:00 |  | WARRANTY |  |  | 10/24/2021 0:00 | 10/24/2022 0:00 | [6 empty] | 300000 | 239185.02 | 73757 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 38 | Public Works | Stormwater | General Upgrades |  |  | 9/22/2020 16:51
Public Works | P12617 | 1801 NE 45TH STREET STORMWATER IMPROVEMENTS | This project is for the installation of stormwater infrastructure to alleviate stormwater flooding at 1801 NE 45th Street. | 1258 | Thomas Lawrence |  |  | Rares Petrica | PBS | PBS | 8 | Warranty | 36 | Stormwater | No |  | 470 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 131059 | 126993 | 0 | 0 | 4066 | PLANNING | 10/1/2021 0:00 | 2/28/2022 0:00 | 10/1/2021 0:00 | 2/28/2022 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | 3/1/2022 0:00 | 4/30/2022 0:00 | 2/28/2022 0:00 | 10/1/2022 0:00 |  | WARRANTY | 5/1/2022 0:00 | 5/1/2023 0:00 | 9/1/2022 0:00 | 5/20/2023 0:00 | [6 empty] | 131059 | 173016.66 | 70347 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 11 | 38 | Public Works | Stormwater | General Upgrades |  |  | 9/22/2020 16:52 |  |  | No
Public Works | P12618 | DOLPHIN ISLES B-14 SEWER BASIN REHABILIATION | This project is for the rehabilitation of the Dolphin Isles B-14 Sewer basin located in the Dolphin Isles neighborhood. This is a high priority project because of the recent sanitary sewer overflows resulting in the release of untreated wastewater in the Cityâ€™s waterways. The project scope will include pre and post television survey with closed circuit television (CCTV) video rehabilitation of the mainline sewers manholes and service laterals and in-house project management fees. | 1338 | Jose Colmenares |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | Yes |  | 495 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 2657900.53 | 86769 | 0 | 0 | 2571131.53 | PLANNING |  |  | 12/3/2020 0:00 | 10/1/2023 0:00 |  | DESIGN |  |  | 10/1/2023 0:00 | 9/30/2024 0:00 |  | BIDDING |  |  | 10/1/2024 0:00 | 3/31/2025 0:00 |  | CONST |  |  | 4/1/2025 0:00 | 3/31/2027 0:00 |  | WARRANTY |  |  | 4/1/2027 0:00 | 3/31/2028 0:00 | [6 empty] | 2657900.53 | 178648.77 | 73738 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 68 | Public Works | Water Sewer | Study/Investigation | No | No | 9/29/2020 10:00 |  |  | No
Public Works | P12619 | BAYVIEW DRIVE 16 FORCE MAIN TO PUMP STATION B-14 | This project is for the replacement of 3450 linear feet of 12-inch diameter sewer force main with a 16-inch diameter sewer force main. The force main extends from Bayview Drive and NE 26th Court to Pump Station B-14. | 894 | Steve Hillberg |  |  | Steve Hillberg | PBS | PBS | 2 | Design | 37 | Water Sewer | No |  | 495 | Yes | Yes | -1 | -1 | 0 | 0 | [10 empty] | 3730000 | 95579.39 | 81528.14 | 0 | 3552892.47 | PLANNING |  |  | 12/3/2020 0:00 | 3/22/2021 0:00 |  | DESIGN |  |  | 3/23/2021 0:00 | 3/31/2023 0:00 |  | BIDDING |  |  | 3/31/2023 0:00 | 7/31/2023 0:00 |  | CONST |  |  | 7/31/2023 0:00 | 4/6/2023 0:00 |  | WARRANTY |  |  | 4/6/2023 0:00 | 4/6/2024 0:00 | [6 empty] | 3730000 | 109977.89 | 73589 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation | No | No | 9/29/2020 10:01 |  |  | No
Public Works | P12637 | ADA PARKING LOT IMPROVEMENTS - UTILITIES ADMINISTRATION BUILDING | This project is to provide modifications to the existing parking spaces area to provide ADA access to the Fiveash Water Treatment Plant Facility and Administration Building. | 687 | Alex Rio |  |  | Raymond Nazaire | PBS | PBS | 15 | Complete | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 100000 | 101409.14 | -1409.14 | 0 | 0 | PLANNING | [5 empty] | DESIGN |  |  | 3/17/2021 0:00 | 4/30/2021 0:00 |  | BIDDING |  |  | 4/30/2021 0:00 | 6/15/2021 0:00 |  | CONST |  |  | 6/15/2021 0:00 | 3/30/2023 0:00 |  | WARRANTY |  |  | 3/30/2023 0:00 | 3/30/2024 0:00 | [6 empty] | 100000 | 152110.64 | 69728 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 42 | Public Works | Engineering | ADA Compliance | No | No | 2/16/2021 10:34 |  |  | No
Public Works | P12641 | CASTLE HARBOR ISLE BRIDGE DESIGN AND REPLACEMENT | This project is for the design and construction of the Castle Harbor Isle Bridge. On March 11 2021 following the inspection of the Castle Harbor Isle Bridge staff recommended the closure of the westbound lane of the bridge. Upon further inspection it was determined that there were two structurally weak points on the bridge one in the center and one near the edge. Due to the risk of failure staff has recommended the bridge be replaced. The project scope will include the immediate repair of the two structurally weak points on the bridge and the design construction and in-house project management fees for the bridge replacement. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 2 | Design | 19 | Bridge | No |  | 331 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 2000000 | 416385.23 | 9498 | 0 | 1574116.77 | PLANNING |  |  | 7/12/2021 0:00 | 10/22/2021 0:00 |  | DESIGN |  |  | 12/4/2023 0:00 | 11/22/2024 0:00 |  | BIDDING |  |  | 11/25/2024 0:00 | 2/21/2025 0:00 |  | CONST |  |  | 2/24/2025 0:00 | 2/24/2026 0:00 |  | WARRANTY |  |  | 2/25/2026 0:00 | 2/25/2027 0:00 | [6 empty] | 2000000 | 573391.67 | 73489 | 2/12/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 4/15/2021 16:29
Parks and Rec | P12654 | HARBORDALE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Harbordale Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include addition of accessible benches addition of yellow tactile ground surface indicators accessible parking spot accessible route to exercise equipment and addition of accessible picnic tables. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 355000 | 0 | 0 | 0 | 355000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 355000 | 1349.635 | 72955 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:24
Parks and Rec | P12661 | LINCOLN PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Lincoln Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include picnic tables pavilion chess/checker tables and playground entrance access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 261000 | 0 | 0 | 0 | 261000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 261000 | 3260.68 | 72961 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:27
Parks and Rec | P12665 | PALM AIRE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Palm Aire Village Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches picnic tables water fountain access accessible path to picnic area playground and playcourts. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 212500 | 0 | 0 | 0 | 212500 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 212500 | 3982.195 | 72986 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:28
Parks and Rec | P12678 | TWIN LAKES NORTH PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Twin Lakes North Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches replacement picnic tables replacement water fountain replacement pathways and playground accessibility.The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 304300 | 275 | 0 | 0 | 304025 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 304300 | 549.5 | 73000 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:34
Public Works | P12694 | CITY HALL STRUCTURAL IMPROVEMENTS | This project is for work associated with concrete restoration/repair work at city hall facility. | 884 | Raymond Nazaire |  |  | Raymond Nazaire | PBS | PBS | 6 | Construction | 22 | CityFacilities | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 142734 | 97340 | 40817 | 0 | 4577 | PLANNING |  |  | 10/1/2016 0:00 | 10/31/2016 0:00 |  | DESIGN |  |  | 11/1/2016 0:00 | 4/13/2017 0:00 |  | BIDDING |  |  | 11/6/2020 0:00 | 1/1/2021 0:00 |  | CONST |  |  | 2/1/2022 0:00 | 9/30/2023 0:00 |  | WARRANTY |  |  | 9/30/2023 0:00 | 9/30/2024 0:00 | [6 empty] | 142734 | 113402.75 | 71233 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 23 | 38 | Public Works | General Services | General Upgrades |  | No | 8/5/2021 16:20 |  |  | No
Public Works | P12695 | HENDRICKS ISLE SEAWALLS REPLACEMENT PROJECT | This project replaces two existing substandard municipal seawalls along Hendricks Isle. The first seawall is 260-feet between 505 and 535 Hendricks Isle and the other is 60-feet at the north end of Hendricks Isle. The new seawalls are designed to a top wall elevation of 5.0 (NAVD88) in accordance with the City seawall ordinance. This project is current under construction by Ebsary Foundation with an estimated completion date of February 2023. | 1336 | Scarlet Del Valle |  |  | Rares Petrica | PBS | PBS | 8 | Warranty | 33 | Seawalls | Yes |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 |  | 1471590 |  |  |  |  | 1471590 |  |  | 899436 | 1533405 | 1142069.18 | 0 | 0 | 391335.82 | PLANNING |  |  | 7/1/2020 0:00 | 6/30/2021 0:00 |  | DESIGN |  |  | 7/1/2021 0:00 | 2/28/2022 0:00 |  | BIDDING |  |  | 1/1/2022 0:00 | 6/20/2022 0:00 |  | CONST |  |  | 6/21/2022 0:00 | 2/15/2023 0:00 |  | WARRANTY |  |  | 2/16/2023 0:00 | 2/15/2024 0:00 |  |  | 1471590 |  |  |  | 1533405 | 1255612.43 | 73739 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No |  | 8/25/2021 9:19 |  |  | No
Public Works | P12700 | PLANT A STORMWATER TREATMENT FACILITY UPGRADES | This project will provide upgrades addressing environmental sustainability and stormwater issues for the Plant A facility site. These upgrades include new stormwater infrastructure recycling debris collection and water quality treatment. | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 409 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 510302 | 22908 | 69070 | 0 | 418324 | PLANNING |  |  | 10/1/2021 0:00 | 12/31/2021 0:00 |  | DESIGN |  |  | 7/14/2023 0:00 | 4/12/2024 0:00 |  | BIDDING |  |  | 4/13/2024 0:00 | 6/10/2024 0:00 |  | CONST |  |  | 6/11/2024 0:00 | 12/10/2024 0:00 |  | WARRANTY |  |  | 12/11/2024 0:00 | 12/10/2025 0:00 | [6 empty] | 510302 | 36713.52 | 73234 | 2/6/2024 0:00 | 2/6/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 38 | Public Works | Stormwater | General Upgrades |  |  | 9/15/2021 9:37 |  |  | No
Public Works | P12706 | TAXIWAYS B & G REALIGNMENT | This project provides for the design and construction of the re -alignment of taxiways Bravo and Quebec. These taxiways will be demolished and re-constructed as perpendicular taxiways to runway 9-27 to conform to current Federal Aviation Administration (FAA) design standards. New light-emitting-diode (LED) taxiway edge lights and guidance signs will be installed as well as in-ground and elevated Runway Guard Light units at the hold-short lines. The Airport Light and Control Monitoring (ALCM) system will also be modified with the new taxiway configuration. | 865 | Khant Myat |  |  | Khant Myat | PBS | PBS | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 433130 | 10661 | 0 | 0 | 422469 | PLANNING |  |  | 7/23/2022 0:00 | 8/24/2022 0:00 |  | DESIGN |  |  | 8/25/2022 0:00 | 2/25/2023 0:00 |  | BIDDING |  |  | 2/26/2023 0:00 | 6/26/2023 0:00 |  | CONST |  |  | 6/27/2023 0:00 | 2/23/2024 0:00 |  | WARRANTY |  |  | 2/24/2024 0:00 | 2/25/2025 0:00 | [6 empty] | 433130 | 21412.25 | 69911 | 6/30/2023 0:00 |  | STATUS | Yes | Yes | 8 | 9 | 36 | Public Works | Airport | Replacement |  |  | 9/15/2021 9:39 |  |  | No
Public Works | P12707 | RUNWAY 13-31 PAVEMENT SEALING | This project provides for the design and construction of the pavement sealing of runway 13-31 and its taxiway connectors. The project will also include pavement striping. | 865 | Khant Myat |  |  | Khant Myat | PBS | PBS | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 241280 | 19384 | 0 | 0 | 221896 | PLANNING |  |  | 7/23/2022 0:00 | 1/24/2023 0:00 |  | DESIGN |  |  | 3/1/2023 0:00 | 5/31/2023 0:00 |  | BIDDING |  |  | 6/1/2023 0:00 | 10/4/2023 0:00 |  | CONST |  |  | 10/11/2023 0:00 | 4/10/2024 0:00 |  | WARRANTY |  |  | 4/11/2024 0:00 | 4/12/2025 0:00 | [6 empty] | 241280 | 38812.75 | 69912 | 6/30/2023 0:00 |  | STATUS | Yes | Yes | 8 | 9 | 43 | Public Works | Airport | Rehabilitation |  |  | 9/15/2021 9:39 |  |  | No
Public Works | P12708 | RUNWAY 9 RUN-UP RELOCATION & SOUTH END TAXIWAYS | This project combines P12522-Runway 9 Run-Up Area (South) and FY 20200889-Runway 9 Taxiway Intersection Improvements. The project is for the design and construction of the run -up area and the installation of a blast fence at the western end of Runway 9. In addition this project is to design the re-alignment of taxiways Echo and Juliet on the southern end of Runway 9. The taxiways will be extended into perpendicular taxiways. The project will also include the milling and resurfacing of taxiway Echo. New asphalt striping sodding and light -emitting-diode (LED) edge-lights and guidance signs will be installed. This project is partially funded by the Federal Aviation Administration (FAA) grant for approx. 90% reimbursement of the eligible project costs and a grant from Florida Department | 865 | Khant Myat |  |  | Khant Myat | PBS | PBS | 4 | Bidding | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 312196 | 38246.97 | 221913.74 | 0 | 52035.29 | PLANNING |  |  | 6/2/2021 0:00 | 9/16/2021 0:00 |  | DESIGN |  |  | 4/1/2022 0:00 | 8/1/2021 0:00 |  | BIDDING |  |  | 8/2/2022 0:00 | 1/6/2023 0:00 |  | CONST |  |  | 1/9/2023 0:00 | 3/8/2024 0:00 |  | WARRANTY |  |  | 3/9/2024 0:00 | 3/10/2025 0:00 | [6 empty] | 312196 | 73845.72 | 71862 | 10/25/2023 0:00 |  | STATUS | Yes | Yes | 8 | 9 | 34 | Public Works | Airport | New Construction |  |  | 9/15/2021 9:39 |  |  | No
Public Works | P12709 | BAYVIEW DR. FROM SUNRISE BLVD.TO OAKLAND PARK BLV | This project is for the installation of new stormwater infrastructure and tidal control systems to address documented flooding issues along Bayview Drive from Sunrise Boulevard to Oakland Park Boulevard. Potential conceptual design elements may consist of new and/or improved swale areas drainage structures drainage piping tidal value installation and sod restoration. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 470 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 809190 | 80587.09 | 2446.1 | 0 | 726156.81 | PLANNING |  |  | 10/1/2021 0:00 | 12/30/2022 0:00 |  | DESIGN |  |  | 1/2/2023 0:00 | 3/4/2024 0:00 |  | BIDDING |  |  | 3/5/2024 0:00 | 5/6/2024 0:00 |  | CONST |  |  | 5/7/2024 0:00 | 7/8/2024 0:00 |  | WARRANTY |  |  | 7/9/2024 0:00 | 7/9/2025 0:00 | [6 empty] | 809190 | 108776.145 | 73758 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/15/2021 9:39 |  |  | No
Public Works | P12710 | NW 21ST AVENUE PIPE REHABILITATION | This project is for the rehabilitation of 1450 liner feet of 54-inch reinforced concrete pipe located along NW 21st Avenue between Sistrunk Boulevard/NW 6th Street and the New River using trenchless concrete spin casting techniques or other trenchless technology methods. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | Yes |  | 470 | Yes | Yes | 0 | 0 | -1 | 0 | [6 empty] | 1567392.8 |  |  |  | 1210000 | 217917.75 | 874459.28 | 0 | 117622.97 | PLANNING |  |  | 10/1/2021 0:00 | 12/31/2021 0:00 |  | DESIGN |  |  | 1/3/2022 0:00 | 8/31/2023 0:00 |  | BIDDING |  |  | 9/1/2023 0:00 | 1/5/2024 0:00 |  | CONST |  |  | 1/8/2024 0:00 | 3/31/2024 0:00 |  | WARRANTY |  |  | 4/1/2024 0:00 | 4/1/2025 0:00 |  |  | 1567392.8 |  |  |  | 1210000 | 249839.77 | 73759 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 43 | Public Works | Stormwater | Rehabilitation |  |  | 9/15/2021 9:40 |  |  | No
Public Works | P12711 | SW 4TH AVE. - NUGENT AVE. TIDAL VALVES REPLACEMENT | This project is for the installation of tidal valves #11-19 and other stormwater infrastructure to alleviate tidal flooding between SE 4th Avenue and Nugent Avenue in downtown Fort Lauderdale. | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 305000 | 8118 | 0 | 0 | 296882 | PLANNING |  |  | 10/1/2021 0:00 | 12/31/2021 0:00 |  | DESIGN |  |  | 12/31/2021 0:00 | 4/1/2022 0:00 |  | BIDDING |  |  | 4/1/2021 0:00 | 7/1/2022 0:00 |  | CONST |  |  | 7/1/2022 0:00 | 12/31/2022 0:00 |  | WARRANTY |  |  | 12/31/2022 0:00 | 12/31/2023 0:00 | [6 empty] | 305000 | 16236 | 71729 | 10/20/2023 0:00 | 10/20/2023 0:00 | STATUS | Yes | Yes | 8 | 11 | 90 | Public Works | Stormwater | Master Plans |  |  | 9/15/2021 9:40 |  |  | No
Public Works | P12712 | SE 5TH AVE - SE 15TH AVE TIDAL VALVES REPLACEMENT | This project is for the installation of tidal valves #43-54 and other stormwater infrastructure to alleviate tidal flooding between SE 5th Avenue and SE 15th Avenue in downtown Fort Lauderdale. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 220000 | 7929 | 0 | 0 | 212071 | PLANNING |  |  | 10/1/2021 0:00 | 9/30/2022 0:00 |  | DESIGN |  |  | 10/3/2022 0:00 | 3/4/2024 0:00 |  | BIDDING |  |  | 3/5/2024 0:00 | 5/6/2024 0:00 |  | CONST |  |  | 5/7/2024 0:00 | 7/8/2024 0:00 |  | WARRANTY |  |  | 7/9/2024 0:00 | 7/9/2025 0:00 | [6 empty] | 220000 | 22500.84 | 73760 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 90 | Public Works | Stormwater | Master Plans |  |  | 9/15/2021 9:40
Public Works | P12713 | SE 5TH AVE - ANDREWS AVE TIDAL VALVES REPLACEMENT | Evaluation was done to look at the need for tidal valves to alleviate tidal flooding between SE 5th Avenue and South Andrews Avenue in downtown Fort Lauderdale. This project addresses tidal flooding south of intersection of SE 4th Street and Riverwalk North. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 292000 | 12683 | 81650.05 | 0 | 197666.95 | PLANNING |  |  | 10/1/2021 0:00 | 9/30/2022 0:00 |  | DESIGN |  |  | 10/1/2022 0:00 | 7/31/2023 0:00 |  | BIDDING | [5 empty] | CONST |  |  | 3/1/2024 0:00 | 5/31/2024 0:00 |  | WARRANTY |  |  | 5/31/2024 0:00 | 5/31/2025 0:00 | [6 empty] | 292000 | 27494.69 | 73744 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 90 | Public Works | Stormwater | Master Plans |  |  | 9/15/2021 9:40 |  |  | No
Public Works | P12714 | NUGENT AVE - ANDREWS AVE TIDAL VALVES REPLACEMENT | This project is for the installation of tidal valves #20-29 and other stormwater infrastructure to alleviate tidal flooding between Nugent Avenue and South Andrews Avenue in downtown Fort Lauderdale . | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 212000 | 4320 | 0 | 0 | 207680 | PLANNING |  |  | 10/1/2021 0:00 | 12/31/2021 0:00 |  | DESIGN |  |  | 12/31/2021 0:00 | 4/1/2022 0:00 |  | BIDDING |  |  | 4/1/2022 0:00 | 7/1/2022 0:00 |  | CONST |  |  | 7/1/2022 0:00 | 12/31/2022 0:00 |  | WARRANTY |  |  | 12/31/2022 0:00 | 12/31/2023 0:00 | [6 empty] | 212000 | 8640 | 71730 | 10/20/2023 0:00 | 10/20/2023 0:00 | STATUS | Yes | Yes | 8 | 11 | 90 | Public Works | Stormwater | Master Plans |  |  | 9/15/2021 9:41 |  |  | No
Public Works | P12718 | MAUSOLEUMS-SUNSET MEMORIAL GARDENS CEMETERY | This project funds the construction of three mausoleums totaling 476 crypts at Sunset Memorial Gardens located at 3201 NW 19th Street Fort Lauderdale FL 33311. | 885 | Connie Hayman |  |  | Raymond Nazaire |  | PBS | 4 | Bidding | 22 | CityFacilities | No |  | 430 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 2271329 | 34563.05 | 0 | 1100160 | 1136605.95 | PLANNING |  |  | 6/1/2021 0:00 | 11/1/2021 0:00 |  | DESIGN |  |  | 11/1/2021 0:00 | 4/28/2023 0:00 |  | BIDDING |  |  | 5/1/2023 0:00 | 4/23/2024 0:00 |  | CONST |  |  | 4/24/2024 0:00 | 1/7/2025 0:00 |  | WARRANTY |  |  | 1/8/2025 0:00 | 1/8/2026 0:00 | [6 empty] | 2271329 | 90196.61 | 73490 | 2/12/2024 0:00 |  | STATUS | Yes | No | 8 | 15 | 34 | Public Works | Cemeteries | New Construction |  |  | 9/15/2021 9:42
Public Works | P12719 | MELROSE MANORS NEIGHBORHOOD IMPROVEMENTS | This project includes design permitting and bidding assistance for proposed stormwater improvements within the Melrose Manors Neighborhood. The proposed stormwater improvements include: stormwater structures & piping swales water quality structures and pump stations. In addition to stormwater improvements; pavement & landscaping restoration and waterline & sewerline relocation would be included. This project was added to the original 7 priority neighborhoods that made up Phase 1 of the Stormwater Masterplan Program due to sever flooding sustained in during storm ETA. The design and permitting will be partially funded by a $1 million FDEP grant. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 473 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 4462542 | 1204461.89 | 1111896.37 | 0 | 2146183.74 | PLANNING |  |  | 12/20/2021 0:00 | 1/31/2023 0:00 |  | DESIGN |  |  | 2/1/2023 0:00 | 8/1/2025 0:00 |  | BIDDING |  |  | 8/4/2025 0:00 | 2/4/2026 0:00 |  | CONST |  |  | 2/5/2026 0:00 | 2/7/2028 0:00 |  | WARRANTY |  |  | 2/8/2028 0:00 | 2/8/2029 0:00 | [6 empty] | 4462542 | 1281684.65 | 73761 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/17/2021 14:37 |  |  | Yes
Public Works | P12726 | MERLE FOGG SEAWALL REPLACEMENT | This project replaces a collapsed substandard municipal seawall along Merle Fogg Park. The portion of seawall to be replaced is approximately 130 linear feet. The new seawall is designed to a top wall elevation of 5.0 (NAVD88) in accordance with the City seawall ordinance. This project will be constructed by Ebsary Foundation with an estimated completion date of Spring 2024. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 33 | Seawalls | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | 24 |  | 186133.91 |  |  | 1208592.91 | 1022459 |  |  |  | 1556902.55 | 1080229.79 | 362898.41 | 84237.31 | 29537.04 | PLANNING |  |  | 9/1/2021 0:00 | 12/12/2021 0:00 |  | DESIGN | 12/13/2021 0:00 | 5/30/2022 0:00 | 12/13/2021 0:00 | 9/8/2022 0:00 |  | BIDDING | 6/1/2022 0:00 | 12/31/2022 0:00 | 9/8/2022 0:00 | 9/4/2023 0:00 |  | CONST | 1/1/2023 0:00 | 8/7/2023 0:00 | 9/5/2023 0:00 | 5/16/2024 0:00 |  | WARRANTY | 8/8/2023 0:00 | 8/8/2024 0:00 | 5/17/2024 0:00 | 5/17/2025 0:00 |  |  | 1022459 | 186133.91 | 1208592.91 | 24 | 1556902.55 | 1131613.82 | 73780 | 3/6/2024 0:00 | 3/6/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No | No | 10/15/2021 15:36 |  |  | No
Public Works | P12728 | SOUTHEAST ISLES SEAWALL REPLACEMENT PROJECT | This project is for the replacement of approximately 790 linear feet of existing seawalls along East Las Olas Blvd. and along SE 10th Street. The seawalls are #12 13 14 30 and 36 as identified in the City's Seawall Masterplan. The new seawalls will be constructed of marine grade steel sheet-piles with a concrete cap set at an elevation of 5.0 NAVD88 per the City's new seawall ordinance.The project has been awarded to Poseidon Engineering for construction which is estimated to begin in July 2023. | 1336 | Scarlet Del Valle |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 33 | Seawalls | No |  | 470 | Yes | Yes | 0 | -1 | 0 | -1 | [6 empty] | 2954062.01 |  |  |  | 4071581 | 2311265.48 | 1192820.54 | 0 | 567494.98 | PLANNING |  |  | 4/1/2020 0:00 | 6/30/2021 0:00 |  | DESIGN |  |  | 7/1/2021 0:00 | 3/31/2022 0:00 |  | BIDDING |  |  | 4/1/2022 0:00 | 5/30/2023 0:00 |  | CONST |  |  | 7/27/2023 0:00 | 7/31/2024 0:00 |  | WARRANTY |  |  | 8/1/2024 0:00 | 7/31/2025 0:00 |  |  | 2954062.01 |  |  |  | 4071581 | 2399376.26 | 73740 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 36 | Public Works | Stormwater | Replacement | No | No | 10/29/2021 15:35 |  |  | No
Public Works | P12730 | SWING BRIDGE 865748 ELECTRICAL AND MECHANICAL REHABILITATIONS | The scope of the work consists of the cleaning and rust removal from the mechanical gears of the swing bridge and the relocation of the electrical box attached to the bridge. | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PBS | PBS | 8 | Warranty | 19 | Bridge | No |  |  | Yes | Yes | 0 | -1 | -1 | 0 |  | 262800 | [7 empty] | 300000 | 302000 | 294870.26 | 10000 | 0 | -2870.26 | PLANNING |  |  | 4/1/2021 0:00 | 4/30/2021 0:00 |  | DESIGN |  |  | 11/1/2021 0:00 | 11/15/2021 0:00 |  | BIDDING |  |  | 1/3/2022 0:00 | 1/3/2023 0:00 |  | CONST |  |  | 1/3/2023 0:00 | 2/23/2023 0:00 |  | WARRANTY |  |  | 2/23/2023 0:00 | 2/23/2024 0:00 | [6 empty] | 302000 | 338676.26 | 73639 | 2/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No | No | 11/19/2021 15:28 |  |  | No
Public Works | P12734 | 2941 NW 19 STREET FACILITY REHABILITATION | This project is intended to rehabilitate the property at 2941 NW 19 Street to be establishedas a career center. The facility will include a technology room that will be equipped withcomputers high-speed internet and telephones to easily access employmentopportunities and remote learning. It is expected that this will revitalize the affected laborforce with career development and training workshops to provide neighbors with acompetitive advantage in their search for employment. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | CM | PBS | 11 | Hold | 22 | CityFacilities | No | CM | 331 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 21479 | 24224 | 13525 | 0 | -16270 | PLANNING |  |  | 3/1/2022 0:00 | 11/4/2022 0:00 |  | DESIGN |  |  | 11/7/2022 0:00 | 2/17/2023 0:00 |  | BIDDING |  |  | 2/20/2023 0:00 | 5/26/2023 0:00 |  | CONST |  |  | 5/29/2023 0:00 | 10/4/2023 0:00 |  | WARRANTY |  |  | 10/5/2023 0:00 | 10/5/2024 0:00 | [6 empty] | 21479 | 50058.38 | 73354 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No |  | 1/14/2022 12:01 |  |  | No
Public Works | P12743 | OSCEOLA CREEK RESTORATION PROJECT | The project consists of the restoration of the Osceola Creek from SW 32th Place to Marina Blvd. The restoration includes removal of debris garbage and other impediments to normal drainage. Maintenance dredging of accumulated bottom sediments removal of exotic tree species. and mangrove trimming is also included as part of the scope for this project.This project is part of the in-kind water quality consent order. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 31 | Canals | No |  | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [6 empty] | 6186100 |  |  |  | 7375592.94 | 1173352 | 5403060 | 0 | 799180.94 | PLANNING |  |  | 9/6/2018 0:00 | 9/5/2019 0:00 |  | DESIGN |  |  | 9/6/2019 0:00 | 12/31/2022 0:00 |  | BIDDING |  |  | 1/1/2023 0:00 | 9/4/2023 0:00 |  | CONST |  |  | 9/5/2023 0:00 | 3/31/2024 0:00 |  | WARRANTY |  |  | 3/31/2024 0:00 | 4/30/2025 0:00 |  |  | 6186100 |  |  |  | 7375592.94 | 1223666.56 | 73746 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 69 | 91 | Public Works | Environmental Services | Canal Dredging | Yes |  | 2/17/2022 15:25 |  |  | No
Public Works | P12745 | RIVER OAKS STORMWATER PUMP STATIONS | This project is for the construction of (2) new stormwater pump stations within the River Oaks Preserve that will serve the Edgewood and River Oaks Stormwater infrastructure. The project was awarded to Ric-Man Construction on December 6th 2022 and construction will take place over the next 2 years. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | No |  | 470 | Yes |  | 0 | 0 | 0 | -1 | [6 empty] | 10338284 |  |  |  | 11500000 | 4751198.59 | 5617967.71 | 0 | 1130833.7 | PLANNING |  |  | 4/1/2021 0:00 | 10/29/2021 0:00 |  | DESIGN |  |  | 11/1/2021 0:00 | 6/30/2022 0:00 |  | BIDDING |  |  | 7/1/2022 0:00 | 6/11/2023 0:00 |  | CONST |  |  | 6/12/2023 0:00 | 11/14/2024 0:00 |  | WARRANTY |  |  | 11/15/2024 0:00 | 11/15/2025 0:00 |  |  | 10338284 |  |  |  | 11500000 | 4825760.31 | 73762 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 3/25/2022 12:21 |  |  | Yes
Public Works | P12749 | NE 14 STREET STORMWATER IMPROVEMENTS | The drainage system in this area is undersized and does not have a positive outfall to the waterway. As part of this project the system will be upsized and connected to an existing outfall to provide more efficient drainage attenuation. | 793 | Sayd Hussain | 793 | Sayd Hussain | Rares Petrica | PBS | PBS | 8 | Warranty | 36 | Stormwater | No |  | 470 | Yes | Yes | -1 | 0 | 0 | 0 | [6 empty] | 349000 |  | 250000 |  | 349123 | 302704.44 | 45274.93 | 0 | 1143.63 | PLANNING |  |  | 2/1/2022 0:00 | 9/1/2022 0:00 |  | DESIGN |  |  | 9/2/2022 0:00 | 3/1/2023 0:00 |  | BIDDING |  |  | 3/15/2023 0:00 | 5/15/2023 0:00 |  | CONST |  |  | 5/30/2023 0:00 | 8/11/2023 0:00 |  | WARRANTY |  |  | 10/1/2023 0:00 | 10/1/2024 0:00 |  |  | 349000 |  |  |  | 349123 | 334472.42 | 71731 | 1/22/2024 0:00 | 1/22/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction | No | No | 4/15/2022 11:41 |  |  | No
Parks and Rec | P12759 | GUTHRIE BLAKE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Guthrie Blake Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include native planting playground improvements security lighting ADA pathways ADA benches park entrance improvements ADA bike rack garbage can relocation and addition ADA features in playground. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 520000 | 0 | 0 | 0 | 520000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 520000 | 1017.6525 | 73014 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 11:04 |  |  | Yes
Public Works | P12765 | NEW WATER TREATMENT PLANT - PROSPECT LAKE WATER TREATMENT PLANT | New Water Treatment Plant. Owners rep services for planning design and construction of a new water treatment plant at the prospect wellfield. Prospect Lake Water Treatment Plant. | 1212 | Daniel Fisher |  |  | Daniel Fisher | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 450 | Yes | Yes | -1 | -1 | -1 | -1 | [6 empty] | 540750000 |  |  |  | 560747774 | 25970140.36 | 448483095.7 | 0 | 86294537.91 | PLANNING |  |  | 1/1/2022 0:00 | 3/15/2023 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  | 3/16/2023 0:00 | 9/12/2026 0:00 |  | WARRANTY |  |  | 9/12/2026 0:00 | 9/12/2056 0:00 |  |  | 540750000 |  |  |  | 560747774 | 26027376.64 | 73776 | 3/5/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No | No | 5/25/2022 10:30 |  |  | Yes
Transportation and Mobility | P12766 | COMMERCIAL ROAD PARKING IMPROVEMENTS | This project includesÂ the improvement of the parking lots on Commercial Boulevard. Â The parking lots need milling and resurfacing pavement marking drainage cleaningreplacement of curbing and ADA compliance. This project will be for the construction activities related to the improvements of the Commercial Boulevard parking lots. | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 4 | Bidding | 17 | Parking | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 3886904.09 | 149855.5 | 56048.5 | 3443814 | 237186.09 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 3886904.09 | 156260.44 | 73511 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 10 | 83 | 36 | Transportation and Mobility | Parking Systems | Replacement | No | No | 5/26/2022 9:52 | No | No | Yes
Public Works | P12770 | FXE DECORATIVE STREET POSTS - PHASE 2 | Design and construction of new decorative colored and precast concrete poles. The new poles will include a decorative airport name/logo. New concrete curbing will be installed in areas where the new posts do not meet the minimum separation distance from the roadway. This project is the phase 2 of the original project in the same area around the Executive Airport. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 2 | Design | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 400000 | 21801 | 0 | 0 | 378199 | PLANNING |  |  | 5/3/2022 0:00 | 9/1/2021 0:00 |  | DESIGN |  |  | 9/5/2022 0:00 | 12/14/2022 0:00 |  | BIDDING |  |  | 1/9/2023 0:00 | 5/31/2023 0:00 |  | CONST |  |  | 6/1/2023 0:00 | 9/20/2023 0:00 |  | WARRANTY |  |  | 9/21/2023 0:00 | 9/22/2024 0:00 | [6 empty] | 400000 | 44217.81 | 69925 | 6/30/2023 0:00 |  | STATUS | Yes | Yes | 8 | 9 | 34 | Public Works | Airport | New Construction |  |  | 6/8/2022 8:36 |  |  | No
Public Works | P12785 | NW 15 AVE STORMWATER IMPR FXE | Design and construction new stormwater improvements system on NW 15 Avenue between South Perimeter Road and NW 56th Street. The project will include survey design bidding and construction. The project will consist of installation of exfiltration trenches with perforated pipes catch basin swales sod pavement and pavement markings. The project may also include regrading of existing swale and roadway. | 865 | Khant Myat |  |  | Khant Myat | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 468 | No | No | 0 | 0 | 0 | 0 | [10 empty] | 115000 | 106624.2 | 5078 | 0 | 3297.8 | PLANNING |  |  | 7/6/2022 0:00 | 10/26/2022 0:00 |  | DESIGN |  |  | 11/4/2022 0:00 | 6/21/2023 0:00 |  | BIDDING |  |  | 6/22/2023 0:00 | 12/13/2023 0:00 |  | CONST |  |  | 1/8/2024 0:00 | 8/16/2024 0:00 |  | WARRANTY |  |  | 8/17/2024 0:00 | 8/18/2025 0:00 | [6 empty] | 115000 | 113660.7 | 70591 | 8/2/2023 0:00 | 8/2/2023 0:00 | STATUS | Yes | Yes | 8 | 56 | 34 | Public Works | Drainage | New Construction | No | No | 6/20/2022 14:36 |  |  | No
Public Works | P12786 | 3030 HOLIDAY DRIVE STORMWATER IMPROVEMENTS PROJECT | This project includes design permitting and construction of proposed stormwater improvements along Holiday Drive. The proposed stormwater improvements will include a full replacement and upsizing of a collapse outfall pipe and additional inlets to alleviate flooding. | 793 | Sayd Hussain | 793 | Sayd Hussain | Rares Petrica | PBS | PBS | 6 | Construction | 36 | Stormwater | No |  |  | Yes |  | 0 | 0 | 0 | -1 | [6 empty] | 656000 |  |  |  | 656000 | 500374.81 | 42322.09 | 0 | 113303.1 | PLANNING |  |  | 1/3/2022 0:00 | 8/16/2022 0:00 |  | DESIGN |  |  | 8/17/2022 0:00 | 12/16/2022 0:00 |  | BIDDING |  |  | 12/17/2022 0:00 | 3/1/2023 0:00 |  | CONST |  |  | 3/1/2023 0:00 | 9/30/2023 0:00 |  | WARRANTY |  |  | 10/1/2023 0:00 | 10/1/2024 0:00 |  |  | 656000 |  |  |  | 656000 | 559020.08 | 72968 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 34 | Public Works | Engineering | New Construction | No |  | 7/14/2022 16:11 | No | No | No
Public Works | P12790 | BAYVIEW DRIVE BRIDGE OVER LONGBOAT INLET | This project is for the replacement of the Bayview Drive bridge. This bridge is a 20-foot-long single span reinforced concrete slab bridge constructed in 1962. The 42-foot-wide bridge has a roadway width of 28.3 feet and carries two (2) lanes of traffic.Additionally it has two (2) 2.9-foot-wide sidewalks separated from the roadway by a raised curb in a residential neighborhood. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | No |  | 331 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 1235400 | 17040 | 0 | 0 | 1218360 | PLANNING |  |  | 10/13/2022 0:00 | 5/17/2024 0:00 |  | DESIGN |  |  | 5/20/2024 0:00 | 11/22/2024 0:00 |  | BIDDING |  |  | 2/15/2024 0:00 | 8/15/2024 0:00 |  | CONST |  |  | 8/16/2024 0:00 | 8/16/2025 0:00 |  | WARRANTY |  |  | 8/17/2025 0:00 | 8/17/2026 0:00 | [6 empty] | 1235400 | 36371.4 | 73492 | 2/12/2024 0:00 |  | STATUS | Yes | No | 8 | 25 | 36 | Public Works | Bridges | Replacement |  |  | 9/14/2022 13:29 |  |  | No
Public Works | P12791 | SE 13TH STREET BRIDGE | This project is for the repair/replacement of the SE 13th Street bridge. The bridge is a 180.5 foot long nine (9) span reinforced concrete double T-beam bridge constructed in 1952. The bridge has a roadway width of 21 feet and carries two (2) lanes of traffic in a residential neighborhood. There is a 2.5 foot sidewalk on the south side of the bridge. This bridge serves as the only entry point for residences east of the bridge. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 11 | Hold | 19 | Bridge | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 705185 | 0 | 0 | 0 | 705185 | PLANNING |  |  | 10/13/2022 0:00 | 10/6/2023 0:00 |  | DESIGN |  |  | 11/4/2024 0:00 | 11/5/2025 0:00 |  | BIDDING |  |  | 11/6/2025 0:00 | 2/20/2026 0:00 |  | CONST |  |  | 2/23/2026 0:00 | 2/23/2027 0:00 |  | WARRANTY |  |  | 2/24/2027 0:00 | 2/24/2027 0:00 | [6 empty] | 705185 | 916.56 | 73493 | 2/12/2024 0:00 |  | STATUS | No | No | 8 | 25 | 36 | Public Works | Bridges | Replacement |  |  | 9/14/2022 13:29 |  |  | No
Transportation and Mobility | P12792 | SUNRISE LANE DISTRICT STREETSCAPES | This project focuses on roadway improvements to the support the area's surrounding businesses. The scope of work includes widening the sidewalk area; improving nighttime visibility through pedestrian lighting roadway lighting and overhead festival lighting; realigning the street parking spots; landscaping; and installing entryway features to help create a unique destination feel for the district. These improvements will help attract visitors to the area by letting them know there are stores and restaurants within the area just off A1A including wayfinding features. |  |  |  |  | Karen Warfel | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 220800 | 37189.27 | 168954.31 | 0 | 14656.42 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 220800 | 42929.83 | 73004 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | 10 | 23 | 38 | Transportation and Mobility | General Services | General Upgrades |  |  | 9/14/2022 13:30 |  |  | No
Public Works | P12798 | DEEPWELL MECHANICAL INTEGRITY TESTING & PIPE REPLACEMENT | This project will replace aging above ground valves and pipes at the George T. Lohmeyer Wastewater Treatment Plant. | 1257 | Justin Murray |  |  | Miguel Arroyo | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 451 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 3450000 | 62615 | 172304 | 2000000 | 1215081 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 3450000 | 63164 | 67729 | 2/28/2023 0:00 |  | STATUS | Yes | Yes | 8 | 23 | 36 | Public Works | General Services | Replacement |  |  | 9/14/2022 13:33 |  |  | No
Public Works | P12799 | REHABILITATION/ REPLACEMENT OF 48 TO 54-INCH FORCE MAIN ON ALONG SE 9TH AVENUE AND 10TH AVENUE TO GTL | This project is for the rehabilitation or replacement of 19100 linear feet of 48-54 inch diameter sewer force main. The force main runs along SE 9th Avenue and 10th Avenue to the George T. Lohmeyer Wastewater Treatment Plant. | 1355 | Wilfredo Negron |  |  | William Power | PBS | PBS | 4 | Bidding | 23 | Utilities | No |  | 451 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 1382802 | 717792.1 | 669130.49 | 2700100 | -2704220.59 | PLANNING |  |  | 8/31/2022 0:00 | 10/16/2023 0:00 |  | DESIGN |  |  | 5/18/2023 0:00 | 10/20/2023 0:00 |  | BIDDING |  |  | 10/23/2023 0:00 | 7/29/2024 0:00 |  | CONST |  |  | 7/29/2024 0:00 | 6/18/2026 0:00 |  | WARRANTY |  |  | 6/18/2026 0:00 | 6/17/2027 0:00 | [6 empty] | 1382802 | 778676.356 | 73605 | 2/20/2024 0:00 | 2/20/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation | Yes |  | 9/14/2022 13:35 |  |  | No
Public Works | P12800 | GTL REACTOR REHABILITATION | This project will provide more efficient oxygen transfer by replacing mixers and rehabilitate concrete in the reactors at the George T. Lohmeyer Wastewater Treatment Plant (GTL). GTL currently has two reactors that have severe corrosions inside of them due to the current environment they are in. The mixers have been rebuilt once and will need to be fully replaced in the next three years. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 451 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 3303983 | 20068 | 0 | 0 | 3283915 | PLANNING |  |  | 10/31/2022 0:00 | 2/28/2024 0:00 |  | DESIGN |  |  | 2/15/2024 0:00 | 3/17/2025 0:00 |  | BIDDING |  |  | 3/18/2025 0:00 | 7/23/2025 0:00 |  | CONST |  |  | 7/24/2025 0:00 | 8/4/2026 0:00 |  | WARRANTY |  |  | 8/5/2025 0:00 | 8/5/2026 0:00 | [6 empty] | 3303983 | 62820.55 | 73716 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation |  |  | 9/14/2022 13:36 |  |  | No
Public Works | P12802 | SW 29TH STREET SMALL WATERMAINS | This project funds a small water main replacement located at SW 29th Street from SW 9th Avenue through SW 12th Avenue. This project will replace existing water mains which are undersized and deteriorated with new 6-inch water mains. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 2 | Design | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 881005 | 24888 | 0 | 0 | 856117 | PLANNING |  |  | 4/3/2023 0:00 | 8/27/2023 0:00 |  | DESIGN |  |  | 8/28/2023 0:00 | 2/19/2024 0:00 |  | BIDDING |  |  | 2/20/2024 0:00 | 8/21/2024 0:00 |  | CONST |  |  | 8/22/2024 0:00 | 8/22/2025 0:00 |  | WARRANTY |  |  | 8/23/2025 0:00 | 8/23/2026 0:00 | [6 empty] | 881005 | 71187 | 73720 | 3/1/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/14/2022 13:37 |  |  | No
Public Works | P12803 | POINSETTIA DRIVE SMALL WATERMAIN IMPROVEMENTS | This project is for small water main improvements on Poinsettia Drive. This project will replace existing water mains which are undersized and deteriorated with approximately 14300 linear feet of 6-inch water mains. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 436313.31 | 31659 | 0 | 0 | 404654.31 | PLANNING |  |  | 4/3/2023 0:00 | 8/1/2023 0:00 |  | DESIGN |  |  | 8/2/2023 0:00 | 12/2/2023 0:00 |  | BIDDING |  |  | 12/3/2023 0:00 | 3/3/2024 0:00 |  | CONST |  |  | 3/4/2024 0:00 | 3/4/2025 0:00 |  | WARRANTY |  |  | 3/5/2025 0:00 | 3/5/2026 0:00 | [6 empty] | 436313.31 | 90993.12 | 73713 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation |  |  | 9/14/2022 13:37 |  |  | No
Public Works | P12805 | SMALL WATER MAIN ABANDONMENT - SE 25TH AVENUE | Abandon approximately 1100 linear feet of old 6-inch cast iron water main on SE 25th Avenue from 17th Street Ramp to SE 19th Place (Barbara Drive). Move all water services from the old 6-inch water main to the existing 8-inch water main. Abandon the 6-inch water main in place (cut cap grout). An option would be to pipe burst the main to maintain water main redundancy. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 2 | Design | 23 | Utilities | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 225000 | 62013.5 | 42532.5 | 0 | 120454 | PLANNING |  |  | 4/3/2023 0:00 | 9/20/2023 0:00 |  | DESIGN |  |  | 9/21/2023 0:00 | 4/29/2024 0:00 |  | BIDDING |  |  | 4/30/2024 0:00 | 7/30/2024 0:00 |  | CONST |  |  | 7/31/2024 0:00 | 7/31/2025 0:00 |  | WARRANTY |  |  | 8/1/2024 0:00 | 8/1/2025 0:00 | [6 empty] | 225000 | 123783.68 | 73714 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 70 | Public Works | Water Sewer | Demolition |  |  | 9/14/2022 13:38 |  |  | No
Public Works | P12806 | PUBLIC WORKS ADMIN BUILDING GENERATOR REPLACEMENT | This project is for the replacement of the Public Works Administration building generator. The current 600-kilo-watt emergency generator is 32 years old and has exceeded its useful life and repair parts are very difficult to obtain and costly. The old generator also does not meet new clean air act standards for diesel engines. The Public Works Administration Building is the center for Public Works Operations and houses an Emergency Operations Center that is critical for the command and control of utility operations during emergencies and natural disasters. | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 4 | Bidding | 23 | Utilities | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 830000 | 71324.5 | 13832.5 | 450000 | 294843 | PLANNING |  |  | 12/1/2022 0:00 | 2/10/2023 0:00 |  | DESIGN |  |  | 2/13/2023 0:00 | 10/31/2023 0:00 |  | BIDDING |  |  | 11/1/2023 0:00 | 4/30/2024 0:00 |  | CONST |  |  | 5/1/2024 0:00 | 10/31/2024 0:00 |  | WARRANTY |  |  | 10/31/2024 0:00 | 10/30/2025 0:00 | [6 empty] | 830000 | 146989.168 | 73709 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/14/2022 13:39 |  |  | No
Public Works | P12807 | PUMPING STATION D-34 EMERGENCY GENERATOR | This project is to design and install a new emergency generator and electrical equipment for waste water pumping station D-34. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 2 | Design | 23 | Utilities | No |  | 454 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 835000 | 22356.5 | 20302.5 | 0 | 792341 | PLANNING |  |  | 1/3/2023 0:00 | 2/10/2023 0:00 |  | DESIGN |  |  | 2/13/2023 0:00 | 1/1/2024 0:00 |  | BIDDING |  |  | 1/2/2024 0:00 | 4/30/2024 0:00 |  | CONST |  |  | 5/1/2024 0:00 | 10/31/2024 0:00 |  | WARRANTY |  |  | 11/1/2024 0:00 | 11/3/2025 0:00 | [6 empty] | 835000 | 68017.22 | 73717 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades |  |  | 9/14/2022 13:39 |  |  | No
Public Works | P12808 | NORTH ANDREWS FEC RAILWAY WATERMAIN REPLACEMENT | Replace approximately 400 linear feet (LF) of 16-inch water main at North Andrews Avenue and Florida East Coast (FEC) railway. | 1355 | Wilfredo Negron |  |  | William Power | PBS | PBS | 2 | Design | 23 | Utilities | No |  | 454 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 380366 | 70949.5 | 103292.5 | 0 | 206124 | PLANNING |  |  | 4/3/2023 0:00 | 8/27/2023 0:00 |  | DESIGN |  |  | 8/28/2023 0:00 | 4/24/2024 0:00 |  | BIDDING |  |  | 4/25/2024 0:00 | 10/24/2024 0:00 |  | CONST |  |  | 10/25/2024 0:00 | 10/25/2025 0:00 |  | WARRANTY |  |  | 10/26/2025 0:00 | 10/26/2026 0:00 | [6 empty] | 380366 | 115587.7 | 73621 | 2/21/2024 0:00 | 2/21/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/14/2022 13:41 |  |  | No
Public Works | P12809 | SE 15TH AVENUE FORCE MAIN REPLACEMENT | This project is for the replacement of 4780 linear feet (LF) of aging sewer force main which has experienced multiple failures in 2020 and 2021. | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 2 | Design | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | 0 | 0 | -1 | [10 empty] | 2500000 | 31842 | 434407 | 0 | 2033751 | PLANNING |  |  | 3/20/2023 0:00 | 8/27/2023 0:00 |  | DESIGN |  |  | 8/28/2023 0:00 | 4/28/2024 0:00 |  | BIDDING |  |  | 4/29/2024 0:00 | 10/26/2024 0:00 |  | CONST |  |  | 10/27/2024 0:00 | 4/20/2026 0:00 |  | WARRANTY |  |  | 4/21/2026 0:00 | 4/21/2027 0:00 | [6 empty] | 2500000 | 86596.44 | 73708 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/14/2022 13:41 |  |  | No
City Manager | P12811 | RUNWAY 9-27 PAVEMENT REHABILITATION PROJECT | This project provides for the planning design and construction of the pavement rehabilitation of Runway 9-27. The project would include the removal of existing pavement preparation of limerock subgrade and the construction of new pavement with new or recycled materials. The adjacent taxiway intersections will also be milled and re-surfaced as part of this project. New striping will be applied after the paving has been completed. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 4 | Bidding | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 172000 | 16516 | 0 | 0 | 155484 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 172000 | 33031.75 | 71860 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 43 | City Manager's Office | Airport | Rehabilitation |  |  | 9/14/2022 13:42 |  |  | No
City Manager | P12813 | ENVIRONMENTAL ASSESSMENT FOR RUNWAY 9 EXTENSION | This project provides funding for the City to conduct an Environmental Assessment (EA) for the proposed Runway 9 western extension. The EA will describe the need for the proposal alternatives environmental impacts of the proposed action and alternatives. The EA will also provide a listing of the agencies consulted to document the impacts anticipated. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 0 | 8968 | 0 | 0 | -8968 | PLANNING |  |  | 3/1/2022 0:00 | 1/2/2023 0:00 |  | DESIGN |  |  | 7/17/2023 0:00 |  |  | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 0 | 20680 | 71863 | 10/25/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 35 | City Manager's Office | Airport | Renovation |  |  | 9/14/2022 13:42 |  |  | No
City Manager | P12814 | AIRPORT ENTRY FEATURES | This project is for the construction of new entrance monument signs at various locations around the airport. The primary focus areas for sign placement are the key entry points to the Airport including Commercial Boulevard at NW 21st Avenue W. Prospect Road/W. Perimeter Road at NW 31st Street and Cypress Creek Road at NW 28th Way. These signs will have landscape features and an irrigation system where necessary. Additionally some signs will have a decorated fence around them and if feasible decorative lighting as well. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 350000 | 7000 | 0 | 0 | 343000 | PLANNING |  |  | 11/4/2022 0:00 | 7/17/2023 0:00 |  | DESIGN |  |  | 7/18/2023 0:00 | 12/13/2023 0:00 |  | BIDDING |  |  | 12/14/2023 0:00 | 5/14/2024 0:00 |  | CONST |  |  | 4/4/2024 0:00 | 9/25/2024 0:00 |  | WARRANTY |  |  | 9/26/2024 0:00 | 9/25/2025 0:00 | [6 empty] | 350000 | 13999.75 | 71865 | 10/25/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 38 | City Manager's Office | Airport | General Upgrades |  |  | 9/14/2022 13:43 |  |  | No
Public Works | P12815 | NE 32ND AVENUE AND NE 30TH STREET STORMWATER IMPROVEMENT | This project provides for the installation of additional stormwater infrastructure in the Lauderdale Beach neighborhood to help alleviate flooding from tidal events as well as to prevent permitted discharges from underground parking garages entering into the City's system. The scope of this project includes the design and construction of new stormwater infrastructure to alleviate historical flooding. Potential conceptual design may consist of new and/or improved swale areas drainage structures drainage piping and other stormwater control features. | 1336 | Scarlet Del Valle |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 751619 | 2745 | 0 | 0 | 748874 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 751619 | 7323.12 | 73733 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/14/2022 13:43 |  |  | No
Public Works | P12816 | RIVERLAND ROAD STORMWATER IMPROVEMENTS | This project is for the installation of additional stormwater infrastructure to help alleviate flooding along the stretch of Riverland Road closest to the South Fork New River. The project scope is for design and construction of new stormwater infrastructure to alleviate historical flooding. Potential conceptual design may consist of new and/or improved swale areas drainage structures drainage piping and other stormwater control features. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 949874 | 3386 | 0 | 0 | 946488 | PLANNING |  |  | 10/17/2022 0:00 | 7/31/2023 0:00 |  | DESIGN |  |  | 8/1/2023 0:00 | 2/29/2024 0:00 |  | BIDDING |  |  | 3/1/2024 0:00 | 6/30/2024 0:00 |  | CONST |  |  | 7/1/2024 0:00 | 7/31/2025 0:00 |  | WARRANTY |  |  | 8/1/2025 0:00 | 8/1/2026 0:00 | [6 empty] | 949874 | 6771.5 | 73747 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/14/2022 13:43 |  |  | No
Public Works | P12819 | NE 11TH COURT AND SEMINOLE DRIVE STORMWATER IMPROVEMENTS | This project is for the replacement of undersized stormwater infrastructure along NW 11th Court and Seminole Drive. This project's scope includes the design and construction of new stormwater infrastructure to alleviate historical flooding. Potential conceptual design may consist of new and/or improved swale areas drainage structures drainage piping and other stormwater control features. | 1336 | Scarlet Del Valle | 793 | Sayd Hussain | Rares Petrica | PBS | PBS | 8 | Warranty | 36 | Stormwater | No |  | 470 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 387280 | 369820.1 | 5626.65 | 0 | 11833.25 | PLANNING |  |  | 10/1/2022 0:00 | 11/1/2022 0:00 |  | DESIGN |  |  | 11/15/2022 0:00 | 3/30/2023 0:00 |  | BIDDING |  |  | 4/1/2023 0:00 | 6/15/2023 0:00 |  | CONST |  |  | 7/1/2023 0:00 | 10/30/2023 0:00 |  | WARRANTY |  |  | 11/1/2023 0:00 | 11/1/2024 0:00 | [6 empty] | 387280 | 387720.26 | 73734 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/14/2022 13:45 |  |  | No
Public Works | P12820 | HOLLY HEIGHTS DRIVE STORMWATER IMPROVEMENTS | This project is to provide stormwater improvements for Holly Heights Drive and adjacent streets in Middle River Terrace Neighborhood. The project's scope includes the design and construction of new stormwater infrastructure to alleviate historical flooding. Potential conceptual design may consist of new and/or improved swale areas drainage structures drainage piping and other stormwater control features. | 793 | Sayd Hussain |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 487182 | 18558 | 127642.53 | 0 | 340981.47 | PLANNING |  |  | 1/2/2023 0:00 | 5/19/2023 0:00 |  | DESIGN |  |  | 5/20/2023 0:00 | 11/29/2023 0:00 |  | BIDDING |  |  | 11/30/2023 0:00 | 1/15/2024 0:00 |  | CONST |  |  | 1/16/2024 0:00 | 7/5/2024 0:00 |  | WARRANTY |  |  | 7/6/2024 0:00 | 7/5/2025 0:00 | [6 empty] | 487182 | 44216.22 | 72967 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/14/2022 13:46 |  |  | No
Public Works | P12827 | SMALL WATER MAIN REPLACEMENT - SW 31ST AVENUE | This project is to replace approximately 10500 linear feet of 6-inch and 8-inch cast iron pipe installed in the 1950's and relocate the main from backyards to the City right-of-way. This project is located between Broward Blvd. and Riverland Road. | 1352 | Lamar Case |  |  | William Power | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 495 | Yes | Yes | 0 | 0 | -1 | -1 | [10 empty] | 3858449 | 0 | 0 | 0 | 3858449 | PLANNING |  |  | 4/5/2023 0:00 | 12/5/2023 0:00 |  | DESIGN |  |  | 12/5/2023 0:00 | 6/28/2024 0:00 |  | BIDDING |  |  | 7/1/2024 0:00 | 1/6/2025 0:00 |  | CONST |  |  | 1/7/2025 0:00 | 7/5/2025 0:00 |  | WARRANTY |  |  | 7/6/2025 0:00 | 7/6/2026 0:00 | [6 empty] | 3858449 | 23424 | 73715 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/14/2022 13:50 |  |  | Yes
Public Works | P12831 | PUMP STATION A-7 REDUNDANT FORCEMAIN | This project will fund the installation of a redundant 16-inch sewer force main for Pump Station (PS) A-7. The pipe will connect to the existing force main at PS A-7 run east along SW/SE 2 St to SE 8 Ave then south to SE 2 Court and then east where it will connect to the new 54-inch FM at the intersection of SE 2 Ct and SE 9 Ave. | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 495 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 2620000 | 0 | 0 | 0 | 2620000 | PLANNING |  |  | 1/1/2023 0:00 | 4/23/2023 0:00 |  | DESIGN |  |  | 4/23/2023 0:00 | 10/8/2023 0:00 |  | BIDDING |  |  | 10/8/2023 0:00 | 3/24/2024 0:00 |  | CONST |  |  | 3/24/2024 0:00 | 2/23/2025 0:00 |  | WARRANTY |  |  | 2/23/2025 0:00 | 2/23/2026 0:00 | [6 empty] | 2620000 | 34694.88 | 73710 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation |  |  | 9/14/2022 13:53 |  |  | Yes
Public Works | P12852 | STORMWATER MASTER PLAN - PHASE 2 | The Stormwater Master Plan - Phase 2 will include the design and permitting of the thirteen neighborhoods: Riverland Road Areas Sailboat Bend Tarpon River Flagler Village Harbor Isles/Inlet Poinsettia Heights South Middle River Melrose Park Shady Banks Croissant Park Middle River Terrace Imperial Point and Lake Ridge. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 2 | Design | 36 | Stormwater | No |  | 470 | Yes | Yes | -1 | -1 | -1 | -1 | [6 empty] | 2122658 |  |  |  | 2500000 | 0 | 2122658 | 0 | 377342 | PLANNING | [5 empty] | DESIGN |  |  | 2/6/2024 0:00 | 2/6/2025 0:00 |  | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [6 empty] | 2122658 |  |  |  | 2500000 | 18822.36 | 73749 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction | No | No | 6/6/2023 8:16 |  |  | Yes
Public Works | P12858 | WEST LAKE DRIVE BRIDGE OVER MERCEDES RIVER REPLACEMENT | This project is for the replacement of the West Lake Drive Bridge (#865774) spanning over the Mercedes River. The main bridge is reinforced concrete. The bridge is approximately 150-feet long by 30-feet wide with a narrow 2.5-foot sidewalk on one side. The two-lane bridge serves as the only access to the island and is a designated school bus route. There are no pile driving records for this bridge and the foundation is unknown at this time. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | Yes |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 481250 | 0 | 32381.25 | 0 | 448868.75 | PLANNING |  |  | 7/10/2023 0:00 | 12/15/2023 0:00 |  | DESIGN |  |  | 12/18/2023 0:00 | 12/20/2024 0:00 |  | BIDDING |  |  | 12/23/2024 0:00 | 3/14/2025 0:00 |  | CONST |  |  | 3/15/2025 0:00 | 3/21/2026 0:00 |  | WARRANTY |  |  | 3/22/2026 0:00 | 3/22/2027 0:00 | [6 empty] | 481250 | 6186.78 | 73494 | 2/12/2024 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 43 | Public Works | Bridges | Rehabilitation |  |  | 9/11/2023 6:16 |  |  | No
Public Works | P12859 | BRIDGE #865760 - SE 7TH STREET OVER RIO CORDOVA REPLACEMENT | This project is for the replacement of Bridge #865760 that carries SE 7th Street over the Rio Cordova River. The main bridge material is Precast Sonovoid Slab Units. The bridge is 120-feet long by 36-feet wide with sidewalks on both sides. The two-lane bridge serves as the only access to the island. There are no pile driving records for this bridge and the foundation is unknown at this time. | 1195 | Ana Ziegler |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | Yes |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 481250 | 0 | 32381.25 | 0 | 448868.75 | PLANNING |  |  | 10/10/2022 0:00 | 7/1/2024 0:00 |  | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 481250 | 19476.9 | 73774 | 3/5/2024 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 36 | Public Works | Bridges | Replacement |  |  | 9/11/2023 6:17 |  |  | No
Public Works | P12860 | WEST LAKE DRIVE BRIDGE OVER ESTELLE RIVER REPLACEMENT | This project is for the replacement of the West Lake Drive Bridge (#865771) spanning over the Estelle River. The main bridge material is primarily reinforced concrete. The bridge is approximately 140-feet long by 30-feet wide with a narrow 2.4-foot sidewalk on one side. The two-lane bridge serves as the only access to the island and is a designated school bus route. There are no pile driving records for this bridge and the foundation is unknown at this time. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | Yes |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 481250 | 0 | 32381.25 | 0 | 448868.75 | PLANNING |  |  | 7/10/2023 0:00 | 12/15/2023 0:00 |  | DESIGN |  |  | 12/18/2023 0:00 | 12/20/2024 0:00 |  | BIDDING |  |  | 12/23/2024 0:00 | 3/14/2025 0:00 |  | CONST |  |  | 3/15/2025 0:00 | 3/21/2026 0:00 |  | WARRANTY |  |  | 3/22/2026 0:00 | 3/22/2027 0:00 | [6 empty] | 481250 | 14779.53 | 73495 | 2/12/2024 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 43 | Public Works | Bridges | Rehabilitation |  |  | 9/11/2023 6:17 |  |  | No
Public Works | P12861 | WEST LAKE DRIVE BRIDGE OVER LUCILLE RIVER REPLACEMENT | This project is for the replacement of the West Lake Drive Bridge (#865773) spanning over the Lucille River. The main bridge is primarily reinforced concrete. The bridge is approximately 184-feet long by 30-feet wide with a narrow 3-foot sidewalk on one side. The two-lane bridge serves as the only access to the island and is a designated school bus route. There are no pile driving records for this bridge and the foundation is unknown at this time. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | Yes |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 481250 | 0 | 32381.25 | 0 | 448868.75 | PLANNING |  |  | 7/10/2023 0:00 | 12/15/2023 0:00 |  | DESIGN |  |  | 12/18/2023 0:00 | 12/20/2024 0:00 |  | BIDDING |  |  | 12/23/2024 0:00 | 3/14/2025 0:00 |  | CONST |  |  | 3/15/2025 0:00 | 3/21/2026 0:00 |  | WARRANTY |  |  | 3/22/2026 0:00 | 3/22/2027 0:00 | [6 empty] | 481250 | 13885.26 | 73496 | 2/12/2024 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 36 | Public Works | Bridges | Replacement |  |  | 9/11/2023 6:17 |  |  | No
Public Works | P12863 | SE 8TH STREET BRIDGE REPLACEMENT | This project is for the replacement of the SE 8th Street bridge (Bridge #865761). The bridge requires numerous repairs and if not fixed the Florida Department of Transportation (FDOT) could downgrade the bridge weight capacity or close the bridge entirely. | 885 | Connie Hayman |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 19 | Bridge | No |  | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 2285400 | 0 | 0 | 0 | 2285400 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2285400 | 15123.24 | 73497 | 2/12/2024 0:00 |  | STATUS | Yes | Yes | 8 | 25 | 43 | Public Works | Bridges | Rehabilitation | No | No | 9/25/2023 19:59 |  |  | No
Public Works | P12866 | TEMPORARY TRAILER FOR THE OCEAN RESCUE HEADQUARTERS | The Fire Rescue Department is requesting a temporary trailer to service as the Fort Lauderdale Ocean Rescue headquarters. The trailer will have the capabilities of housing all thirty (30) personnel and associated equipment. There are three main components for this site to be functional and fully operational. A portion of the site will be housed utilizing the Las Olas Garage for vehicle and equipment storage. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | FIR | PBS | 1 | Project Initiation & Planning | 14 | Fire | No |  |  |  |  | 0 | -1 | 0 | 0 | [10 empty] | 250000 | 0 | 0 | 0 | 250000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 250000 | 243.36 | 73356 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | 3 | 28 | 36 | Fire | Facilities | Replacement |  |  | 9/25/2023 20:03 |  |  | No
Public Works | P12869 | EXCAVATE AND DISPOSE OF DRY LIME SLUDGE | This project funds the excavation and disposal of approximately 300000 cubic yards of dry lime sludge stored in the 8-acre east sludge storage area. The Fiveash Water Treatment Plant produces lime sludge as a byproduct of its lime softening treatment process. The lime sludge is pumped continuously to one of two storage areas while lime sludge in the other adjacent storage area dries. The dry lime sludge must be removed to make room for storage of more liquid sludge after the storage area becomes full. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 2000000 | 0 | 94910 | 0 | 1905090 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2000000 | 366 | 73721 | 3/1/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 43 | Public Works | Water Sewer | Rehabilitation |  |  | 9/25/2023 20:04 |  |  | No
Public Works | P12870 | EQUIPMENT REPLACEMENT AT RE-PUMP STATIONS A B & E | This project is for the replacement of pumps and motors at the City's three (3) sanitary re-pump stations (A B & E). | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | 0 | -1 | 0 | [10 empty] | 500000 | 0 | 492686 | 0 | 7314 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 500000 | 1145.7 | 73712 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/25/2023 20:04 |  |  | No
Public Works | P12871 | FIVEASH REPLACEMENT OF THE ROTARY MECHANISMS (RECIRCULATION ARM) IN HYDROTREATER #2 | This project is to replace one of the Hydrotreaters (Hydrotreater #2) at the Fiveash Water Treatment Plant (WTP). Hydrotreaters are used to remove impurities and contaminants from water through a chemical process involving hydrogenation. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 862360 | 0 | 0 | 0 | 862360 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 862360 | 732 | 73722 | 3/1/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/25/2023 20:04 | No | No | No
Public Works | P12872 | SEWER BASIN A-99 COLLECTION SYSTEM REHABILITATION (I&I) | The project includes CCTV (closed-circuit television) inspection rehabilitation recommendations and rehabilitation work for sewer main lines and lateral connections clean out installations as needed and manhole repairs and sealing throughout Sewer Basin A-99 | 697 | Louis Lafaurie |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 2494284 | 0 | 0 | 0 | 2494284 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2494284 | 5957.64 | 73673 | 2/23/2024 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 68 | Public Works | Engineering | Study/Investigation |  |  | 9/25/2023 20:04 |  |  | No
Public Works | P12873 | SEWER BASIN D-7 COLLECTION SYSTEM REHABILITATION (I&I) | This project includes funding for a CCTV (Closed-Circuit Television) inspection followed by the necessary rehabilitation work to repair the sewer main lines and lateral connections. This project will involve clean out installations as needed; manhole repairs; and sealing throughout Sewer Basin D-7 | 1329 | Hong Xu |  |  | Brandy Leighton | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 1291650 | 0 | 0 | 0 | 1291650 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1291650 | 4468.23 | 73711 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 8 | 65 | 68 | Public Works | Engineering | Study/Investigation |  |  | 9/25/2023 20:05 |  |  | No
Public Works | P12874 | GEORGE T. LOHMEYER BELT PRESSES REPLACEMENT | The project is for replacement of biosolids dewatering equipment specifically belt filter presses at the George T. Lohmeyer (GTL) Waste Water Treatment Plant. Currently GTL maintains seven (7) belt filter presses. | 1380 | Gabrielle Bork |  |  | William Power | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 455 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 600000 | 0 | 0 | 0 | 600000 | PLANNING |  |  | 10/27/2023 0:00 | 1/31/2024 0:00 |  | DESIGN |  |  | 2/1/2024 0:00 | 8/1/2024 0:00 |  | BIDDING |  |  | 8/2/2024 0:00 | 12/2/2024 0:00 |  | CONST |  |  | 12/3/2024 0:00 | 12/2/2025 0:00 |  | WARRANTY |  |  | 12/3/2025 0:00 | 12/3/2026 0:00 | [6 empty] | 600000 | 8249.04 | 73540 | 2/16/2024 0:00 | 2/16/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/25/2023 20:05 |  |  | No
Public Works | P12875 | GEORGE T. LOHMEYER WASTEWATER TREATMENT PLANT SECONDARY SERV | This project is for the design and construction of a secondary server room at the George. T. Lohmeyer Wastewater Treatment Plant (GTL) which will provide greater resiliency in case one of the rooms experiences water damage. | 1355 | Wilfredo Negron |  |  | William Power | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 455 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 100000 | 0 | 0 | 0 | 100000 | PLANNING |  |  | 10/9/2023 0:00 | 3/7/2024 0:00 |  | DESIGN |  |  | 3/8/2024 0:00 | 10/4/2024 0:00 |  | BIDDING |  |  | 10/5/2024 0:00 | 1/3/2025 0:00 |  | CONST |  |  | 1/4/2025 0:00 | 9/1/2025 0:00 |  | WARRANTY |  |  | 9/2/2025 0:00 | 9/2/2026 0:00 | [6 empty] | 100000 | 0 | 72833 | 1/11/2024 0:00 | 1/11/2024 0:00 | STATUS | Yes | Yes | 8 | 12 | 41 | Public Works | Water Sewer | Equipment |  |  | 9/25/2023 20:05 |  |  | No
Public Works | P12876 | GEORGE T. LOHMEYER WASTEWATER TREATMENT PLANT CLARIFIER REHABILITATION | This project is for the Clarifier Battery Resurfacing - Launder and Weir Repair and Mechanism Replacement at the George T.Lohmeyer Wastewater Treatment Plant (GTL). Currently GTL has two (2) clarifiers that separate solids from treated water withconcrete that is old and failing. | 1374 | Mark Roads |  |  | Daniel Fisher | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No | PBS | 455 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 840968 | 0 | 0 | 0 | 840968 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 840968 | 12728.64 | 73723 | 3/1/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 90 | Public Works | Water Sewer | Master Plans | No | No | 9/25/2023 20:05 | Yes | Yes | No
Parks and Rec | P12755 | ESTERRE DAVIS WRIGHT PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Esterre Davis Wright Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include walking trail playground improvements and surfacing outdoor exercise equipment site furnishings park signage security lighting ADA benches ADA picnic tables garbage cans relocation ADA bike rack and accessible parking improvements. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 665000 | 0 | 0 | 0 | 665000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 665000 |  | 73011 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 5/5/2022 10:55 |  |  | Yes
Transportation and Mobility | P12440 | NW 15TH AVE TWIN LAKES ROAD CLOSURE | Design and construct a road closure on NW 15th Ave between the residential and commercial uses north of NW 46th Street as identified within the Twin Lakes North Neighborhood Mobility Master Plan. The project will include a closure that allows pedestrians and bicycles but not vehicles and appropriate signage to warn vehicles prior to turning down the street to the north and south. | 1314 | Kristin Thompson |  |  | Lisa Marie Glover | TAM | TAM | 11 | Hold | 27 | Roadway Improvements | No |  |  |  |  | -1 | 0 | 0 | 0 | [10 empty] | 50000 | 9989.9 | 0 | 0 | 40010.1 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 50000 |  | 73064 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 35 | Transportation and Mobility | Transportation | Renovation | No |  | 7/5/2018 8:47 |  |  | No
Parks and Rec | P12756 | FLAMINGO PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Flamingo Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include native planting site furnishings walking trails playground improvements security lighting outdoor exercise equipment park signage ADA benches ADA picnic tables garbage cans relocation ADA pathways ADA exercise equipment ADA playground and park entrances. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 940000 | 0 | 0 | 0 | 940000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 940000 |  | 73012 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 11:00 |  |  | Yes
Police | P12841 | POLICE SUBSTATION BUILD OUT | This project is for the design and construction of a new police substation within the Sistrunk Corridor. The City of Fort Lauderdale will partner with the LA Lee YMCA Family Center / Mizell Community Center and construct the substation through a lease tenant buildout. The project includes a variety of alterations and improvements to the building located at 1409 Sistrunk Boulevard to ensure that the family center can contain a functional public safety facility. The scope of this project includes the design and construction of various improvements including offices for district assigned officers a kitchen area restroom facilities and an intake lobby for residents in need of services. Â | [5 empty] | POL | POL | 6 | Construction | 16 | Police | No |  |  |  |  | 0 | 0 | -1 | 0 | [10 empty] | 225000 | 72676.58 | 143515.57 | 0 | 8807.85 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 225000 |  | 73216 | 1/29/2024 0:00 |  | STATUS | Yes | Yes | 7 | 21 | 35 | Police | Police Facilities | Renovation |  |  | 11/9/2022 10:25 |  |  | No
Parks and Rec | P12644 | BASS PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Bass Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include building/window accessibility picnic tables pool entrance and deck pool deck seating drinking fountain pool restrooms pool stairs and aquatic lift improvements. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 6640000 | 510390.19 | 118330.54 | 0 | 6011279.27 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 6640000 |  | 72915 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:19 |  |  | Yes
Parks and Rec | P12663 | MILLS POND PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Mills Pond Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches picnic tables replacement restrooms access routes to playfields water fountain playground resurfacing bleachers access and boat ramp access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 5334500 | 947503.55 | 69924.7 | 0 | 4317071.75 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 5334500 |  | 72914 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:27 |  |  | Yes
Transportation and Mobility | P12158 | CORDOVA ROAD COMPLETE STREETS PROJECT | This project includes landscaped medians two new pedestrian crossings pedestrian lighting and traffic calming. This neighborhood has a much higher percentage of neighbors that do not have access to a vehicle (17.7% v 7.7%) and access their jobs by walking (12.7% v 2.9%) than the city as a whole. There were 45 crashes in this two block corridor over the past five years. FDOT will lead design/construction. | 1314 | Kristin Thompson |  |  |  | TAM | TAM | 2 | Design | 27 | Roadway Improvements | Yes |  |  |  |  | 0 | 0 | 0 | -1 | [10 empty] | 170000 | 114644.15 | 12152.72 | 35100 | 8103.13 | PLANNING |  |  | 2/20/2019 0:00 | 10/1/2019 0:00 |  | DESIGN |  |  | 11/19/2018 0:00 | 10/1/2021 0:00 |  | BIDDING |  |  | 1/1/2021 0:00 | 4/9/2021 0:00 |  | CONST |  |  | 7/1/2021 0:00 | 6/30/2022 0:00 |  | WARRANTY |  |  | 7/1/2022 0:00 | 7/1/2023 0:00 | [6 empty] | 170000 |  | 73077 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 8 | 24 |  | Public Works | Transportation |  | No | No | 7/16/2015 11:40 |  |  | No
Transportation and Mobility | P12586 | LAKE RIDGE MASTER PLAN IMPLEMENTATION | Implementation of traffic calming measures identified in the Lake Ridge Mobilility Master Plan including lower cost tactical urbanism measures.Pilot road diet using paint and planters on NE15th Ave between NE11th St and NE13th St.Mini-roundabout - NE 11th St @ NE 10th AveRubber Speed humps - at NE11th Street @ 12th Ave & 17th Ave NE17th Terrace: between 12th & 13th St NE17th Way: between 12th & 13th St NE17th Ave: between 12th & 13th St NE18th Ave: between 11th & 12th St and between 12th & 13th St | 1314 | Kristin Thompson |  |  | Karen Warfel | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 97053.96 | 64969.19 | 0 | 0 | 32084.77 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 97053.96 |  | 71883 | 10/24/2023 0:00 | 10/24/2023 0:00 | STATUS | Yes | Yes | 10 | 23 | 68 | Transportation and Mobility | General Services | Study/Investigation |  |  | 7/23/2020 14:47 |  |  | No
Public Works | P12330 | CITY-OWNED SEAWALL RESTORATION AND REPLACEMENT | This project will address the capital repair and/or replacement of the City-owned seawalls as identified in the proposed Seawall Master Plan (Project No. 12212). This project is placeholder for seawall replacement funding as allocated by fiscal year. As funds become available in this project a project specific seawall project number is opened to capitalize the asset and the funds are move into it from this project through the commission budget amendment process. | 1100 | Rares Petrica |  |  | Rares Petrica | PBS | PBS | 10 | Annual | 33 | Seawalls | No |  |  |  |  | -1 | -1 | 0 | -1 | [10 empty] | 2359763 | 0 | 0 | 0 | 2359763 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2359763 |  | 70336 | 7/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 43 | Public Works | Engineering | Rehabilitation | No | No | 9/19/2017 7:53 |  |  | No
Parks and Rec | P12752 | BILL KEITH PRESERVE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Bill Keith Preserve Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include trail improvements native planting remove exotic vegetaion park pathways ADA pavilion furnishings entrance paths and ADA picnic tables. | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 545000 | 0 | 0 | 0 | 545000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 545000 |  | 72934 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 10:53 |  |  | No
Parks and Rec | P12763 | WARBLER WETLANDS IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Warbler Wetlands Improvement Project AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include parking pavilion and park signage. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 705000 | 0 | 0 | 0 | 705000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 705000 |  | 72937 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 11:17 |  |  | No
Public Works | P12247 | BROWARD COUNTY SEGMENT II BEACH NOURISHMENT | The project involves placement of beach-compatible sand along 4.9 miles of Broward County coastline between Hillsboro Inlet and Port Everglades (3.54 miles within the City limits). This includes beach nourishment at Pompano Beach and Lauderdale-by-the-Sea; beach restoration at northern Fort Lauderdale (between Flamingo Ave and Terramar St.); and dune construction within the Lauderdale-by-the-Sea and Fort Lauderdale segments. $203490 Hurricane Sandy reimbursement is in full $8378924 ($2792975 A1A Beach Repairs paid equally over a three year time period) including a $6764404 ($2254801 in Federal Funds reimbursed to the City equally over a three yearsâ€™ time period) commencing October 15 2016. It is not known when the Federal reimbursement to the City is expected and is not inc. | 1016 | Todd Hiteshew |  |  |  | PBS | PBS | 11 | Hold | 28 | Environmental | No |  |  | Yes | No | -1 | -1 | 0 | -1 | [10 empty] | 7320000 | 4880000 | 0 | 0 | 2440000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 7320000 |  | 70214 | 7/14/2023 0:00 |  | STATUS | Yes | Yes | 2 | 74 | 35 | Dept. of Sustainable Development | Beach CRA | Renovation | No | No | 8/16/2016 8:31
Parks and Rec | P12683 | FLORANADA PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Floranda Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include sidewalk access pavilion picnic tables restrooms park entrances water fountain BBQ grill surfacing and bleachers access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PBS | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 656782 | 227700 | 0 | 0 | 429082 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 656782 |  | 72932 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No |  | 5/7/2021 13:47
Community Redevelopment | P11595 | CENTRAL BEACH WAYFINDING & INFORMATION SIGNAGE | Construction and installation of a family of distinct coordinated vehicular pedestrian and parking signage; trolley/bus informational signage; and beach regulatory informational signs for the Fort Lauderdale Beach gateway area near E. Las Olas Blvd. and A1A. | 1320 | Marc Isaac |  |  |  | CRA | CRA | 1 | Project Initiation & Planning | 17 | Parking | No | PBS |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 83774.6 | 76364.5 | 0 | 0 | 7410.1 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 83774.6 |  | 73222 | 1/30/2024 0:00 |  | STATUS | Yes | Yes | 10 | 28 | 34 | Transportation and Mobility | Facilities | New Construction | No | No |  |  |  | No
Information Technology | P12344 | FIRE ALERTING SYSTEM - REPLACEMENT | In August of 2014 the City of Fort Lauderdale entered into a Inter Local Agreement with Broward County for a Regional Communications System to provide dispatch services for the Police and Fire Departments. Broward County currently provides fire department alerting and dispatching services to the Broward Sheriff's Office (BSO) Department of Fire Rescue and municipal fire departments throughout the county. Currently 106 fire stations are alerted and dispatched by the County. Dispatch operations are conducted from three public safety answering points (PSAPs) geographically located in the north central and south areas of the county with specific station alerting and dispatching responsibilities assigned to each PSAP.It is currently recommended that all municipalities fully inte | 1092 | Troy Bailey |  |  |  | FIR | ITS | 25 | Implementation | 14 | Fire | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 1300000 | 1293622.44 | 0 | 0 | 6377.56 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1300000 |  | 73050 | 1/19/2024 0:00 | 1/19/2024 0:00 | STATUS | Yes | No | 3 | 17 | 35 | Fire | Fire Bond | Renovation | No | No | 9/19/2017 10:23
Transportation and Mobility | P12627 | LAUDERTRAIL | LauderTrail is a City Commission-led initiative that resulted from the May 2018 Annual Action Plan meeting. Once completed LauderTrail will be a continuous and comprehensive network with ten miles of connected urban trail facilities for practical and recreational use that will promote a healthy lifestyle and environmental stewardship. The trail is expected to connect 17 neighborhoods 26 parks 11 K-12 schools 7 entertainment districts 14 government services 3 higher education centers over 30 cultural centers 30% of City jobs and 30% of City residents. | 1314 | Kristin Thompson |  |  | Karen Warfel | PKR | TAM | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 5000000 | 369270.13 | 471016.13 | 0 | 4159713.74 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 5000000 |  | 73087 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 20 | 34 | Transportation and Mobility | General Parks | New Construction | No | No | 12/2/2020 10:25
Parks and Rec | P12670 | SARA HORN GREENWAY IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sara Horn Greenway Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include dog waste bag dispenser access bench replacement and access and garbage can relocation. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 75000 | 0 | 0 | 0 | 75000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 75000 |  | 72990 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:31
Parks and Rec | P12657 | JACK AND HARRIET KAYE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Jack and Harriet Kaye Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches and park entrances. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 55000 | 0 | 0 | 0 | 55000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 55000 |  | 72957 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:25
Community Redevelopment | P12621 | PROVIDENT PARK IMPROVEMENTS | The Provident Park Improvement Project will undergo renovation to the existing structural site. The funds are being used to upgrade the park and will include: interactive water splash pads walking trails bandstand feature monument pedestals amphitheater monuments to honor the neighborhoods historical significance new restrooms and landscape designs. | 1221 | Corey Ritchie |  |  |  | PKR | CRA | 2 | Design | 12 | Parks | No |  |  | No | Yes | 0 | 0 | -1 | 0 | [10 empty] | 1364916.37 | 136701.64 | 27168.36 | 0 | 1201046.37 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1364916.37 |  | 73039 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | [6 empty] | No | No | 10/13/2020 13:56
Public Works | P12818 | SAILBOAT BEND STORMWATER IMPROVEMENTS | This project is for the installation of stormwater infrastructure along SW 2nd Court in order to alleviate ponding in the neighborhood. This project provides for the design and construction of new stormwater infrastructure to alleviate historical flooding. Potential conceptual design may consist of new and/or improved swale areas drainage structures drainage piping and other stormwater control features. | 1187 | Juan Carlos Samuel |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No |  | 470 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 714239 | 0 | 0 | 0 | 714239 | PLANNING |  |  | 1/2/2023 0:00 | 12/29/2023 0:00 |  | DESIGN |  |  | 1/1/2024 0:00 | 1/1/2026 0:00 |  | BIDDING |  |  | 1/2/2026 0:00 | 12/31/2026 0:00 |  | CONST |  |  | 1/1/2027 0:00 | 1/1/2029 0:00 |  | WARRANTY |  |  | 1/2/2029 0:00 | 1/2/2030 0:00 | [6 empty] | 714239 |  | 73764 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 34 | Public Works | Stormwater | New Construction |  |  | 9/14/2022 13:44 |  |  | No
Public Works | P12864 | CITY HALL REPLACEMENT | The project includes the phase one effort of planning for the rehabilitation or replacement of City Hall. Phase one includes project management design permitting and bidding of the project. | 1156 | Danica Grujicic |  |  | Raymond Nazaire | PBS | PBS | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 4032868 | 0 | 0 | 0 | 4032868 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 4032868 |  | 73355 | 2/6/2024 0:00 |  | STATUS | Yes | Yes | 63 | 23 | 36 | City Hall | General Services | Replacement | No | No | 9/25/2023 20:02 |  |  | No
Parks and Rec | P12760 | LAUDEREDALE MANORS PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Lauderdale Manors Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include playground improvements solar panels community center renovations ineractive water feature pool renovations ADA benches ADA picnic tables and grills trashcans relocation ADA pathways ADA drinking fountain ADA pool deck ADA shower tower ADA water playground. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 1856000 | 0 | 0 | 0 | 1856000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1856000 |  | 72929 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 5/5/2022 11:05 |  |  | No
Parks and Rec | P12646 | CHATEAU PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Chateau Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include improvements to site furnishings park signage and the stormwater treatment area. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 100000 | 0 | 0 | 0 | 100000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 100000 |  | 72949 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:20
Public Works | P12801 | GTL PLC CONTROL PANELS UPGRADE | This project entails an upgrade of the plant-wide Programmable Logic Controller (PLC) panels for PLC's 1A1B4567. A PLC receives electrical signals from several instruments and valves converts them to treatment process numbers and communicates them to the central computer system for viewing by operators. Operators in turn record these numbers for regulatory compliance and base their process decisions on these essential numbers. For consistency these panels will be upgraded with the same PLC's that currently exist at the Charles W. Fiveash and Peele Dixie water treatment plants as well as throughout the Distribution and Collection (D&C) network. | 1348 | Ivan Rivera |  |  | Miguel Arroyo | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 451 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 1050000 | 0 | 0 | 200000 | 850000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1050000 |  | 65470 | 10/27/2022 0:00 | 10/27/2022 0:00 | STATUS | Yes | Yes | 8 |  |  | Public Works |  |  |  |  | 9/14/2022 13:36 |  |  | No
City Manager | P11510 | 2009 NCIGP HARBOR BEACH PROPERTY HOA COLUMN LIGHTS & UPLIGHTS | 2009 NCIGP (Neighborhood Community Investment Grant Program) for decorative column lights and uplights at bridges in the Harbor Beach neighborhood. | 1282 | Luisa Agathon | 911 | To Be Determined |  | CM | CM | 25 | Implementation | 1 | NCIP | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 |  |  | 0 |  |  | 0 |  |  |  |  | 35000 | 23380 | 0 | 0 | 11620 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [7 empty] | 0 | 0 |  | 35000 |  | 71810 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 | 26 | 34 | Public Works | NCIP | New Construction | No | No
Public Works | P12294 | FIVEASH WTP ELECTRICAL VOLTAGE UPGRADE | Replace 4160 volt switchgear and motors for 10 high service pumps and 1 backwash pump. The work will also include the installation of two variable speed drives on the south high service pumps and one variable speed drive on the north high service pumps. Discuss with FPL the feeding to Fiveash with only 480 volt which would eliminate panel OSW2. If possible there will be a need to install a junction box to supply the administration building with 480 volts instead of 4160 volts. This would also eliminate the need to use a 4160 volt to 480 volt transformer at the administration building. Conduct a full arc flash survey of the plant. | 967 | Miguel Arroyo |  |  |  | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 454 | Yes | Yes | 0 | 0 | 0 | 0 | [10 empty] | 1780000 | 1497703.62 | 34722 | 0 | 247574.38 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1780000 |  | 67635 | 2/23/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 35 | Public Works | Water Sewer | Renovation | No | No | 3/3/2017 18:17
Parks and Rec | P12778 | WESTWOOD HEIGHTS ELEMENTARY PARKS IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Westwood Heights Elementary Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include playground/sunshade installation fencing basketball resurfacing and walking trail. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 375000 | 1966.13 | 52870.38 | 0 | 320163.49 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 375000 |  | 72943 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 6/10/2022 10:01 |  |  | Yes
Information Technology | P12305 | ACCESS CONTROL UPGRADES - CITY WIDE | Access control is utilized in buildings throughout the City to limit and track access to various facilities. This project is to upgrade and consolidate access control systems throughout the City into one City -wide access control platform allowing staff to centrally manage all facilities from one system /location. This platform will be hosted on enterprise grade hardware and provide necessary system redundancy to this critical system.This project is related to an Area For Improvement (AFI) issued on 1/25/2016. | 1323 | Mona Delavari |  |  | Mona Delavari | ITS | ITS | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 839400 | 510285.31 | 55631.25 | 0 | 273483.44 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 839400 |  | 73081 | 1/19/2024 0:00 | 1/19/2024 0:00 | STATUS | Yes | Yes | 4 | 23 | 37 | Information Technology | General Services | Security Upgrades | No | No | 5/4/2017 8:45
Community Redevelopment | P12582 | AQUATIC CENTER SOUTH BUILDING REPLACEMENT | The Fort Lauderdale Aquatic Center sits on a 5.5 acre peninsula on the barrier island. The Aquatic Center pools are undergoing a $27 Million renovation under a design build contract issued to Hensel Phelps. The existing athlete locker rooms is located in the South Building and needs renovation. The South Building is in poor condition and it is not a wise spend of money to perform interior renovations on a building with severe deficiencies. The City received an unsolicited proposal from Hensel Phelps to demolish and rebuild a new South Building. The new South Building will have athlete locker rooms office space conference room meet timing rooms weight room first aid station sun deck storage space and improvements to the perimeter road. | 1320 | Marc Isaac |  |  | Thomas Green | CRA | CRA | 6 | Construction | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 10500000 | 10223944.18 | 50784.51 | 0 | 225271.31 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 10500000 |  | 72948 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 2 | 72 | 34 | Dept. of Sustainable Development | CRA | New Construction | No | No | 6/9/2020 14:42
Parks and Rec | P12653 | GREENFIELD PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Greenfield Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include accessible sidewalk at SE entrance accessible route to picnic tables and swing set garbage can relocation accessible water fountain and addition of accessible benches. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 390000 | 2500 | 350 | 0 | 387150 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 390000 |  | 72954 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:23
Public Works | P12476 | FIVEASH WELLFIELD PUMP REPLACEMENT | This project is for removal and replacement of 19 complete well assemblies. Equipment has exceeded its effective life cycle. Wells would be replaced by operations staff at rate of five (5) units per fiscal year. Community Investment Plan funding is strictly for equipment only. | 934 | Herbert Stanley | 934 | Herbert Stanley | Talal Abi-Karam | PBS | PBS | 6 | Construction | 23 | Utilities | No |  |  |  |  | -1 | -1 | -1 | -1 | [10 empty] | 1500914 | 944854 | 0 | 0 | 556060 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  | 12/5/2017 0:00 | 9/15/2024 0:00 |  | WARRANTY | [10 empty] | 1500914 |  | 73124 | 1/23/2024 0:00 |  | STATUS | Yes | Yes | [8 empty] | 8/30/2018 14:46
Parks and Rec | P12775 | STRANAHAN HIGH SCHOOL PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Stranahan High School Improvement Project.AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include resurfacing of tennis courts fencing basketball court installation fitness equipment installation. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 300000 | 2100.39 | 78526.65 | 0 | 219372.96 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 300000 |  | 72940 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 9:58 |  |  | Yes
Public Works | P12252 | GEORGE T. LOHMEYER (GTL) INTERIOR PAINTING | This project will provide a protective coating application of all interior surfaces at the George T. Lohmeyer Water Treatment Plant. | 1257 | Justin Murray |  |  |  | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 451 | Yes | No | 0 | 0 | 0 | -1 | [10 empty] | 751088 | 302949.65 | 0 | 448138.35 | 0 | PLANNING | [5 empty] | DESIGN |  |  | 10/1/2021 0:00 | 3/1/2022 0:00 |  | BIDDING |  |  | 3/2/2022 0:00 | 8/1/2022 0:00 |  | CONST |  |  | 8/2/2022 0:00 | 12/31/2022 0:00 |  | WARRANTY |  |  | 1/1/2023 0:00 | 1/1/2024 0:00 | [6 empty] | 751088 |  | 62960 | 10/1/2022 0:00 | 1/30/2023 0:00 | STATUS | Yes | Yes | 8 | 28 | 38 | Public Works | Facilities | General Upgrades | No | No | 8/16/2016 9:47 |  |  | No
City Manager | P11696 | 2011 NCIGP HARBOR BEACH LANDSCAPED MEDIANS | 2011 NCIGP (Neighborhood Community Investment Grant Program) for Harbor Beach Landscaped Medians. This project represents the 2011 NCIGP for Harbor Beach Homeowner Association (HOA) request for landscaped medians and all things related at the following locations: Seabreeze Blvd & Mayan Drive Seabreeze Blvd. & Haskins Ave and River Lane. | 1282 | Luisa Agathon |  |  |  | CM | CM | 6 | Construction | 1 | NCIP | No |  |  | Yes |  | 0 | -1 | 0 | 0 | [10 empty] | 35000 | 22748.22 | 0 | 0 | 12251.78 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 35000 |  | 71811 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 26 | 34 | City Manager's Office | NCIP | New Construction | No | No
Information Technology | P12056 | CITYWIDE CAMERA INITIATIVE | Parks neighborhoods streets and other public venues represent prime target areas for camera installations. Public events can also be monitored for suspicious activities through the security and surveillance cameras. | 1322 | Wayne Gooden |  |  | Mona Delavari | POL | ITS | 25 | Implementation | 16 | Police | No |  |  | No | No | -1 | -1 | -1 | -1 | [10 empty] | 862829 | 859670.58 | 0 | 0 | 3158.42 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 862829 |  | 73048 | 1/19/2024 0:00 | 1/19/2024 0:00 | STATUS | Yes | No | 7 | 22 | 39 | Police | Police Equipment | Technology | No | No | 5/19/2014 12:08
Parks and Rec | P12649 | DOTTIE MANCINI PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Dottie Mancini Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches picnic tables restrooms lavatory water fountain and fitness stations resurfacing. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 965000 | 100515.13 | 5444.73 | 0 | 859040.14 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 965000 |  | 72923 | 1/17/2024 0:00 |  | STATUS | Yes | No | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:22
Parks and Rec | P12771 | GEORGE ENGLISH PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sunset Park Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City. Improvements at this site will include pickleball courts. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 1202912.5 | 224934 | 92500 | 0 | 885478.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1202912.5 |  | 73015 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 9:55 |  |  | No
Public Works | P12363 | GEORGE T LOHMEYER WWTP FUEL ISLAND IMPROVEMENTS | Fleet Services originally budgeted $10000 to install a canopy over the fuel island to protect the fuel dispenser and the Fuel tracking system from the inclement weather. One quote obtained for the canopy estimated $43000. A need has arisen to address the potential fuel spill at the fuel island and the recommendation is to add an oil/water system to prevent contamination of the sewer and storm drainage system. | 1170 | Omar Castellon |  |  |  | PBS | PBS | 2 | Design | 22 | CityFacilities | No |  | 583 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 140000 | 102343.5 | 0 | 0 | 37656.5 | PLANNING |  |  | 6/7/2019 0:00 | 8/14/2019 0:00 |  | DESIGN |  |  | 8/14/2019 0:00 |  |  | BIDDING |  |  | 8/14/2019 0:00 |  |  | CONST | [5 empty] | WARRANTY | [10 empty] | 140000 |  | 67712 | 2/27/2023 0:00 |  | STATUS | Yes | Yes | 8 | 33 | 34 | Public Works | Fleet | New Construction | No | No | 10/9/2017 18:24 |  |  | No
Public Works | P12601 | GTL ROADWAY RESURFACING | This project is to resurface roadways within George T. Lohmeyer Wastewater Treatment Plant (GTL) fence line. | 1257 | Justin Murray |  |  |  | PBS | PBS | 11 | Hold | 23 | Utilities | No |  | 451 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 200000 | 0 | 0 | 0 | 200000 | PLANNING |  |  | 10/1/2021 0:00 | 1/1/2023 0:00 |  | DESIGN |  |  | 1/1/2023 0:00 | 1/1/2024 0:00 |  | BIDDING | [5 empty] | CONST |  |  | 1/1/2024 0:00 | 3/1/2024 0:00 |  | WARRANTY |  |  | 3/2/2024 0:00 | 3/1/2025 0:00 | [6 empty] | 200000 |  | 70345 | 7/17/2023 0:00 |  | STATUS | Yes | No | 8 | 23 | 43 | Public Works | General Services | Rehabilitation |  |  | 9/22/2020 16:47
Parks and Rec | P12684 | OSSWALD PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Osswald Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches picnic tables replacement restrooms pathways water fountain add ADA accessible parking stall parking space striping outdoor fitness area surfacing and accessible route to playcourts. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PBS | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 3184000 | 949403.4 | 215352 | 0 | 2019244.6 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 3184000 |  | 72930 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/7/2021 13:47 |  |  | Yes
Parks and Rec | P12776 | NORTH FORK SCHOOL PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of North Fork School Park Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include playground installation fencing/integrating Broward and 15th Ave green spaces/walking path lighting basketball courts and water viewing deck/interactive learning feature. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 785000 | 3262.08 | 7591.04 | 0 | 774146.88 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 785000 |  | 72941 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 9:59 |  |  | Yes
Parks and Rec | P12754 | COONTIE HATCHEE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Coontie Hatchee Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include park signage security lighting native planting walking paths park walkways ADA exercise equipment ADA playground ADA pavilions and ADA park furnishings. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 430000 | 0 | 0 | 0 | 430000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 430000 |  | 73009 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 5/5/2022 10:54 |  |  | Yes
Transportation and Mobility | P12796 | LAS OLAS MOBILITY | In 2017 a unified effort was launched to evaluate the transportation landscaping planning and urban design needs of the Las Olas Boulevard corridor from Andrews Avenue to SR A1A aimed at building consensus on the future of a world-class corridor. The effort included extensive stakeholder participation by the Las Olas Working Group established that included residents business owners and property owners along the entire corridor. The project is estimated at $140 million. Staff is working with Stantec Consulting Services to identify different funding opportunities of which a special assessment is the most feasible option. Based on prior city projects that used a special assessment model where the City had a participatory role in the funding staff is requesting a phased funding approach | 1314 | Kristin Thompson |  |  | Karen Warfel | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 5500000 | 410.9 | 0 | 2000000 | 3499589.1 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 5500000 |  | 73088 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 90 | Transportation and Mobility | Transportation | Master Plans |  |  | 9/14/2022 13:32 |  |  | No
Parks and Rec | P12672 | SOUTH MIDDLE RIVER PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of South Middle River Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches replacement picnic tables replacement water fountain replacement pathways replacement fitness equipment surfacing and BBQ grill access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 290700 | 0 | 0 | 0 | 290700 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 290700 |  | 72993 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:31
Parks and Rec | P12651 | FLORENCE C. HARDY PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Florence C. Hardy Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches lawn bowling court access restrooms pathways addition of accessible parking exercise station surfacing and bleachers access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 4 | Bidding | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 2585000 | 533298.98 | 35985.69 | 1677600.6 | 338114.73 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2585000 |  | 72913 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:23 |  |  | Yes
Parks and Rec | P12624 | DISTRICT 1 - LOCKHART PARK - | This project is for the design and construction of the new Lockhart Park. AECOM will perform the planning design permitting bidding and construction administration for this project. The park will include site improvements athletic fields surface parking a community center splash pad/water feature lighting landscaping and hardscape. InterMiami built the soccer stadium and was originally responsible for park design and construction and the City was responsible for the community center and splashpad/water feature. The City will now administer the design and construction of all park elements and is coordinating with InterMiami to determine their financial obligation to the project. | 1320 | Marc Isaac |  |  | Thomas Green | PKR | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 2400000 | 452629.89 | 1524723.6 | 0 | 422646.51 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2400000 |  | 72925 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No | No | 11/18/2020 8:46 |  |  | Yes
Parks and Rec | P12780 | ROCK ISLAND ELEMENTARY PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Rock Island Elementary Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include playground installation and fencing. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 262500 | 1807.53 | 2489.15 | 0 | 258203.32 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 262500 |  | 72945 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 10:07 |  |  | Yes
Parks and Rec | P12679 | VICTORIA PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Victoria Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches replacement accessible route to park/park entrance pathway accessibility accessible route to waterway and an addition of trash cans.The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 205000 | 0 | 0 | 0 | 205000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 205000 |  | 73001 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:34
Transportation and Mobility | P12879 | CITY HALL PARKING GARAGE IMPROVEMENTS | Staff recommends completing a structural assessment to determine the future repair and maintenance needs of the City Hall Garage. This assessment is to review the conditions of the garage and to develop a short term midterm and long-term repair and maintenance schedule (with cost estimates for budgeting purposes). This assessment should still be completed despite the current closure of the existing City Hall facility as the garage is still being utilized by City and 1 East Broward users. | 1373 | Mitxi Sanchez |  |  |  | TAM | TAM | 1 | Project Initiation & Planning | 17 | Parking | No |  | 461 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 500000 | 0 | 0 | 0 | 500000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 500000 |  | 73514 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 10 | 32 | 38 | Transportation and Mobility | Garages | General Upgrades |  |  | 9/25/2023 20:06 |  |  | No
Parks and Rec | P12717 | MAUSOLEUMS-LAUDERDALE MEMORIAL GARDENS CEMETERY | This project funds the construction of a 340' corner mausoleum that consists of 762 crypts and 256 large niches at Lauderdale Memorial Gardens Cemetery located at 2001 SW 4th Avenue Fort Lauderdale FL 33315. | [5 empty] | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 430 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 1561584 | 0 | 0 | 0 | 1561584 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1561584 |  | 73138 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 15 | 34 | Parks and Recreation | Cemeteries | New Construction |  |  | 9/15/2021 9:41 |  |  | No
Parks and Rec | P12658 | LAKE ESTATES LINEAR PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Lake Estates Linear Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include landscaping improvements. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 250000 | 0 | 0 | 0 | 250000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 250000 |  | 72958 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:25
Public Works | P12886 | HARBOR ISLES STORMWATER IMPROVEMENTS | This project is for the analysis and design of stormwater improvements in the Harbor Beach Neighborhood. The Consultant will be utilizing the existing Interconnected Channel and Pond Routing (IPRC) model to assess the drainage infrastructure in the neighborhood and develop construction ready plans and specifications that can be bid out to contractors for implementation. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No | PBS | 470 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 567880 | 0 | 0 | 0 | 567880 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 567880 |  | 73751 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 90 | Public Works | Stormwater | Master Plans | No | No | 9/25/2023 20:08 | No | No | No
City Manager | P12881 | TAXIWAY L & P EXTENSION & RUN-UP AREA | This project is for the planning design and construction of the extension of Taxiways Lima and Papa to conform to current Federal Aviation Administration (FAA) design standards as well as to correct alignment issues. Portions of the taxiways will be demolished and re-constructed to the new alignment. Additionally a run-up area will be constructed east of Taxiway Papa to accommodate a growing number of piston aircraft in the northwest corner of the Airport. New light-emitting-diode (LED) taxiway edge-lights guidance signs striping runway guard lights (RGL) and an airport lighting control and monitoring system (ALCMS) update will also be included as part of the project. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 58750 | 0 | 0 | 0 | 58750 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 58750 |  | 71868 | 10/25/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 43 | City Manager's Office | Airport | Rehabilitation |  |  | 9/25/2023 20:07 |  |  | No
Information Technology | P11989 | NPF CRA WIRELESS CAMERA AND WI-FI | A wireless security camera and Wi-Fi system will be installed on city-owned light poles along the NE 6th St/Sistrunk corridor to provide an enhanced level of security for area businesses residents visitors and property owners in the area. The security cameras will work well with other law enforcement activities such as the new police substation license plate reader device and other enhanced enforcement tactics deployed in the redevelopment area. | 1350 | Aarmondas Walker |  |  |  | ITS | ITS | 15 | Complete | 16 | Police | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 300000 | 299686.61 | 0 | 0 | 313.39 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 300000 |  | 71815 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 2 |  |  | Dept. of Sustainable Development |  |  | No | No | 9/19/2013 13:32 |  |  | No
Parks and Rec | P12652 | FRANCIS L. ABREU PLACE | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Francis L. Abreu Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include accessible route from park entrance and accessible bench and transfer pad. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 60000 | 0 | 0 | 0 | 60000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 60000 |  | 72953 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:23
Transportation and Mobility | P12687 | FEDERAL COURTHOUSE PARKING GARAGE | This project is for construction of a 350+ space parking garage for the new federal coiurthouse location on SE 3rd Avenue and SE 11th street. This project will be for the design and construction of the garage and will include garage requirements determined by the General Services Adminstration (GSA). | 1150 | Diana Carrillo |  |  |  | TAM | TAM | 11 | Hold | 17 | Parking | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 2193019 | 10589.4 | 350000 | 0 | 1832429.6 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2193019 |  | 73076 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 83 | 34 | Transportation and Mobility | Parking Systems | New Construction | No | No | 5/25/2021 11:06
Parks and Rec | P12673 | STRANAHAN LANDING IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Stranahan Landing Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches and walkways. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 231000 | 0 | 0 | 0 | 231000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 231000 |  | 72994 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:32
Parks and Rec | P12782 | HARBORDALE ELEMENTARY PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Harbordale Elementary Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include playground installation and court resurfacing. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 275000 | 1835.16 | 2496.12 | 0 | 270668.72 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 275000 |  | 72947 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 10:09 |  |  | Yes
Parks and Rec | P12655 | HORTT PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Hortt Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include addition of accessible benches addition of accessible picnic tables restrooms accessibility pathways/sidewalks improvement park entrance improvements playcourts access garbage can relocation accessible little free library exercise area improvements playground improvements and co | 1320 | Marc Isaac |  |  |  | PKR | PKR | 6 | Construction | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 2050000 | 203504.13 | 908601.44 | 0 | 937894.43 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2050000 |  | 72920 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:24 |  |  | Yes
Community Redevelopment | P12096 | SISTRUNK ENHANCEMENT PH. II -UNDERGROUNDING UTILITIES | Provides for the undergrounding of existing Florida Power and Light Company electric distribution lines along Sistrunk Boulevard from NW 9th Avenue to N. Andrews Avenue. | 1017 | Bob Wojcik |  |  |  | CRA | CRA | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 347 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 2197705 | 1989869.02 | 0 | 0 | 207835.98 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2197705 |  | 73035 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | [6 empty] | No | No | 9/18/2014 11:43
Parks and Rec | P12767 | MILLS POND CONCESSION STAND/RESTROOM ROOF REPLACEMENT | Repair the roof at the Mills Pond Park Football Concession Stand/Restroom. | 1142 | Corey Callier |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 146509 | 133190 | 0 | 0 | 13319 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 146509 |  | 71801 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | [7 empty] | No | 5/26/2022 10:06
Transportation and Mobility | P12794 | LAS OLAS INTERSECTION PAVING | This project is for mill and resurface two (2) painted intersections given the current conditions of the intersection markings. Existing conditions have impaired the use of safety devices that are in place to provide safe connections for both motorists and pedestrians and will include Americans with Disabilities Act (ADA) improvements and crosswalk enhancements. The specific intersections that would be improved are as followsâ€™ 1st Avenue and Las Olas Boulevard and SE 2nd Avenue and Las Olas Boulevard | 1318 | Mackendy Philippi |  |  |  | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 80000 | 39927.35 | 0 | 0 | 40072.65 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 80000 |  | 73067 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 23 | 38 | Transportation and Mobility | General Services | General Upgrades |  |  | 9/14/2022 13:30 |  |  | No
Parks and Rec | P12845 | POOL RESURFACING - RIVERLAND POOL & LAUDERDALE MANORS POOL | This project is for the resurfacing of the main pools at Lauderdale Manors Park and Riverland Park. | 1363 | Jennifer Gigler |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 331 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 364332 | 283037 | 81295 | 0 | 0 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 364332 |  | 73143 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 28 | 38 | Parks and Recreation | Facilities | General Upgrades | No | No | 1/31/2023 21:07 | No | No | No
Public Works | P12438 | FREIGHT ELEVATOR REPLACEMENT AT GTL DEWATERING BLDG | The freight elevator at George T. Lohmeyer (GTL) requires an immediate replacement. It exceeded its life expectancy according to the study completed by our consultant CDM Smith in June of 2016. It currently requires on average $125000 in annual repairs and it is constantly breaking resulting in considerable downtime. In summary it is not just impacting daily operations of the plant but it is also a life and safety issue for the staff. In addition the elevator is outdated and the elevator capacity needs to be increased from 6000 to 10000 tons. Project is on hold until Consultant (TetraTech) has new Contract with the City. | 1257 | Justin Murray |  |  |  | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 451 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 1200000 | 63200.9 | 0 | 0 | 1136799.1 | PLANNING |  |  | 1/1/2022 0:00 |  |  | DESIGN |  |  | 7/2/2022 0:00 | 12/1/2022 0:00 |  | BIDDING |  |  | 12/2/2022 0:00 | 4/1/2023 0:00 |  | CONST |  |  | 4/2/2023 0:00 | 1/1/2024 0:00 |  | WARRANTY |  |  | 1/2/2024 0:00 | 1/1/2025 0:00 | [6 empty] | 1200000 |  | 67721 | 2/1/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | No | No | 6/1/2018 9:15
| P12891 | Holiday Park Parking Garage | [6 empty] | TAM |  | 1 | Project Initiation & Planning | 17 | Parking | No |  | 461 | Yes | Yes | 0 | 0 | 0 | 0 | [10 empty] | 500000 | 0 | 0 | 0 | 500000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 500000 |  | 73116 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 9/26/2023 12:27 |  |  | No
Parks and Rec | P12675 | TARPON COVE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Tarpon Cove Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include dog waste bag dispenser access park garbage can access and canal access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 248500 | 0 | 0 | 0 | 248500 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 248500 |  | 72997 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:33
Public Works | P12704 | REPLACE A/C BACK UNIT PEELE DIXIE MEMBRANE BLDG | This project funds the replacement of the back-up air conditioning (A/C) unit in the membrane building electric room at the Peele Dixie Water Treatment Plant. | 967 | Miguel Arroyo |  |  |  | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 50000 | 46536.5 | 0 | 0 | 3463.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 50000 |  | 67588 | 2/22/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/15/2021 9:38
Public Works | P12541 | SECURITY AND ACCESS SYSTEM UPGRADE | The Fort Lauderdale Executive Airport (FXE) has over 180000 aircraft operations per year making it one of the topfive General Aviation airports in the United States. In order to continue being an attractive destination the Airportmust maintain the general airfield. In order to accomplish this the Airport has identified certain improvements thatwill enhance security provide a higher level of service to our tenants and continue servicing aircraft flying in and outof FXE. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 600000 | 0 | 0 | 0 | 600000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 600000 |  | 70019 | 7/7/2023 0:00 |  | STATUS | Yes | Yes | 10 | 9 | 37 | Transportation and Mobility | Airport | Security Upgrades | No | No | 9/10/2019 15:09 |  |  | No
Parks and Rec | P12669 | SAILBOAT BEND PRESERVE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sailboat Bend Preserve Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include pathways tree trimming bench and garbage can relocation. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 142000 | 0 | 0 | 0 | 142000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 142000 |  | 72989 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:30
Public Works | P12051 | CONTRACT FOR SUPERVISORY CONTROL AND DATA ACQUISITION (SCADA) SYS | Request for specialized contractor to implement a supervisory control and data acquisition (SCADA) system within the Utilites Bureau. The contractor will be responsible for creating constructing and updating the necessary systems/equipment througout the various water plants the wastewater plant and the water/wastewater distribution and sewer collection system. | 967 | Miguel Arroyo |  |  |  | PBS | PBS | 25 | Implementation | 23 | Utilities | No |  | 454 |  |  | -1 | -1 | -1 | -1 | [10 empty] | 850000 | 758367.93 | 0 | 0 | 91632.07 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 850000 |  | 62988 | 8/1/2022 0:00 |  | STATUS | Yes | Yes | 8 | 82 | 39 | Public Works | Utilities Engineering | Technology | No | No | 4/24/2014 12:45
Parks and Rec | P12632 | JOSEPH C. CARTER PARK IMPROVEMENT PROJECT | This project is for the design and construction of the Joseph C. Carter Park Improvements. The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include site improvements community center shade structure and playground athletic fields aquatic complex renovations and site lighting upgrades. | 1320 | Marc Isaac |  |  | Thomas Green | PKR | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 13621000 | 1503830.63 | 345623.72 | 0 | 11771545.65 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 13621000 |  | 72926 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No | No | 2/9/2021 14:18 |  |  | Yes
Community Redevelopment | P12315 | AQUATIC CENTER RENOVATION | Unique and world renowned in the aquatics field the Fort Lauderdale Aquatic Complex is a City -owned and operated 5-acre venue comprised of municipal swimming pools and the International Swimming Hall of Fame (ISHOF) museum.Renovation of the existing facility for public use includes the following improvements: Remove existing 50 Meter Competition Pool and provide new expanded fully FINA compliant pool with moveable bulkheads; Remove existing Dive Pool and provide new expanded FINA compliant pool and dive tower; Spectator seating for Diving and Competition pool; Remove existing Spa for divers and provide new covered spa; Repair existing 50 Meter training pool with new surfacing and gutters; repair and/or expand Instructional pool; New pool deck; Remove existing grandstand building an | 1320 | Marc Isaac |  |  | Thomas Green | CRA | CRA | 6 | Construction | 22 | CityFacilities | No |  | 346 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 30617756.87 | 30496326.62 | 65415.68 | 0 | 56014.57 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 30617756.87 |  | 73020 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 77 | 74 | 35 | Economic Development | Beach CRA | Renovation | No | No | 5/30/2017 17:39
Parks and Rec | P12761 | RIVERLAND PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Riverland Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include activity center renovations interactive water feature solar panels playground improvements walking trail/outdoor exercise equipment pool registration window and deck table seating locker room improvements ADA pool ramp handrails ADA water playground and ADA aquatic lift. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 2738000 | 0 | 0 | 0 | 2738000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2738000 |  | 72933 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 11:05 |  |  | No
City Manager | P12812 | RUNWAY 9 RUN-UP RELOCATION & SOUTH END TAXIWAYS INTERSECTION IMPROVEMENTS | This project combines P12522-Runway 9 Run-Up Area (South) and FY 20200889-Runway 9 Taxiway Intersection Improvements. The project is for the design and construction of the run-up area and the installation of a blast fence at the western end of Runway 9. In addition this project is to design the re-alignment of taxiways Echo and Juliet on the southern end of Runway 9. The taxiways will be extended into perpendicular taxiways. The project will also include the milling and resurfacing of taxiway Echo. New asphalt striping sodding and light-emitting-diode (LED) edge-lights and guidance signs will be installed. This project is partially funded by the Federal Aviation Administration (FAA) grant for approx. 90% reimbursement of the eligible project costs and a grant from Florida Departmen | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | Yes |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 312196 | 0 | 0 | 0 | 312196 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 312196 |  | 71861 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 35 | City Manager's Office | Airport | Renovation |  |  | 9/14/2022 13:42 |  |  | No
Parks and Rec | P12750 | ANN HERMAN PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Ann Herman Park Improvement Project.AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include site furnishing fitness equipment stormwater management playground improvements ADA pathways ADA bike rack ADA playground ADA picnic table ADA water fountain and ADA exercise equipment. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 435000 | 0 | 0 | 0 | 435000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 435000 |  | 73007 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades | No | No | 5/5/2022 10:15 |  |  | Yes
Parks and Rec | P12762 | WALKER PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Walker Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include bike racks park signage picnic tables fencing pavilion benches security lighting playground improvements ADA park entrance sidewalk improvements and ADA tennis court entrance. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 650700 | 0 | 0 | 0 | 650700 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 650700 |  | 72936 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 11:14 |  |  | No
Transportation and Mobility | P12788 | RIVER OAKS TRAFFIC IMPROVEMENTS | This project includesÂ the milling and resurfacing roadway and sidewalk improvements minor drainage improvements possible landscape signing and pavement marking improvements throughout the River Oaks neighborhood. | 1314 | Kristin Thompson |  |  |  | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 75000 | 0 | 4940 | 0 | 70060 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 75000 |  | 73066 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 23 | 36 | Transportation and Mobility | General Services | Replacement | No | No | 8/10/2022 8:54 |  |  | No
Parks and Rec | P12781 | STEPHEN FOSTER ELEMENTARY PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Stephen Foster Elementary Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include fencing playground installtion basketball resurfacing and walking path. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 500000 | 2332.33 | 18174.18 | 0 | 479493.49 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 500000 |  | 72946 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 10:08 |  |  | Yes
Parks and Rec | P12650 | EARL LIFSHEY OCEAN PARK | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Earl Lifshey Ocean Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include seating walkways and native plants and trees signage. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 86000 | 0 | 0 | 0 | 86000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 86000 |  | 72952 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:22
Parks and Rec | P12680 | WARFIELD PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Warfield Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include accessible parking community center improvements restroom improvements garden access basketball courts improvements walking trail playground resurfacing benches and picnic table. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 4 | Bidding | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 1510000 | 160130.46 | 25868.67 | 1188280 | 135720.87 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1510000 |  | 72924 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:35 |  |  | Yes
Transportation and Mobility | P12699 | LAS OLAS ISLES SIGNALIZED CROSSWALKS | This project calls for the installation of two signalized crosswalks on East Las Olas Blvd one at Coconut Isle Dr and the other on Coral Way. | 1314 | Kristin Thompson |  |  | Lisa Marie Glover | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 630620 | 58894.44 | 570960 | 0 | 765.56 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 630620 |  | 73073 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 38 | Transportation and Mobility | Transportation | General Upgrades |  |  | 9/15/2021 9:37 |  |  | No
Parks and Rec | P12682 | CROISSANT PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Croissant Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include community center improvements park furniture park entrances access pathways parking lot improvements pool deck improvements portable aquatic lift shower tower and water playground. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 2620000 | 334145.37 | 277312.25 | 0 | 2008542.38 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2620000 |  | 72931 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No |  | 5/7/2021 13:46 |  |  | Yes
Parks and Rec | P12844 | FIRE STATION 3 HVAC REMOVAL AND INSTALLATION | Replacement of the HVAC system at Fire Station 3. | 1142 | Corey Callier |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 14 | Fire | No |  | 331 | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 221330 | 0 | 224423 | 0 | -3093 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 221330 |  | 73144 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 28 | 38 | Parks and Recreation | Facilities | General Upgrades | No | No | 1/31/2023 21:05 |  |  | No
Public Works | P12887 | NE 4TH STREET DRAINAGE IMPROVEMENTS | This project is intended to be constructed alongside a Transportation and Mobility streetscape improvement project that will interconnect the existing drainage systems in the area on NE 4th Street between NE 3rd Avenue and US-1 ensuring flood protection and runoff conveyance for years to come. | 1336 | Scarlet Del Valle |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No | PBS | 470 | Yes |  | 0 | -1 | 0 | 0 | [10 empty] | 508844 | 0 | 0 | 0 | 508844 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 508844 |  | 73726 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 11 | 90 | Public Works | Stormwater | Master Plans | No | No | 9/25/2023 20:08 | No | No | No
Community Redevelopment | P12507 | NPF STREETSCAPE IMPROVEMENT PROJECT | This project entails screetscape improvements within the Public Right-Of-Way along NW 5th Avenue and Various Streets within the Northwest Progresso Flagler Heights (NPF) CRA Community Redevelopment Area. | 1221 | Corey Ritchie |  |  |  | CRA | CRA | 6 | Construction | 27 | Roadway Improvements | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 2500646 | 491938.52 | 97440 | 0 | 1911267.48 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2500646 |  | 73037 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | 77 | 72 | 34 | Economic Development | CRA | New Construction | No | No | 6/12/2019 14:44
Parks and Rec | P12674 | SWEETING PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sweeting Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include bench and pathway access. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 230000 | 0 | 0 | 0 | 230000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 230000 |  | 72996 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:32
Parks and Rec | P12753 | COOLEY'S LANDING MARINA IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Cooley's Landing Marina Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include restroom renovations security lighting solar panels outdoor fitness equipment admin. building renovations boat slip improvement ADA walkways ADA site furnishings ADA restrooms ADA locker rooms and ADA dock walkways. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 100000 | 43741.7 | 406066.5 | 0 | -349808.2 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 100000 |  | 72928 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 10:53 |  |  | No
Parks and Rec | P12668 | RIVERSIDE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Riverside Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include sidewalks tactile indicators swing set access grabage can access and relocation free little library access community center improvements accessible parking restriping fencing and pathways. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 6 | Construction | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 680000 | 102995.08 | 420090.41 | 0 | 156914.51 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 680000 |  | 72921 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:30 |  |  | Yes
Public Works | P12581 | PEELE DIXIE WTP FACILITY IMPROVEMENTS | This project is for the roof replacements and roadway improvements at the Peele Dixie Water Treatment Plant. Indications of mold was discovered during an inspection by a qualified vendor at the original building that is almost 100 years old. Before the City can begin the mold remediation process the roof and roadway need to be replaced at the water treatment plant. | 967 | Miguel Arroyo |  |  | Talal Abi-Karam | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 435000 | 0 | 0 | 0 | 435000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 435000 |  | 67520 | 2/17/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | No | No | 6/1/2020 13:17
City Manager | P12883 | DESIGN AND CONSTRUCT FXE MAINTENANCE APRON PAVEMENT REHAB PROJECT | This project is to design and construct the apron at the airport maintenance building. The scope of the design includes but is not limited to topographical survey geotechnical report development of construction plans and technical specifications and development of a construction cost estimate. The construction scope of the project includes but is not limited to survey clearing and grubbing testing maintenance of traffic milling and resurfacing of asphalt sodding and pavement markings. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 46750 | 0 | 0 | 0 | 46750 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 46750 |  | 71870 | 10/25/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 43 | City Manager's Office | Airport | Rehabilitation |  |  | 9/25/2023 20:07 |  |  | No
Parks and Rec | P12643 | ANNIE BECK PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Annie Beck Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include park entrances accessible ramp trail entries walking trails site furnishings and accessible benches. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 4 | Bidding | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 545000 | 73110.19 | 30590.32 | 373645 | 67654.49 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 545000 |  | 72922 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:19 |  |  | Yes
Parks and Rec | P12660 | LEWIS LANDING PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Lewis Landing Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include accessible water cooler benches pavilion and central receptacles picnic tables pavilion electrical outlets and pathways.The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 35000 | 0 | 0 | 0 | 35000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 35000 |  | 72960 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:26
Public Works | P12620 | LAS OLAS MARINA PUMP STATION D-31 |  | 934 | Herbert Stanley |  |  | Steve Roberts Jr. | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 495 | Yes | Yes | 0 | 0 | 0 | 0 | [10 empty] | 2500000 | 2202220.67 | 297779.33 | 0 | 0 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 2500000 |  | 71906 | 10/26/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement | No | No | 9/29/2020 10:10 |  |  | Yes
Transportation and Mobility | P12851 | HOLIDAY PARK PARKING GARAGE | Design of a parking garage with 1000 spaces. |  |  |  |  | Kristin Thompson | TAM | TAM | 1 | Project Initiation & Planning | 17 | Parking | No |  |  | Yes | Yes | -1 | -1 | 0 | 0 | [10 empty] | 500000 | 199.4 | 0 | 500000 | -199.4 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 500000 |  | 73078 | 1/19/2024 0:00 |  | STATUS | Yes | Yes | 10 | 32 | 34 | Transportation and Mobility | Garages | New Construction | No | No | 5/18/2023 9:12 |  | No | No
Transportation and Mobility | P12865 | ANNUAL SIDEWALK GAP CONSTRUCTION | This project provides annual funding for the construction of new sidewalks within the City of Fort Lauderdale. The City will prioritize filling the gaps as identified in in the Sidewalk Master Plan as well as areas frequently identified by residents through the Q-Alert request list. 32 locations were identified as needing additional sidewalks from the Neighborhood Mobility Master Plans (over 10 miles of sidewalk construction requested). This is a recurring request to commence construction of the neededinfrastructure. | 1210 | Karen Warfel |  |  | Karen Warfel | TAM | TAM | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 250000 | 0 | 0 | 0 | 250000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 250000 |  | 72995 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | 10 | 24 | 34 | Transportation and Mobility | Transportation | New Construction | No | No | 9/25/2023 20:02 |  |  | No
Parks and Rec | P12681 | WESTWOOD HEIGHTS TRIANGLE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Westwood Heights Triangle Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include improvements to park signage benches bike racks and sidewalk connection. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 21000 | 0 | 0 | 0 | 21000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 21000 |  | 73002 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:35
Public Works | P12797 | PLANT A AND FORMER TRASH TRANSFER STATION REMEDIATION | This project involves remediating Plant A and the former Trash Transfer Station by placing an engineering control consisting of a Geo textile fabric and one (1) foot of clean fill within the open area. The perimeter fence will also be removed and replaced as needed. Cracks in the pavement will be sealed in addition to curbing being installed to contain the engineering controls. This project also contains several options which may or not be included depending on costs including the removal of a ramp and creating parking spaces regrading the berm and installing a parking area east of the entrance road to the toe of the berm. | 1016 | Todd Hiteshew |  |  | Todd Hiteshew | PBS | PBS | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  | 409 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 1800000 | 0 | 0 | 0 | 1800000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1800000 |  | 72917 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 8 | 69 | 35 | Public Works | Environmental Services | Renovation |  |  | 9/14/2022 13:32 |  |  | No
Parks and Rec | P12691 | FIRE STATION #49 ROOF REPLACEMENT | Replace the roof at Fire Station #49. | 1143 | Enrique Sanchez |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 428000 | 368214.5 | 59785.5 | 0 | 0 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 428000 |  | 70207 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 23 | 38 | Parks and Recreation | General Services | General Upgrades | No | No | 8/4/2021 15:12
Public Works | P12787 | LEAD AND COPPER RULE REVISION (LCRR) COMPLIANCE PROGRAM | The inventory must include all service lines connected to the public water distribution system regardless of ownership status (e.g. where service line ownership is shared the inventory would include both the portion of the service line owned by the water system and the customer-owned portion of the service line | 1339 | Garry Brandy |  |  | Talal Abi-Karam | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  |  | No | Yes | -1 | -1 | -1 | -1 | [10 empty] | 1600000 | 0 | 0 | 0 | 1600000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1600000 |  | 71967 | 10/24/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 68 | Public Works | Water Sewer | Study/Investigation | No | No | 7/22/2022 14:05
Public Works | P12884 | DESIGN AND CONSTRUCTION OF TAXIWAY ECHO PAVEMENT REHABILITATION | This project is for the reconstruction of Taxiway Echo (portion east of Runway 13-31) and will include the removal of existing pavement preparation of subgrade and construction of new pavement with new or recycled materials. | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 76200 | 0 | 0 | 0 | 76200 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 76200 |  | 71965 | 10/24/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 43 | City Manager's Office | Airport | Rehabilitation |  |  | 9/25/2023 20:07 |  |  | No
Parks and Rec | P12656 | IMPERIAL POINT ENTRANCEWAY IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Imperial Point Entranceway Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches and pathways. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 95000 | 0 | 0 | 0 | 95000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 95000 |  | 72956 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:25
Transportation and Mobility | P12600 | TRAFFIC FLOW IMPROVEMENTS | In order to address the FY 2021 City Commission Priority to improve traffic flow throughout the City of Fort Lauderdale the Transportation and Mobility Department is requesting to provide technology improvements to improve critical areas and pinch points throughout the City. This project will be done in coordination with the Florida Department of Transportation and Broward County Traffic Engineering. | 1292 | Lisa Marie Glover |  |  |  | TAM | TAM | 11 | Hold | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 730972 | 35212.4 | 138003.6 | 0 | 557756 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 730972 |  | 72729 | 1/4/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 38 | Transportation and Mobility | Transportation | General Upgrades |  |  | 9/22/2020 16:47 |  |  | No
Public Works | P12833 | EV CHARGER INSTALLATION AT CITY FACILITIES | This project is for the purchase and installation of additional electric vehicle (EV) chargers at City-owned facilities. With this project the goal is to install approximately fifteen (15) EV chargers per fiscal year. Staff will focus on City facilities where City vehicles are parked overnight including the following facilities: City Hall the Parks and Recreation Headquarters the Public Works building at NW 38th Street and the Development Services building. | 1170 | Omar Castellon |  |  | Sandy Leonard | PBS | PBS | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  | 583 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 200000 | 0 | 0 | 0 | 200000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 200000 |  | 65496 | 10/27/2022 0:00 |  | STATUS | Yes | Yes | 8 | 33 | 34 | Public Works | Fleet | New Construction |  |  | 9/14/2022 14:00 |  |  | No
Parks and Rec | P12671 | SISTRUNK PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sistrunk Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include flag stage access and walkway ramp compliance. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 428000 | 0 | 0 | 0 | 428000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 428000 |  | 72991 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:31
Department of Sustainable Development | P12560 | PURCHASE AND RENOVATION OF GREG BREWTON CENTER (DSD) | The Greg Brewton Department of Sustainable Development building is a city building that has been in service for over 15 years. The building and associated parking areas were purchased by the building fund in February 2020. As a result of this purchase DSD will consolidate capital improvement projects focused on building upgrades/improvements delayed or deferred due to funding. | 1265 | Mark Leibowitz |  |  |  | DSD | DSD | 25 | Implementation | 22 | CityFacilities | No |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 19067120 | 1094162.73 | 80943.34 | 0 | 17892013.93 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 19067120 |  | 73297 | 2/5/2024 0:00 |  | STATUS | Yes | No | [6 empty] | No | No | 11/7/2019 9:13
Public Works | P12764 | FXE RUNWAY 9-27 REHABILITATION PROJECT | Design and construction of the pavement rehabilitation of Runway 9-27. The project would include the removal of existing pavement preparation of limerock subgrade and the construction of new pavement with new or recycled materials. The adjacent taxiway intersections will also be milled and re-surfaced as part of this project. New striping will be applied after the paving has been completed | 865 | Khant Myat |  |  | Khant Myat | CM | PBS | 4 | Bidding | 3 | Airport | Yes |  | 468 | No | Yes | -1 | 0 | 0 | 0 | [8 empty] | 9000000 | 9500000 | 573678 | 180.6 | 0 | 0 | 573497.4 | PLANNING |  |  | 7/22/2022 0:00 | 1/31/2023 0:00 |  | DESIGN |  |  | 2/1/2023 0:00 | 8/1/2023 0:00 |  | BIDDING |  |  | 8/2/2023 0:00 | 3/1/2024 0:00 |  | CONST |  |  | 3/2/2024 0:00 | 10/6/2024 0:00 |  | WARRANTY |  |  | 10/7/2024 0:00 | 10/7/2025 0:00 | [6 empty] | 573678 |  | 70022 | 7/7/2023 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 34 | City Manager's Office | Airport | New Construction | No | Yes | 5/25/2022 10:11 |  |  | No
Transportation and Mobility | P12880 | PARKING FACILITY ELECTRIC VEHICLE CHARGING STATIONS | This project is for the purchase and installation of 100 additional electric vehicle (EV) charging stations over a five-year period at City parking facilities. Transportation and Mobility (TAM) is seeking to increase the number of EV charging stations at City parking facilities to ensure that this public service is distributed throughout the community. This project will also help accelerate decarbonization of the transportation sector. |  |  |  |  | Bryan Green | TAM | TAM | 1 | Project Initiation & Planning | 17 | Parking | No |  | 461 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 150000 | 0 | 0 | 0 | 150000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 150000 |  | 73217 | 1/29/2024 0:00 |  | STATUS | Yes | Yes | 10 | 83 | 34 | Transportation and Mobility | Parking Systems | New Construction |  |  | 9/25/2023 20:06 |  |  | No
Parks and Rec | P12667 | PROVIDENT PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Provident Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include picnic tables and pathways. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 5000 | 0 | 0 | 0 | 5000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 5000 |  | 72988 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:29
Parks and Rec | P12758 | FORT LAUDERDALE BEACH IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Fort Lauderdale Beach Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include fitness equipment improvements ADA routes and surfaces parking lot park pathways signage ADA picnic tables showers boat storage playground improvements basketball courts and volleyball courts. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 1300000 | 0 | 0 | 0 | 1300000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1300000 |  | 72935 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 5/5/2022 11:03 |  |  | No
Parks and Rec | P12648 | CORTEZ TRIANGLE PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Cortez Triangle Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include a pathway accessible route and benches. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 81000 | 0 | 0 | 0 | 81000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 81000 |  | 72951 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:21
Parks and Rec | P12685 | SUNSET PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sunset Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include sidewalk access improvements pathway access restrooms improvements and addition of accessible parking spaces. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 1029000 | 315804.7 | 8217.32 | 0 | 704977.98 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1029000 |  | 73006 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/7/2021 13:48
Public Works | P12702 | GTL SLUDGE HOLDING TANK COVERS AND ROOF | This project is for the replacement of the asphalt membrane roof the replacement of the steel cover and associated water piping (with a flat aluminum cover and a new pipe) and for the reconfiguration of odor control ductwork at George T. Lohmeyer Wastewater Treatment Plant. | 1257 | Justin Murray |  |  |  | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 451 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 2696822 | 0 | 0 | 2696822 | 0 | PLANNING |  |  | 10/1/2021 0:00 | 1/1/2022 0:00 |  | DESIGN |  |  | 1/2/2022 0:00 | 4/1/2022 0:00 |  | BIDDING |  |  | 4/2/2022 0:00 | 10/1/2022 0:00 |  | CONST |  |  | 10/2/2022 0:00 | 4/1/2023 0:00 |  | WARRANTY |  |  | 4/2/2023 0:00 | 4/2/2024 0:00 | [6 empty] | 2696822 |  | 67727 | 2/28/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/15/2021 9:37
Parks and Rec | P12664 | NORTH FORK RIVERFRONT PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of North Fork Riverfront Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches replacement picnic tables replacement trash can relocation and accessible route to Kayak launch. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 172000 | 0 | 0 | 0 | 172000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 172000 |  | 72985 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:28
Parks and Rec | P12839 | FIRE STATION 35 ROOF REPLACEMENT | Roof repairs at Fire Station 35. | 1142 | Corey Callier |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  | 331 | Yes | No | -1 | 0 | 0 | 0 | [10 empty] | 100000 | 76463 | 0 | 0 | 23537 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 100000 |  | 71803 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 11/2/2022 16:09 | No | No | No
Public Works | P12862 | PROSPECT WELLFIELD ELECTRICAL & SIGNAL IMPROVEMENTS | This project is to install parallel conduits for electrical and signal cables to four wells numbers 37 43 38 & 44. For the electrical supply the city will provide one electrical junction box and lid for contractor installation at each well and contractor will install one conduit for each well and install electrical cables. The city will splice the electrical cables and connect them to the power supply and the well pump motors control centers. For the signal work the contractor will furnish and install two conduits and furnish and install one junction box at each well. The city will supply splice and connect the signal cables. The city will disconnect and abandon or recycle the old electrical cables after completion of this project. | 894 | Steve Hillberg |  |  | Talal Abi-Karam | PBS | PBS | 4 | Bidding | 37 | Water Sewer | No | PBS | 454 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 397260 | 0 | 0 | 0 | 397260 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 397260 |  | 73590 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 34 | Public Works | Water Sewer | New Construction | No | No | 9/21/2023 14:13 |  |  | No
Parks and Rec | P12635 | DISTRICT 3 - NW 6TH STREET | Land Acquisition for Parks Bond projects in District 3. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 129087 | 129087.5 | 0 | 0 | -0.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 129087 |  | 71798 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 45 | Parks and Recreation | General Parks | Purchase | No | No | 2/9/2021 16:16
Transportation and Mobility | P12737 | NAUTICAL PARKING LOT IMPROVEMENTS | This project includes the improvement of the Nautical parking lot. This parking lot with 58 parking spaces needs milling and resurfacing pavement markings drainage cleaning and replacement of curbing landscaping and irrigation. This project will be for the construction activities related to the improvements. | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 4 | Bidding | 17 | Parking | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 250000 | 1227.56 | 0 | 242511.13 | 6261.31 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 250000 |  | 73510 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 10 | 31 | 38 | Transportation and Mobility | Lots | General Upgrades |  |  | 2/2/2022 15:39 |  |  | Yes
Parks and Rec | P12843 | BEACH COMMUNITY CENTER | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of the Beach Community Center. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include gym access sidewalk improvements accessible parking benches restrooms solar panels parking structure rooftop park center renovations security lighting and patio furnishings. The proposed funding source for this project is Park Bond Funds 353 | 1278 | Alex Torres |  |  | Alex Torres | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 531750 | 0 | 0 | 0 | 531750 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 531750 |  | 73018 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 28 | 34 | Parks and Recreation | Facilities | New Construction | No | No | 1/11/2023 8:42 |  |  | No
Parks and Rec | P12777 | SUNRISE MIDDLE SCHOOL PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Sunrise Middle School Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include fencing pool chiller field pavilion demo/entryway and site improvements and track resurfacing | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 1725000 | 24375.84 | 217074.48 | 0 | 1483549.68 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1725000 |  | 72942 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 6/10/2022 10:00 |  |  | Yes
Parks and Rec | P12867 | MAUSOLEUM ROOF REPLACEMENT - LAUDERDALE MEMORIAL PARK CEMETERY | This project supports the mausoleum roof replacement at Lauderdale Memorial Park Cemetery. | 1381 | Raymond Myers |  |  | Carl Williams | PKR | PKR | 1 | Project Initiation & Planning | 26 | Roof | No |  |  |  |  | 0 | 0 | 0 | -1 | [10 empty] | 516890 | 0 | 0 | 0 | 516890 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 516890 |  | 73779 | 3/6/2024 0:00 |  | STATUS | Yes | Yes | 6 | 28 | 38 | Parks and Recreation | Facilities | General Upgrades |  |  | 9/25/2023 20:03 |  |  | No
Transportation and Mobility | P12738 | VENICE LOT PARKING INPROVEMENTS | This project includes the improvement of the Venice parking lot. The parking lot needs milling and resurfacing replacement of curbing in some sections irrigation updates and new pavement markings. | 1373 | Mitxi Sanchez |  |  |  | TAM | TAM | 4 | Bidding | 17 | Parking | No |  |  | Yes |  | 0 | 0 | 0 | -1 | [10 empty] | 220000 | 26551.1 | 0 | 59000 | 134448.9 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 220000 |  | 73506 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 10 | 31 | 35 | Transportation and Mobility | Lots | Renovation |  |  | 2/4/2022 7:16 |  |  | Yes
Parks and Rec | P12779 | THURGOOD MARSHALL ELEMENTARY PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Thurgood Marshall Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include playground installation court renovations and walking trails. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 400000 | 2111.36 | 20444.36 | 0 | 377444.28 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 400000 |  | 72944 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 38 | Parks and Recreation | General Parks | General Upgrades |  |  | 6/10/2022 10:07 |  |  | Yes
Parks and Rec | P12757 | FLORANDA PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Floranda Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include bleachers shade playground athletic field lighting upgrade site furnishings restroom renovation ADA sidewalk pavilion picnic tables ADA restrooms park entrances ADA water fountain BBQ grill surfacing and ADA bleachers. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 126218 | 0 | 0 | 0 | 126218 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 126218 |  | 73013 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 11:02 |  |  | No
Department of Sustainable Development | P12235 | LAND & ASSET MANAGEMENT SYSTEM PROJECT | The current land management software solution Community Plus is obsolete that no longer offers the functionality needed by the Community and the multiple Departments it serves. In addition the software is running on unsupported hardware and legacy database management system. The adoption of a new and resourceful software system is in alignment with strategic goals focused on business development neighborhood enhancement and internal support. Community Plus is composed of seven modules or applications utilized as the backbone operations for Permitting Planning Code Business Tax Fire Prevention Alarm Billing and Special Assessments. Replacement of Community Plus must include the replacement of all seven applications. |  |  |  |  | Simeon Ivanov | DSD | DSD | 15 | Complete | 22 | CityFacilities | No |  | 331 | Yes | No | -1 | -1 | -1 | -1 | [10 empty] | 5209899 | 5180180.25 | 0 | 0 | 29718.75 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 5209899 |  | 71808 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 2 | 64 | 39 | Dept. of Sustainable Development | Budget Office | Technology | No | No | 7/5/2016 8:13
Parks and Rec | P12751 | BENNESON PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Benneson Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include security lighting basketball/tennis/pickleball renovations park benches park signage park entrances sidewalk improvements ADA picnic tables ADA park furnishings and ADA playground. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 412500 | 0 | 0 | 0 | 412500 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 412500 |  | 73008 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/5/2022 10:52 |  |  | Yes
Parks and Rec | P12161 | FACILITY ASSESSMENT - ROOFING PRIORITIES | This project supports the repair and replacement of roofs roof finishes roof openings gutters and downspouts at the Fire Prevention Bureau Parks/Fleet Compound Las Olas Marina Beach Maintenance Building and Carter Hardy Riverland Holiday Osswald and Floyd Hull Parks. | 1143 | Enrique Sanchez |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | No | No | 0 | -1 | -1 | -1 | [10 empty] | 269555.36 | 112169.25 | 0 | 0 | 157386.11 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 269555.36 |  | 73130 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 |  | 35 | Parks and Recreation |  | Renovation | No | No | 8/12/2015 9:26
Parks and Rec | P12162 | FACILITY ASSESSMENT - HVAC ELECTRICAL & PLUMBING PRIORITIES | This project supports the repair and replacement of all equipment distribution systems controls and energy supply systems required by the heating ventilating and air conditioning system; electrical distribution systems including panels lighting end devices and emergency power generation; plumbing fixtures and domestic water distribution. The projects will be completed throughout the City at Fire Station 2 Fire Prevention Bureau Parks/Fleet Compound War Memorial Auditorium Beach Community Center and Carter Floyd Hull Holiday Oswald Croissant Lauderdale Manors Warfield Hardy Riverside and Mills Pond Parks. | 1143 | Enrique Sanchez |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | No | No | -1 | -1 | -1 | -1 | [10 empty] | 4171053.52 | 61246.54 | 10156.94 | 0 | 4099650.04 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 4171053.52 |  | 73131 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 |  |  | Parks and Recreation |  |  | No | No | 8/12/2015 9:39
Public Works | P12885 | TARPON RIVER STORMWATER IMPROVEMENTS | This project is for the replacement of the SE 8th Street bridge. The bridge requires numerous repairs and if not fixed the Florida Department of Transportation (FDOT) could downgrade the bridge weight capacity or close the bridge entirely. | 1357 | Deborah Cueva |  |  | Rares Petrica | PBS | PBS | 1 | Project Initiation & Planning | 36 | Stormwater | No | PBS | 331 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 564950 | 0 | 0 | 0 | 564950 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 564950 |  | 73750 | 3/1/2024 0:00 | 3/1/2024 0:00 | STATUS | Yes | Yes | 8 | 25 | 36 | Public Works | Bridges | Replacement | No | No | 9/25/2023 20:08 | No | No | No
Transportation and Mobility | P12739 | PELICAN LOT PARKING IMPROVEMENTS | This project includes the improvements of the Pelican parking lot. The parking lot needs milling and resurfacing replacement of curbing in some sections irrigation updates and new pavement markings. | 1373 | Mitxi Sanchez |  |  |  | TAM | TAM | 4 | Bidding | 17 | Parking | No |  |  |  |  | 0 | 0 | 0 | -1 | [9 empty] | 100000 | 220000 | 19948.75 | 0 | 0 | 200051.25 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 220000 |  | 73507 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 10 | 31 | 35 | Transportation and Mobility | Lots | Renovation |  |  | 2/4/2022 7:28 |  |  | Yes
Public Works | P12888 | WATERSHED ASSET MANAGEMENT PLAN (WAMP) - CONDITION ASSESSMENT | The City published its Watershed Asset Management Plan (WAMP) in Dec 2019. The initial plan development and implementation efforts were funded for five years. In that time the City made great strides in developing an improved asset registry identifying critical assets and developing a Condition Assessment Plan. This condition assessment will include 190 miles of underground pipes and 14500 discrete assets like catch basins and pump stations. As a strategic planning initiative mirroring similar efforts in water and wastewater continuing to support the development of the storm water WAMP is part of the City's long-term vision. | 716 | Elkin Diaz |  |  | Elkin Diaz | PBS | PBS | 10 | Annual | 36 | Stormwater | No |  | 470 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 3750000 | 0 | 0 | 3750000 | 0 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 3750000 |  | 72358 | 12/4/2023 0:00 |  | STATUS | Yes | Yes | 8 | 11 | 68 | Public Works | Stormwater | Study/Investigation |  |  | 9/25/2023 20:08 | No | No | No
Parks and Rec | P12838 | PRINT SHOP ROOF REPLACEMENT | Repair the roof at the City of Fort Lauderdale Print Shop | 1142 | Corey Callier |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 26 | Roof | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 153397 | 113644 | 0 | 0 | 39753 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 153397 |  | 71802 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 36 | Parks and Recreation | General Parks | Replacement | No | No | 10/26/2022 13:34 |  |  | No
Public Works | P12868 | WELLFIELD COMMUNICATIONS | This project is for installing a hardened communication network throughout the Prospect Wellfield. | 961 | Jud Hopping |  |  | Jud Hopping | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 300000 | 0 | 0 | 0 | 300000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 300000 |  | 71899 | 10/26/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 38 | Public Works | Water Sewer | General Upgrades |  |  | 9/25/2023 20:03 |  |  | No
Public Works | P12628 | INTERLOCAL AGREEMENT WITH POMPANO BEACH | The City of Fort Lauderdale has water distribution system interconnects with neighboring Utilities including Broward County the City of Plantation and the City of Pompano Beach. The interconnects are used mutually in times of need to assist the neighboring utilities with maintaining water demand when performing maintenance of treatment facilities or during emergencies such as treatment plant or water distribution system failures. The existing interconnects are not metered; thus the Utilities do not have the ability to measure or quantify the water used or provided. Therefore there is no accounting of non-revenue water and no ability to bill the consuming utility for water provided. |  |  |  |  | Omar Castellon | PBS | PBS | 1 | Project Initiation & Planning | 23 | Utilities | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 299455 | 0 | 0 | 299455 | 0 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  | 2/14/2022 0:00 |  |  | WARRANTY | [10 empty] | 299455 |  | 71903 | 10/26/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 35 | Public Works | Water Sewer | Renovation | No | No | 12/4/2020 12:01 |  |  | No
Transportation and Mobility | P12890 | ARTS & SCIENCES DISTRICT GARAGE ELEVATOR UPGRADES | The State of Florida implemented new code requirements on all elevators. Broward County is now requiring these codes to be met by December 31 2023. |  |  |  |  | Bryan Green | TAM | TAM | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  |  |  |  | 0 | -1 | 0 | 0 | [10 empty] | 169390 | 0 | 0 | 0 | 169390 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 169390 |  | 73218 | 1/29/2024 0:00 |  | STATUS | Yes | Yes | 10 | 28 | 38 | Transportation and Mobility | Facilities | General Upgrades |  |  | 9/25/2023 20:09 |  |  | No
Parks and Rec | P12666 | PETER FELDMAN PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Peter Feldman Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include high efficiency security lighting electrical upgrades for events and playground surfacing/shade improvements. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 425000 | 0 | 0 | 0 | 425000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 425000 |  | 72987 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:29
Parks and Rec | P12676 | TARPON RIVER PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Tarpon River Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches surfacing and park garbage can relocation. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 59000 | 0 | 0 | 0 | 59000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 59000 |  | 72998 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:33
Community Redevelopment | P12373 | DC ALEXANDER PARK IMPROVEMENTS | DC Alexander Park is over one (1) acre in area. The proposed improvements shall include a signature family-oriented artistic interactive appurtenance that will transform the park into a destination location. Other improvements include a restroom facility with attached concession stand shaded seating areas inviting greenspace and landscape areas removing the existing parking lot providing turtle-compliant lighting security cameras and security call boxes.SE 5th Street is immediately north of DC Alexander Park. Proposed improvement to include two-waying the street removing on-street parking installing turtle-compliant lighting and widening the sidewalk on the south side of street. Improvements to SE 5th Street are part of this project. The project delivery method for this proj | 1320 | Marc Isaac |  |  |  | DSD | CRA | 6 | Construction | 12 | Parks | No |  | 343 | No | No | 0 | -1 | 0 | 0 | [10 empty] | 10189906 | 6314737.36 | 3746986.9 | 0 | 128181.74 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 10189906 |  | 73019 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 2 | 74 | 34 | Dept. of Sustainable Development | Beach CRA | New Construction | No | No | 11/13/2017 16:16 |  |  | No
Public Works | P12703 | SLUDGE FLOW METER REPLACEMENT | This project is for the replacement of approximately 20 Flow Meters across the George T. Lohmeyer Wastewater Treatment Plant. The flow meters are used to monitor and control the treatment process flows. | 1257 | Justin Murray |  |  |  | PBS | PBS | 1 | Project Initiation & Planning | 37 | Water Sewer | No |  | 451 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 500000 | 0 | 0 | 0 | 500000 | PLANNING |  |  | 10/1/2021 0:00 | 1/1/2022 0:00 |  | DESIGN |  |  | 1/2/2022 0:00 | 6/1/2022 0:00 |  | BIDDING |  |  | 6/2/2022 0:00 | 12/1/2022 0:00 |  | CONST |  |  | 12/2/2022 0:00 | 6/1/2023 0:00 |  | WARRANTY |  |  | 6/2/2023 0:00 | 6/2/2024 0:00 | [6 empty] | 500000 |  | 67728 | 2/28/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/15/2021 9:38
Parks and Rec | P12662 | LU DEANER PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Lu Deaner Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include pathways picnic tables surfacing drinking fountain surfacing benches relocation and exercise equipment surfacing. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 215000 | 0 | 0 | 0 | 215000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 215000 |  | 72962 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:27
City Manager | P12882 | RUNWAY 9 WESTERN EXTENSION & PARALLEL TAXIWAY EXTENSION | This project consists of design and construction for the western extension of Runway 9 by approximately 1000 feet and constructing connecting taxiways to join to Taxiways Foxtrot and Echo. Additionally the first 1000 feet of the approach lighting system lights will be converted to in-ground lights (in the extended runway centerline pavement). New light -emitting-diode (LED) runway edge-lights guidance signs striping sodding will be installed as part of the project. An update to the airport lighting control and monitoring (ALCM) system will also be part of this design. The project also includes the design and construction of Taxiway Echo on the south end to the construction of a new taxiway on the north end in anticipation of the extension of runway 9. | 865 | Khant Myat |  |  | Khant Myat | CM | CM | 1 | Project Initiation & Planning | 3 | Airport | No |  | 468 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 75655 | 0 | 0 | 0 | 75655 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 75655 |  | 71966 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 84 | 9 | 43 | City Manager's Office | Airport | Rehabilitation |  |  | 9/25/2023 20:07 |  |  | No
Parks and Rec | P12793 | STREETLIGHT IMPROVEMENTS | The Fort Lauderdale Street Lighting Master Plan established lighting standards and guidelines for light assemblies (i.e. poles and fixtures). This project is designed to implement improvements listed in the master plan and earmark funding for analysis for Las Olas Boulevard - $260000 NE 4th Avenue - $289000 Riverland Road Neighborhood - $825000 Flagler Village Area - $1903000 and Himmarshee Area - $962000 |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 1000000 | 55481 | 69905 | 0 | 874614 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 1000000 |  | 73142 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 24 | 36 | Parks and Recreation | Transportation | Replacement |  |  | 9/14/2022 13:30 |  |  | No
Parks and Rec | P12659 | LAUDERDALE MANORS ENTRANCE IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Lauderdale Manors Park Entrance Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include native planting playground installation pavilion and park signage. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 235000 | 0 | 0 | 0 | 235000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 235000 |  | 72959 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:26
Parks and Rec | P12164 | FACILITY ASSESSMENT - INTERIOR REPAIR/CONSTRUCTION | This project supports the repair and replacement of the interior windows and doors interior finishes of walls floors and ceilings stair construction and handrails at the Fire Prevention Bureau Fire Stations 2 3 29 35 46 47 49 and 53 Parks/Fleet Compound War Memorial Auditorium and Carter Floyd Hull George English and Holiday Bass Oswald and Warfield Parks. | 1143 | Enrique Sanchez |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | No | No | -1 | -1 | -1 | -1 | [10 empty] | 261144.16 | 61144.16 | 0 | 0 | 200000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 261144.16 |  | 73133 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 |  |  | Public Works |  |  | No | No | 8/12/2015 10:22
Parks and Rec | P12677 | TOWNSEND PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Townsend Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches relocation picnic tables surfacing picnic tables replacement accessible route to benches & picnic tables trash can relocation handrail barrier and tactile warning device relocation. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 63000 | 0 | 0 | 0 | 63000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 63000 |  | 72999 | 1/18/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:33
Parks and Rec | P12633 | HOLIDAY PARK IMPROVEMENT PROJECT | This project is for the design and construction of the Holiday Park Improvements. The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include site improvements parking garage site/sport lighting tennis courts substation splash pad/water feature landscaping shade structures and renovations to the activity center | 1320 | Marc Isaac |  |  | Thomas Green | PKR | PKR | 2 | Design | 12 | Parks | No |  | 353 | Yes | Yes | 0 | -1 | 0 | 0 | [10 empty] | 20950000 | 2515226.54 | 593458.99 | 0 | 17841314.47 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 20950000 |  | 72927 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction | No | No | 2/9/2021 14:26 |  |  | Yes
Parks and Rec | P12773 | DILLARD 6-12 PARK IMPROVEMENTS | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Dillard 6-12 Improvement Project. AECOM will perform the following work on this project: The City is looking to expand park access for City residents at school sites throughout the City.Â Improvements at this site will include tennis court renovations. | 1320 | Marc Isaac |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | -1 | 0 | [10 empty] | 100000 | 908.47 | 1788.36 | 0 | 97303.17 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 100000 |  | 72938 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 6/10/2022 9:57 |  |  | Yes
Public Works | P12889 | BULK PETROLEUM FLUID TANKS AT FLEET SERVICES | This project will fund the purchase and installation of three (3) additional petroleum bulk storage tanks as well as the refurbishment of the one (1) existing bulk petroleum storage tank in the Maintenance Bays at Fleet Services. These tanks will be used to store fluids such as engine and hydraulic system additives as well as oils used in larger volume by Fleet Services. | 1382 | Drew Newstrom |  |  | Drew Newstrom | PBS | PBS | 1 | Project Initiation & Planning | 22 | CityFacilities | No | PBS | 583 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 113677 | 0 | 0 | 0 | 113677 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 113677 |  | 71972 | 10/24/2023 0:00 |  | STATUS | Yes | Yes | 8 | 28 | 41 | Public Works | Facilities | Equipment | No | No | 9/25/2023 20:09 | No | No | No
Transportation and Mobility | P12598 | RIVERLAND ROAD TRAFFIC CALMING | This project will design and construct traffic calming improvements along Riverland Road between State Road 7 and Davie Blvd to complement the Complete Streets project which is being constructed by the Broward Metropolitan Planning Organization (MPO) through Transportation Investments Generating Economic Recovery (TIGER) grants. The concept plan includes raised intersections at Okeechobee Lane SW 35th Avenue SW 14th Street and SW 18th Street as well as a Traffic Circle at SW 31st Avenue. The project will include mini-medians between the intersection improvements to help reduce vehicle passing and to slow vehicles. Additionally the project will add Wave Delineators where possible to create a separation of the bike lane from the vehicle travel lane. | 1210 | Karen Warfel |  |  |  | TAM | TAM | 2 | Design | 27 | Roadway Improvements | No |  | 331 | Yes | Yes | 0 | 0 | -1 | -1 | [10 empty] | 202600 | 119236 | 79384 | 0 | 3980 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 202600 |  | 73005 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | 10 | 23 | 38 | Transportation and Mobility | General Services | General Upgrades |  |  | 9/22/2020 16:46
Public Works | P12417 | MISCELLANEOUS WATER QUALITY IMPROVEMENTS | Investigate adding additional automatic flushers at the following locations to reduce water age: PLUG_F10015 â€“Snyder ParkPLUG_F5472 â€“ SW 15th Avenue/SW 33rd StreetPLUG_F4373 â€“ SW 32nd PlacePLUG_F4366 â€“ SW 32nd Street | 894 | Steve Hillberg |  |  | Steve Hillberg | PBS | PBS | 6 | Construction | 37 | Water Sewer | No | CO | 495 |  | Yes | 0 | 0 | 0 | -1 | [10 empty] | 69000 | 0 | 0 | 0 | 69000 | PLANNING |  |  | 8/2/2021 0:00 | 1/31/2021 0:00 |  | DESIGN |  |  | 1/31/2022 0:00 | 3/31/2023 0:00 |  | BIDDING |  |  | 3/31/2023 0:00 | 7/31/2023 0:00 |  | CONST |  |  | 7/31/2023 0:00 | 9/30/2023 0:00 |  | WARRANTY |  |  | 9/1/2024 0:00 | 9/1/2025 0:00 | [6 empty] | 69000 |  | 73586 | 2/16/2024 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 34 | Public Works | Water Sewer | New Construction | No |  | 1/24/2018 11:11 |  |  | No
Parks and Rec | P12647 | COLEE HAMMOCK PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Colee Hammock Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include an access route to existing monument park walkways benches picnic tables and park furnishings.The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  | 353 | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 245000 | 0 | 0 | 0 | 245000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 245000 |  | 72950 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:21
Parks and Rec | P12575 | CITY HALL 8TH FLOOR RENOVATIONS | The project will include a redesign of the 8th floor Commission offices to better accommodate the additional staff working in the Commission office.Â The project will include an expansion of the office area and redesign the common space to better accommodate Commission assistants and aides while maintaining Sunshine governance rules. | 1143 | Enrique Sanchez |  |  | Enrique Sanchez | PKR | PKR | 15 | Complete | 12 | Parks | No |  |  | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 65983 | 65982.62 | 0 | 0 | 0.38 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 65983 |  | 71796 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 35 | Parks and Recreation | General Parks | Renovation | No | No | 3/6/2020 9:16
Public Works | P12602 | GTL BUILDING INFRASTRUCTURE REPLACEMENT | This project will replace various corroded concrete steel and other critical building components at the George T. Lohmeyer Wastewater Treatment Plant (GTL) that are failing or near failure. These components include but not limited to electrical supports Heating Ventilation Air Conditioning (HVAC) ductwork large and small diameter ductile iron process pipe roof drains and windows. | 1257 | Justin Murray |  |  |  | PBS | PBS | 4 | Bidding | 23 | Utilities | No |  | 451 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 400000 | 155268 | 79229 | 95000 | 70503 | PLANNING | [5 empty] | DESIGN |  |  | 9/1/2021 0:00 | 11/30/2021 0:00 |  | BIDDING |  |  | 12/1/2021 0:00 | 2/28/2022 0:00 |  | CONST |  |  | 3/1/2022 0:00 | 7/31/2022 0:00 |  | WARRANTY |  |  | 8/1/2022 0:00 | 7/31/2023 0:00 | [6 empty] | 400000 |  | 67725 | 2/28/2023 0:00 |  | STATUS | Yes | Yes | 8 | 12 | 36 | Public Works | Water Sewer | Replacement |  |  | 9/22/2020 16:47
Parks and Rec | P12854 | FIRE STATION 54 GENERATOR AUTOMATIC TRANSFER SWITCH REPLACEMENT | Replacement of the automatic transfer switch for the generator at Fire Station 54. | [5 empty] | PKR | PKR | 1 | Project Initiation & Planning | 22 | CityFacilities | No |  |  | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 60000 | 0 | 51134 | 0 | 8866 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 60000 |  | 73190 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 6/16/2023 9:06 |  |  | No
Transportation and Mobility | P12877 | GALT SHOPS WEST IMPROVEMENTS | The Parks and Recreation Department has plans to add a second level to an existing parking facility to create a rooftop park. To accommodate adding a structure above the parking facility the Transportation and Mobility Department will need to redesign the existing parking lot. This project also includes funding to mill and resurface the existing parking lot and other general improvements. | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 1 | Project Initiation & Planning | 17 | Parking | No |  |  | Yes | No | -1 | -1 | 0 | 0 | [10 empty] | 750000 | 2807.5 | 13950 | 0 | 733242.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 750000 |  | 73513 | 2/15/2024 0:00 |  | STATUS | Yes | Yes | 10 | 83 | 34 | Transportation and Mobility | Parking Systems | New Construction | No | No | 9/25/2023 20:06 | No | No | Yes
Fire Department | P12503 | LIFEGUARD TOWER REPLACEMENTS | The Fort Lauderdale Fire Rescue Department is requesting to fund a replacement plan for existing Lifeguard towers.The Fort Lauderdale Ocean Rescue Division covers three miles of public beach with twenty lifeguard towers spaced approximately 265 yards apart. | 1277 | robert bacic |  |  |  | FIR | FIR | 25 | Implementation | 14 | Fire | No |  |  |  | Yes | -1 | -1 | -1 | -1 | [10 empty] | 489984 | 268450 | 0 | 0 | 221534 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 489984 |  | 73214 | 1/29/2024 0:00 |  | STATUS | Yes | Yes | 3 | 18 | 36 | Fire | General Fire | Replacement | No | No | 4/26/2019 10:59 |  |  | No
Community Redevelopment | P12166 | OFF-STREET PARKING | This project provides funding for the construction of public off street parking improvements and parking improvements for vacant lots along Sistrunk. | 1017 | Bob Wojcik |  |  |  | CRA | CRA | 6 | Construction | 17 | Parking | No |  | 347 | No | No | 0 | 0 | -1 | 0 | [10 empty] | 670053.01 | 649098.64 | 20954 | 0 | 0.37 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 670053.01 |  | 73036 | 1/18/2024 0:00 | 1/18/2024 0:00 | STATUS | Yes | Yes | [6 empty] | No | No | 8/12/2015 11:03
Public Works | P12255 | GEORGE T. LOHMEYER (GTL) EXTERIOR PAINTING | This project is for a protective coating application on all exterior surfaces at the George T. Lohmeyer Water Treatment Plant. It must be implemented between major exterior construction projects to avoid damaging new protective coatings. | 1257 | Justin Murray |  |  |  | PBS | PBS | 6 | Construction | 22 | CityFacilities | No |  |  | Yes | Yes | 0 | 0 | 0 | -1 | [10 empty] | 271380 | 16517.97 | 0 | 254862.03 | 0 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST |  |  | 6/1/2021 0:00 | 6/1/2025 0:00 |  | WARRANTY |  |  | 6/2/2025 0:00 | 6/2/2026 0:00 | [6 empty] | 271380 |  | 62961 | 8/1/2022 0:00 |  | STATUS | Yes | Yes | 8 | 65 | 38 | Public Works | Engineering | General Upgrades | No | No | 8/16/2016 11:13
Transportation and Mobility | P12878 | NORTH & SOUTH GALT LOT IMPROVEMENTS | Transportation and Mobility is seeking to improve the North and South Parking Lots located at 3500 Galt Ocean Drive. These improvements include the enhancement of ADA (Americans with Disabilities) accessible ramps from the parking lot to the sidewalk the milling and resurfacing of the parking lot the application of thermal pavement markings and other general improvements. | 1373 | Mitxi Sanchez |  |  |  | TAM | TAM | 1 | Project Initiation & Planning | 17 | Parking | No |  | 461 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 250000 | 0 | 72981.5 | 0 | 177018.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 250000 |  | 73769 | 3/4/2024 0:00 | 3/4/2024 0:00 | STATUS | Yes | Yes | 10 | 83 | 38 | Transportation and Mobility | Parking Systems | General Upgrades |  |  | 9/25/2023 20:06 |  |  | No
Parks and Rec | P12850 | SOUTH SIDE CULTURAL ARTS CENTER HVAC SYSTEM REDESIGN | Evaluate and re-design the HVAC system at South Side Cultural Arts Center. |  |  |  |  | Enrique Sanchez | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | No | Yes | 0 | 0 | 0 | -1 | [10 empty] | 40000 | 24000 | 7000 | 13235 | -4235 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 40000 |  | 73145 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 5/12/2023 16:19 |  |  | No
Transportation and Mobility | P12810 | PARKING WAYFINDING BARRIER ISLAND SIGNAGE | This project includes the installation of wayfinding signs in the Barrier Island area. The signs to be installed are Vehicular Directional Parking Identity Parking Directional Bicycle Parking and Pedestrian Directional signs in various locations within the Barrier Island. | 1367 | Caroline Yeakel |  |  |  | TAM | TAM | 2 | Design | 22 | CityFacilities | No |  | 461 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 375000 | 43256 | 30610.5 | 0 | 301133.5 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 375000 |  | 72721 | 1/3/2024 0:00 |  | STATUS | Yes | Yes | 10 | 24 | 38 | Transportation and Mobility | Transportation | General Upgrades |  |  | 9/14/2022 13:41 |  |  | No
Parks and Rec | P12163 | FACILITY ASSESSMENT - EXTERIOR REPAIR /CONSTRUCTION | This project supports the repair and replacement of roof finishes roof openings gutters and downspouts. In addition to all equipment distribution system; electrical distribution systems including panels lighting end devices and emergency power generation; plumbing fixtures and domestic water distribution. This project will also address deficiencies exterior facing of facilities such as exterior load bearing walls windows columns and finishes such as stucco; floor construction structural frame and roof framework; parking lots fencing and retaining walls; interior windows and doors interior finishes of walls floors and ceiling stair construction and handrails. | 1143 | Enrique Sanchez |  |  |  | PKR | PKR | 1 | Project Initiation & Planning | 12 | Parks | No |  |  | No | No | -1 | -1 | -1 | -1 | [10 empty] | 462500.32 | 243500.32 | 0 | 0 | 219000 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 462500.32 |  | 73132 | 1/22/2024 0:00 |  | STATUS | Yes | Yes | 8 |  |  | Public Works |  |  | No | No | 8/12/2015 9:59 |  |  | No
Parks and Rec | P12645 | BAYVIEW PARK IMPROVEMENT PROJECT | The City of Fort Lauderdale awarded a design consultant agreement to AECOM for implementation and design of the City's Park Bond Program. The design agreement will be administered through task orders and a separate project number will be created for each task order. This project request is for the design and construction of Bayview Park Improvement Project. AECOM will perform the following work on this project: planning design permitting bidding and construction administration. The park will include benches at entrance picnic tables men's restroom water fountain benches and picnic tables under Pavilion. The proposed funding source for this project is Park Bond Funds 353-FD353.01-3199 | 1320 | Marc Isaac |  |  |  | PKR | PKR | 6 | Construction | 12 | Parks | No |  | 353 | Yes | Yes | -1 | 0 | 0 | 0 | [10 empty] | 972000 | 519522.14 | 384987.3 | 0 | 67490.56 | PLANNING | [5 empty] | DESIGN | [5 empty] | BIDDING | [5 empty] | CONST | [5 empty] | WARRANTY | [10 empty] | 972000 |  | 72912 | 1/17/2024 0:00 |  | STATUS | Yes | Yes | 6 | 20 | 34 | Parks and Recreation | General Parks | New Construction |  |  | 5/4/2021 16:20 |  |  | Yes
Public Works | P12564 | C-51 RESERVOIR | The C-51 was first conceptualized in the 1992 Everglades Restoration Plan. The Plan was identified to reduce discharges to the Lake Worth Lagoon. Since 2006 Broward County Palm Beach County and other Lower East Coast area water providers have been collaborating in the development of the C-51 Reservoir to serve as a regional alternative water supply by storing excess wet-season stormwater runoff for later distribution and use during the dry season. | 1016 | Todd Hiteshew |  |  | Todd Hiteshew | PBS | PBS | 6 | Construction | 37 | Water Sewer | No |  | 454 | Yes | Yes | -1 | -1 | -1 | -1 | [10 empty] | 13942530 | 13852399.9 | 0 | 0 | 90130.1 | PLANNING |  |  | 12/17/2019 0:00 | 12/17/2019 0:00 |  | DESIGN |  |  | 12/18/2019 0:00 | 8/31/2020 0:00 |  | BIDDING |  |  | 12/18/2019 0:00 | 8/31/2020 0:00 |  | CONST |  |  | 9/1/2020 0:00 | 9/1/2022 0:00 |  | WARRANTY |  |  | 9/2/2022 0:00 | 9/2/2023 0:00 | [6 empty] | 13942530 |  | 70386 | 7/19/2023 0:00 |  | STATUS | Yes | Yes | [6 empty] | No | No | 12/10/2019 16:15